## Executive Summary
Life in Days — Phase 1 Release Plan | Life in Days — Phase 1 Release Plan | Life in Days — Phase 1 Release Plan | Life in Days — Phase 1 Release Plan | Life in Days — Phase 1 Release Plan | Life in Days — Phase 1 Release Plan | Life in Days — Phase 1 Release Plan | Life in Days — Phase 1 Release Plan | Life in Days — Phase 1 Release Plan | Life in Days — Phase 1 Release Plan | Life in Days — Phase 1 Release Plan | Life in Days — Phase 1 Release Plan | Life in Days — Phase 1 Release Plan | Life in Days — Phase 1 Release Plan | Life in Days — Phase 1 Release Plan | Life in Days — Phase 1 Release Plan | Life in Days — Phase 1 Release Plan | Life in Days — Phase 1 Release Plan | Life in Days — Phase 1 Release Plan | Life in Days — Phase 1 Release Plan | Life in Days — Phase 1 Release Plan
Life in Days — Phase 1 Release Plan | Life in Days — Phase 1 Release Plan | Life in Days — Phase 1 Release Plan | Life in Days — Phase 1 Release Plan | Life in Days — Phase 1 Release Plan | Life in Days — Phase 1 Release Plan | Life in Days — Phase 1 Release Plan | Life in Days — Phase 1 Release Plan | Life in Days — Phase 1 Release Plan | Life in Days — Phase 1 Release Plan | Life in Days — Phase 1 Release Plan | Life in Days — Phase 1 Release Plan | Life in Days — Phase 1 Release Plan | Life in Days — Phase 1 Release Plan | Life in Days — Phase 1 Release Plan | Life in Days — Phase 1 Release Plan | Life in Days — Phase 1 Release Plan | Life in Days — Phase 1 Release Plan | Life in Days — Phase 1 Release Plan | Life in Days — Phase 1 Release Plan | Life in Days — Phase 1 Release Plan
Review workbook generated from PHASE1-ROADMAP-MANIFEST.json on 2026-08-16. Current readiness: 58 Incomplete; 45 Hold + 13 Historical non-authorizing; 0 Ready; 0 execution-allowed. Dates are estimates; evidence gates control delivery. | Review workbook generated from PHASE1-ROADMAP-MANIFEST.json on 2026-08-16. Current readiness: 58 Incomplete; 45 Hold + 13 Historical non-authorizing; 0 Ready; 0 execution-allowed. Dates are estimates; evidence gates control delivery. | Review workbook generated from PHASE1-ROADMAP-MANIFEST.json on 2026-08-16. Current readiness: 58 Incomplete; 45 Hold + 13 Historical non-authorizing; 0 Ready; 0 execution-allowed. Dates are estimates; evidence gates control delivery. | Review workbook generated from PHASE1-ROADMAP-MANIFEST.json on 2026-08-16. Current readiness: 58 Incomplete; 45 Hold + 13 Historical non-authorizing; 0 Ready; 0 execution-allowed. Dates are estimates; evidence gates control delivery. | Review workbook generated from PHASE1-ROADMAP-MANIFEST.json on 2026-08-16. Current readiness: 58 Incomplete; 45 Hold + 13 Historical non-authorizing; 0 Ready; 0 execution-allowed. Dates are estimates; evidence gates control delivery. | Review workbook generated from PHASE1-ROADMAP-MANIFEST.json on 2026-08-16. Current readiness: 58 Incomplete; 45 Hold + 13 Historical non-authorizing; 0 Ready; 0 execution-allowed. Dates are estimates; evidence gates control delivery. | Review workbook generated from PHASE1-ROADMAP-MANIFEST.json on 2026-08-16. Current readiness: 58 Incomplete; 45 Hold + 13 Historical non-authorizing; 0 Ready; 0 execution-allowed. Dates are estimates; evidence gates control delivery. | Review workbook generated from PHASE1-ROADMAP-MANIFEST.json on 2026-08-16. Current readiness: 58 Incomplete; 45 Hold + 13 Historical non-authorizing; 0 Ready; 0 execution-allowed. Dates are estimates; evidence gates control delivery. | Review workbook generated from PHASE1-ROADMAP-MANIFEST.json on 2026-08-16. Current readiness: 58 Incomplete; 45 Hold + 13 Historical non-authorizing; 0 Ready; 0 execution-allowed. Dates are estimates; evidence gates control delivery. | Review workbook generated from PHASE1-ROADMAP-MANIFEST.json on 2026-08-16. Current readiness: 58 Incomplete; 45 Hold + 13 Historical non-authorizing; 0 Ready; 0 execution-allowed. Dates are estimates; evidence gates control delivery. | Review workbook generated from PHASE1-ROADMAP-MANIFEST.json on 2026-08-16. Current readiness: 58 Incomplete; 45 Hold + 13 Historical non-authorizing; 0 Ready; 0 execution-allowed. Dates are estimates; evidence gates control delivery. | Review workbook generated from PHASE1-ROADMAP-MANIFEST.json on 2026-08-16. Current readiness: 58 Incomplete; 45 Hold + 13 Historical non-authorizing; 0 Ready; 0 execution-allowed. Dates are estimates; evidence gates control delivery. | Review workbook generated from PHASE1-ROADMAP-MANIFEST.json on 2026-08-16. Current readiness: 58 Incomplete; 45 Hold + 13 Historical non-authorizing; 0 Ready; 0 execution-allowed. Dates are estimates; evidence gates control delivery. | Review workbook generated from PHASE1-ROADMAP-MANIFEST.json on 2026-08-16. Current readiness: 58 Incomplete; 45 Hold + 13 Historical non-authorizing; 0 Ready; 0 execution-allowed. Dates are estimates; evidence gates control delivery. | Review workbook generated from PHASE1-ROADMAP-MANIFEST.json on 2026-08-16. Current readiness: 58 Incomplete; 45 Hold + 13 Historical non-authorizing; 0 Ready; 0 execution-allowed. Dates are estimates; evidence gates control delivery. | Review workbook generated from PHASE1-ROADMAP-MANIFEST.json on 2026-08-16. Current readiness: 58 Incomplete; 45 Hold + 13 Historical non-authorizing; 0 Ready; 0 execution-allowed. Dates are estimates; evidence gates control delivery. | Review workbook generated from PHASE1-ROADMAP-MANIFEST.json on 2026-08-16. Current readiness: 58 Incomplete; 45 Hold + 13 Historical non-authorizing; 0 Ready; 0 execution-allowed. Dates are estimates; evidence gates control delivery. | Review workbook generated from PHASE1-ROADMAP-MANIFEST.json on 2026-08-16. Current readiness: 58 Incomplete; 45 Hold + 13 Historical non-authorizing; 0 Ready; 0 execution-allowed. Dates are estimates; evidence gates control delivery. | Review workbook generated from PHASE1-ROADMAP-MANIFEST.json on 2026-08-16. Current readiness: 58 Incomplete; 45 Hold + 13 Historical non-authorizing; 0 Ready; 0 execution-allowed. Dates are estimates; evidence gates control delivery. | Review workbook generated from PHASE1-ROADMAP-MANIFEST.json on 2026-08-16. Current readiness: 58 Incomplete; 45 Hold + 13 Historical non-authorizing; 0 Ready; 0 execution-allowed. Dates are estimates; evidence gates control delivery. | Review workbook generated from PHASE1-ROADMAP-MANIFEST.json on 2026-08-16. Current readiness: 58 Incomplete; 45 Hold + 13 Historical non-authorizing; 0 Ready; 0 execution-allowed. Dates are estimates; evidence gates control delivery.
Plan metric | Value | [8 empty] | Status | Tasks
Roadmap tasks | 58 | [8 empty] | Backlog | 40
Done planning tasks | 13 | [8 empty] | Next | 4
In progress | 1 | [8 empty] | In progress | 1
Next | 4 | [8 empty] | Done | 13
Backlog | 40
Milestones | 12
Requirements | 78 | [8 empty] | Milestone | Tasks
Active coverage | 71 | [8 empty] | P0 | 2
Dossiers Ready | 0 | [8 empty] | R0 | 6
Execution allowed | 0 | [8 empty] | R1 | 5
Planning completion | 22.41% | [8 empty] | R2 | 6
[10 empty] | R3 | 5
Council release sequence | Council release sequence | Council release sequence | Council release sequence | Council release sequence | Council release sequence | Council release sequence | Council release sequence |  |  | R4 | 6
Milestone | Release | Start | Target | Outcome | Entry dependency | Tasks | Status note |  |  | R5 | 6
P0 | Council Planning Baseline | 2026-08-14 | 2026-08-16 | A source-grounded, reviewable Product Council package and one canonical delivery manifest. | None | 2 | Evidence-gated estimate |  |  | R6 | 6
R0 | Shared-Host Private Foundation | 2026-08-17 | 2026-08-28 | A synthetic-only private shell can coexist with current services, recover, upgrade, and roll back. | P0 accepted | 6 | Evidence-gated estimate |  |  | R7 | 6
R1 | Manual Journal Archive | 2026-08-31 | 2026-09-18 | First memory-creating release: explicit-date text upload, Calendar, and Journal Day recall. | R0 accepted | 5 | Evidence-gated estimate |  |  | R8 | 4
R2 | Telegram Photo Capture | 2026-09-21 | 2026-10-09 | Authorized durable photo capture with review-safe dating, gallery, cover, duplicates, and privacy-safe derivatives. | R1 accepted | 6 | Evidence-gated estimate |  |  | R9 | 3
R3 | Retrieval and Date Integrity | 2026-10-12 | 2026-10-30 | Cross-month browsing, deterministic search, Needs Date Review, and atomic source redating. | R2 accepted | 5 | Evidence-gated estimate |  |  | R10 | 3
R4 | Source History and Lifecycle Safety | 2026-11-02 | 2026-11-20 | Corrections, upstream conflicts, History, Trash, suppressions, and complete restorable export. | R3 accepted | 6 | Evidence-gated estimate
R5 | Prospective VoiceNotes Sync | 2026-11-23 | 2026-12-11 | Spike-proven, prospective-only VoiceNotes retrieval and replay-safe reconciliation. | R4 accepted and VoiceNotes synthetic contract spike passes | 6 | Evidence-gated estimate
R6 | Generated Text Reflection | 2026-12-14 | 2027-01-08 | Optional evaluated titles, summaries, tags, and Visual Briefs with protection, provenance, and budget enforcement. | R5 accepted and text-model evaluation passes | 6 | Evidence-gated estimate
R7 | Generated Artwork | 2027-01-11 | 2027-01-29 | Optional evaluated symbolic artwork with explicit preflight, versions, suppression, and real-photo cover precedence. | R6 accepted and artwork-model evaluation passes | 6 | Evidence-gated estimate
R8 | Operational Scale and Resilience | 2027-02-01 | 2027-02-19 | The integrated archive degrades safely under dependency, capacity, restart, and job failures. | R0 through R7 accepted | 4 | Evidence-gated estimate
R9 | Private Launch Acceptance and Stabilization | 2027-02-22 | 2027-03-12 | The complete private archive is owner-accepted for routine personal use and stabilized without new scope. | R8 accepted and explicit launch authority | 3 | Evidence-gated estimate
R10 | Conditional Object-store Transition |  |  | Live encrypted media moves only after approved local-capacity watermarks trigger a reversible transition. | Measured storage trigger; no calendar commitment | 3 | Dates intentionally blank

## Release Plan
Milestone Release Plan | Milestone Release Plan | Milestone Release Plan | Milestone Release Plan | Milestone Release Plan | Milestone Release Plan | Milestone Release Plan | Milestone Release Plan | Milestone Release Plan | Milestone Release Plan | Milestone Release Plan | Milestone Release Plan
Milestone Release Plan | Milestone Release Plan | Milestone Release Plan | Milestone Release Plan | Milestone Release Plan | Milestone Release Plan | Milestone Release Plan | Milestone Release Plan | Milestone Release Plan | Milestone Release Plan | Milestone Release Plan | Milestone Release Plan
Every milestone is independently reviewable, but task entry requires its own approved dossier. Start/Target are proposed estimates in Asia/Kolkata. R10 remains blank until the approved storage trigger exists. | Every milestone is independently reviewable, but task entry requires its own approved dossier. Start/Target are proposed estimates in Asia/Kolkata. R10 remains blank until the approved storage trigger exists. | Every milestone is independently reviewable, but task entry requires its own approved dossier. Start/Target are proposed estimates in Asia/Kolkata. R10 remains blank until the approved storage trigger exists. | Every milestone is independently reviewable, but task entry requires its own approved dossier. Start/Target are proposed estimates in Asia/Kolkata. R10 remains blank until the approved storage trigger exists. | Every milestone is independently reviewable, but task entry requires its own approved dossier. Start/Target are proposed estimates in Asia/Kolkata. R10 remains blank until the approved storage trigger exists. | Every milestone is independently reviewable, but task entry requires its own approved dossier. Start/Target are proposed estimates in Asia/Kolkata. R10 remains blank until the approved storage trigger exists. | Every milestone is independently reviewable, but task entry requires its own approved dossier. Start/Target are proposed estimates in Asia/Kolkata. R10 remains blank until the approved storage trigger exists. | Every milestone is independently reviewable, but task entry requires its own approved dossier. Start/Target are proposed estimates in Asia/Kolkata. R10 remains blank until the approved storage trigger exists. | Every milestone is independently reviewable, but task entry requires its own approved dossier. Start/Target are proposed estimates in Asia/Kolkata. R10 remains blank until the approved storage trigger exists. | Every milestone is independently reviewable, but task entry requires its own approved dossier. Start/Target are proposed estimates in Asia/Kolkata. R10 remains blank until the approved storage trigger exists. | Every milestone is independently reviewable, but task entry requires its own approved dossier. Start/Target are proposed estimates in Asia/Kolkata. R10 remains blank until the approved storage trigger exists. | Every milestone is independently reviewable, but task entry requires its own approved dossier. Start/Target are proposed estimates in Asia/Kolkata. R10 remains blank until the approved storage trigger exists.
Milestone | Release | Start | Target | Days | Meaningful outcome | Exit evidence | Entry dependency | Date basis | Tasks | Dossiers Ready | Execution allowed
P0 | Council Planning Baseline | 2026-08-14 | 2026-08-16 | 3 | A source-grounded, reviewable Product Council package and one canonical delivery manifest. | Council reviews, source hashes, requirement coverage, workbook, and GitHub roadmap agree. | None | Estimate; evidence gates control | 2 | 0 | 0
R0 | Shared-Host Private Foundation | 2026-08-17 | 2026-08-28 | 12 | A synthetic-only private shell can coexist with current services, recover, upgrade, and roll back. | Owner access/denial, sanitized capacity and non-regression evidence, encrypted synthetic restore, and rollback proof. | P0 accepted | Estimate; evidence gates control | 6 | 0 | 0
R1 | Manual Journal Archive | 2026-08-31 | 2026-09-18 | 19 | First memory-creating release: explicit-date text upload, Calendar, and Journal Day recall. | An owner-approved text fixture survives ingestion, restart, backup, restore, and export/checksum validation. | R0 accepted | Estimate; evidence gates control | 5 | 0 | 0
R2 | Telegram Photo Capture | 2026-09-21 | 2026-10-09 | 19 | Authorized durable photo capture with review-safe dating, gallery, cover, duplicates, and privacy-safe derivatives. | Authorization, invalid media/date, album, duplicate, cover, Original, privacy, backup, and restore fixtures pass. | R1 accepted | Estimate; evidence gates control | 6 | 0 | 0
R3 | Retrieval and Date Integrity | 2026-10-12 | 2026-10-30 | 19 | Cross-month browsing, deterministic search, Needs Date Review, and atomic source redating. | Known queries work without leakage and a redated item updates both days and restored indexes atomically. | R2 accepted | Estimate; evidence gates control | 5 | 0 | 0
R4 | Source History and Lifecycle Safety | 2026-11-02 | 2026-11-20 | 19 | Corrections, upstream conflicts, History, Trash, suppressions, and complete restorable export. | Three conflict outcomes and delete/restore/export/import invariants pass across every existing data shape. | R3 accepted | Estimate; evidence gates control | 6 | 0 | 0
R5 | Prospective VoiceNotes Sync | 2026-11-23 | 2026-12-11 | 19 | Spike-proven, prospective-only VoiceNotes retrieval and replay-safe reconciliation. | Synthetic contract, activation, eligibility, dating, replay, suppression, upstream revision, and restore gates pass. | R4 accepted and VoiceNotes synthetic contract spike passes | Estimate; evidence gates control | 6 | 0 | 0
R6 | Generated Text Reflection | 2026-12-14 | 2027-01-08 | 26 | Optional evaluated titles, summaries, tags, and Visual Briefs with protection, provenance, and budget enforcement. | Evaluation, typed privacy allowlist, field protection, source-race, failure, spend, and restore gates pass. | R5 accepted and text-model evaluation passes | Estimate; evidence gates control | 6 | 0 | 0
R7 | Generated Artwork | 2027-01-11 | 2027-01-29 | 19 | Optional evaluated symbolic artwork with explicit preflight, versions, suppression, and real-photo cover precedence. | Evaluation, safety, cost, lifecycle, labeling, privacy, cover, and restore gates pass. | R6 accepted and artwork-model evaluation passes | Estimate; evidence gates control | 6 | 0 | 0
R8 | Operational Scale and Resilience | 2027-02-01 | 2027-02-19 | 19 | The integrated archive degrades safely under dependency, capacity, restart, and job failures. | Watermark, restart, alert, fault, backup/restore, security, browser, and accessibility evidence passes. | R0 through R7 accepted | Estimate; evidence gates control | 4 | 0 | 0
R9 | Private Launch Acceptance and Stabilization | 2027-02-22 | 2027-03-12 | 19 | The complete private archive is owner-accepted for routine personal use and stabilized without new scope. | Owner UAT, Recovery Ceremony, observation window, severity gate, and go/no-go or rollback record pass. | R8 accepted and explicit launch authority | Estimate; evidence gates control | 3 | 0 | 0
R10 | Conditional Object-store Transition |  |  |  | Live encrypted media moves only after approved local-capacity watermarks trigger a reversible transition. | Trigger, inventory, dual-write, reconciliation, restore, observed reads, cutover, and rollback gates pass. | Measured storage trigger; no calendar commitment | Trigger-only; no commitment | 3 | 0 | 0

## Roadmap Tasks
Detailed Roadmap Tasks — 58 Work Packages | Detailed Roadmap Tasks — 58 Work Packages | Detailed Roadmap Tasks — 58 Work Packages | Detailed Roadmap Tasks — 58 Work Packages | Detailed Roadmap Tasks — 58 Work Packages | Detailed Roadmap Tasks — 58 Work Packages | Detailed Roadmap Tasks — 58 Work Packages | Detailed Roadmap Tasks — 58 Work Packages | Detailed Roadmap Tasks — 58 Work Packages | Detailed Roadmap Tasks — 58 Work Packages | Detailed Roadmap Tasks — 58 Work Packages | Detailed Roadmap Tasks — 58 Work Packages | Detailed Roadmap Tasks — 58 Work Packages | Detailed Roadmap Tasks — 58 Work Packages | Detailed Roadmap Tasks — 58 Work Packages | Detailed Roadmap Tasks — 58 Work Packages | Detailed Roadmap Tasks — 58 Work Packages | Detailed Roadmap Tasks — 58 Work Packages | Detailed Roadmap Tasks — 58 Work Packages | Detailed Roadmap Tasks — 58 Work Packages | Detailed Roadmap Tasks — 58 Work Packages | Detailed Roadmap Tasks — 58 Work Packages | Detailed Roadmap Tasks — 58 Work Packages | Detailed Roadmap Tasks — 58 Work Packages | Detailed Roadmap Tasks — 58 Work Packages | Detailed Roadmap Tasks — 58 Work Packages | Detailed Roadmap Tasks — 58 Work Packages | Detailed Roadmap Tasks — 58 Work Packages | Detailed Roadmap Tasks — 58 Work Packages
Detailed Roadmap Tasks — 58 Work Packages | Detailed Roadmap Tasks — 58 Work Packages | Detailed Roadmap Tasks — 58 Work Packages | Detailed Roadmap Tasks — 58 Work Packages | Detailed Roadmap Tasks — 58 Work Packages | Detailed Roadmap Tasks — 58 Work Packages | Detailed Roadmap Tasks — 58 Work Packages | Detailed Roadmap Tasks — 58 Work Packages | Detailed Roadmap Tasks — 58 Work Packages | Detailed Roadmap Tasks — 58 Work Packages | Detailed Roadmap Tasks — 58 Work Packages | Detailed Roadmap Tasks — 58 Work Packages | Detailed Roadmap Tasks — 58 Work Packages | Detailed Roadmap Tasks — 58 Work Packages | Detailed Roadmap Tasks — 58 Work Packages | Detailed Roadmap Tasks — 58 Work Packages | Detailed Roadmap Tasks — 58 Work Packages | Detailed Roadmap Tasks — 58 Work Packages | Detailed Roadmap Tasks — 58 Work Packages | Detailed Roadmap Tasks — 58 Work Packages | Detailed Roadmap Tasks — 58 Work Packages | Detailed Roadmap Tasks — 58 Work Packages | Detailed Roadmap Tasks — 58 Work Packages | Detailed Roadmap Tasks — 58 Work Packages | Detailed Roadmap Tasks — 58 Work Packages | Detailed Roadmap Tasks — 58 Work Packages | Detailed Roadmap Tasks — 58 Work Packages | Detailed Roadmap Tasks — 58 Work Packages | Detailed Roadmap Tasks — 58 Work Packages
Every stable task ID projects six P0-prefixed dossier artifacts into its existing issue and Roadmap item. Current control truth: 58 Incomplete; 45 Hold + 13 Historical non-authorizing; 0 Ready; 0 execution-allowed. Done on a planning item never implies implementation or deployment. | Every stable task ID projects six P0-prefixed dossier artifacts into its existing issue and Roadmap item. Current control truth: 58 Incomplete; 45 Hold + 13 Historical non-authorizing; 0 Ready; 0 execution-allowed. Done on a planning item never implies implementation or deployment. | Every stable task ID projects six P0-prefixed dossier artifacts into its existing issue and Roadmap item. Current control truth: 58 Incomplete; 45 Hold + 13 Historical non-authorizing; 0 Ready; 0 execution-allowed. Done on a planning item never implies implementation or deployment. | Every stable task ID projects six P0-prefixed dossier artifacts into its existing issue and Roadmap item. Current control truth: 58 Incomplete; 45 Hold + 13 Historical non-authorizing; 0 Ready; 0 execution-allowed. Done on a planning item never implies implementation or deployment. | Every stable task ID projects six P0-prefixed dossier artifacts into its existing issue and Roadmap item. Current control truth: 58 Incomplete; 45 Hold + 13 Historical non-authorizing; 0 Ready; 0 execution-allowed. Done on a planning item never implies implementation or deployment. | Every stable task ID projects six P0-prefixed dossier artifacts into its existing issue and Roadmap item. Current control truth: 58 Incomplete; 45 Hold + 13 Historical non-authorizing; 0 Ready; 0 execution-allowed. Done on a planning item never implies implementation or deployment. | Every stable task ID projects six P0-prefixed dossier artifacts into its existing issue and Roadmap item. Current control truth: 58 Incomplete; 45 Hold + 13 Historical non-authorizing; 0 Ready; 0 execution-allowed. Done on a planning item never implies implementation or deployment. | Every stable task ID projects six P0-prefixed dossier artifacts into its existing issue and Roadmap item. Current control truth: 58 Incomplete; 45 Hold + 13 Historical non-authorizing; 0 Ready; 0 execution-allowed. Done on a planning item never implies implementation or deployment. | Every stable task ID projects six P0-prefixed dossier artifacts into its existing issue and Roadmap item. Current control truth: 58 Incomplete; 45 Hold + 13 Historical non-authorizing; 0 Ready; 0 execution-allowed. Done on a planning item never implies implementation or deployment. | Every stable task ID projects six P0-prefixed dossier artifacts into its existing issue and Roadmap item. Current control truth: 58 Incomplete; 45 Hold + 13 Historical non-authorizing; 0 Ready; 0 execution-allowed. Done on a planning item never implies implementation or deployment. | Every stable task ID projects six P0-prefixed dossier artifacts into its existing issue and Roadmap item. Current control truth: 58 Incomplete; 45 Hold + 13 Historical non-authorizing; 0 Ready; 0 execution-allowed. Done on a planning item never implies implementation or deployment. | Every stable task ID projects six P0-prefixed dossier artifacts into its existing issue and Roadmap item. Current control truth: 58 Incomplete; 45 Hold + 13 Historical non-authorizing; 0 Ready; 0 execution-allowed. Done on a planning item never implies implementation or deployment. | Every stable task ID projects six P0-prefixed dossier artifacts into its existing issue and Roadmap item. Current control truth: 58 Incomplete; 45 Hold + 13 Historical non-authorizing; 0 Ready; 0 execution-allowed. Done on a planning item never implies implementation or deployment. | Every stable task ID projects six P0-prefixed dossier artifacts into its existing issue and Roadmap item. Current control truth: 58 Incomplete; 45 Hold + 13 Historical non-authorizing; 0 Ready; 0 execution-allowed. Done on a planning item never implies implementation or deployment. | Every stable task ID projects six P0-prefixed dossier artifacts into its existing issue and Roadmap item. Current control truth: 58 Incomplete; 45 Hold + 13 Historical non-authorizing; 0 Ready; 0 execution-allowed. Done on a planning item never implies implementation or deployment. | Every stable task ID projects six P0-prefixed dossier artifacts into its existing issue and Roadmap item. Current control truth: 58 Incomplete; 45 Hold + 13 Historical non-authorizing; 0 Ready; 0 execution-allowed. Done on a planning item never implies implementation or deployment. | Every stable task ID projects six P0-prefixed dossier artifacts into its existing issue and Roadmap item. Current control truth: 58 Incomplete; 45 Hold + 13 Historical non-authorizing; 0 Ready; 0 execution-allowed. Done on a planning item never implies implementation or deployment. | Every stable task ID projects six P0-prefixed dossier artifacts into its existing issue and Roadmap item. Current control truth: 58 Incomplete; 45 Hold + 13 Historical non-authorizing; 0 Ready; 0 execution-allowed. Done on a planning item never implies implementation or deployment. | Every stable task ID projects six P0-prefixed dossier artifacts into its existing issue and Roadmap item. Current control truth: 58 Incomplete; 45 Hold + 13 Historical non-authorizing; 0 Ready; 0 execution-allowed. Done on a planning item never implies implementation or deployment. | Every stable task ID projects six P0-prefixed dossier artifacts into its existing issue and Roadmap item. Current control truth: 58 Incomplete; 45 Hold + 13 Historical non-authorizing; 0 Ready; 0 execution-allowed. Done on a planning item never implies implementation or deployment. | Every stable task ID projects six P0-prefixed dossier artifacts into its existing issue and Roadmap item. Current control truth: 58 Incomplete; 45 Hold + 13 Historical non-authorizing; 0 Ready; 0 execution-allowed. Done on a planning item never implies implementation or deployment. | Every stable task ID projects six P0-prefixed dossier artifacts into its existing issue and Roadmap item. Current control truth: 58 Incomplete; 45 Hold + 13 Historical non-authorizing; 0 Ready; 0 execution-allowed. Done on a planning item never implies implementation or deployment. | Every stable task ID projects six P0-prefixed dossier artifacts into its existing issue and Roadmap item. Current control truth: 58 Incomplete; 45 Hold + 13 Historical non-authorizing; 0 Ready; 0 execution-allowed. Done on a planning item never implies implementation or deployment. | Every stable task ID projects six P0-prefixed dossier artifacts into its existing issue and Roadmap item. Current control truth: 58 Incomplete; 45 Hold + 13 Historical non-authorizing; 0 Ready; 0 execution-allowed. Done on a planning item never implies implementation or deployment. | Every stable task ID projects six P0-prefixed dossier artifacts into its existing issue and Roadmap item. Current control truth: 58 Incomplete; 45 Hold + 13 Historical non-authorizing; 0 Ready; 0 execution-allowed. Done on a planning item never implies implementation or deployment. | Every stable task ID projects six P0-prefixed dossier artifacts into its existing issue and Roadmap item. Current control truth: 58 Incomplete; 45 Hold + 13 Historical non-authorizing; 0 Ready; 0 execution-allowed. Done on a planning item never implies implementation or deployment. | Every stable task ID projects six P0-prefixed dossier artifacts into its existing issue and Roadmap item. Current control truth: 58 Incomplete; 45 Hold + 13 Historical non-authorizing; 0 Ready; 0 execution-allowed. Done on a planning item never implies implementation or deployment. | Every stable task ID projects six P0-prefixed dossier artifacts into its existing issue and Roadmap item. Current control truth: 58 Incomplete; 45 Hold + 13 Historical non-authorizing; 0 Ready; 0 execution-allowed. Done on a planning item never implies implementation or deployment. | Every stable task ID projects six P0-prefixed dossier artifacts into its existing issue and Roadmap item. Current control truth: 58 Incomplete; 45 Hold + 13 Historical non-authorizing; 0 Ready; 0 execution-allowed. Done on a planning item never implies implementation or deployment.
ID | Title | Status | Artifact readiness | Execution allowed | Execution scope | Milestone | Type | Owner role | Priority | Start | Target | Days | Requirement IDs | Dependencies | Parent PRD / PID | Task PRD | Task technical plan | Task design spec | Task QA plan | Task delivery checklist | Task council readiness | Shared design input | Shared architecture input | Description | Acceptance evidence | Rollback / restore impact | Done meaning | GitHub issue
AUD-001 | v5 Feature Audit | Done | Incomplete | No | planning-only-historical | P0 | Audit | Product Manager + UI/UX Designer | High | 2026-08-14 | 2026-08-14 | 1 |  |  | https://github.com/arunpr614/Life-Reflection/blob/main/docs/product/PRODUCT-REQUIREMENTS.md | https://github.com/arunpr614/Life-Reflection/blob/main/docs/work-items/AUD-001/P0-AUD-001-PRD.md | https://github.com/arunpr614/Life-Reflection/blob/main/docs/work-items/AUD-001/P0-AUD-001-TECHNICAL-PLAN.md | https://github.com/arunpr614/Life-Reflection/blob/main/docs/work-items/AUD-001/P0-AUD-001-DESIGN-SPEC.md | https://github.com/arunpr614/Life-Reflection/blob/main/docs/work-items/AUD-001/P0-AUD-001-QA-PLAN.md | https://github.com/arunpr614/Life-Reflection/blob/main/docs/work-items/AUD-001/P0-AUD-001-DELIVERY-CHECKLIST.md | https://github.com/arunpr614/Life-Reflection/blob/main/docs/work-items/AUD-001/P0-AUD-001-COUNCIL-READINESS.md | https://github.com/arunpr614/Life-Reflection/blob/main/docs/council/UX-DESIGN-REVIEW.md | https://github.com/arunpr614/Life-Reflection/blob/main/docs/architecture/PHASE1-IMPLEMENTATION-PLAN.md | Classify every v5 interaction as strong, partial, missing, or outside implementation evidence. | Published v5 feature audit with a source hash and requirement-by-requirement evidence classification. | Planning evidence only; no production data mutation. Any later implementation still needs its own migration, restore, and rollback proof. | This planning artifact is complete; it does not claim feature implementation, deployment, production readiness, or release acceptance. | https://github.com/arunpr614/Life-Reflection/issues/2
PC-001 | Integrated Council Planning Package | Done | Incomplete | No | planning-only-historical | P0 | Planning | Project Manager | High | 2026-08-14 | 2026-08-16 | 3 |  | AUD-001 | https://github.com/arunpr614/Life-Reflection/blob/main/docs/product/PRODUCT-REQUIREMENTS.md | https://github.com/arunpr614/Life-Reflection/blob/main/docs/work-items/PC-001/P0-PC-001-PRD.md | https://github.com/arunpr614/Life-Reflection/blob/main/docs/work-items/PC-001/P0-PC-001-TECHNICAL-PLAN.md | https://github.com/arunpr614/Life-Reflection/blob/main/docs/work-items/PC-001/P0-PC-001-DESIGN-SPEC.md | https://github.com/arunpr614/Life-Reflection/blob/main/docs/work-items/PC-001/P0-PC-001-QA-PLAN.md | https://github.com/arunpr614/Life-Reflection/blob/main/docs/work-items/PC-001/P0-PC-001-DELIVERY-CHECKLIST.md | https://github.com/arunpr614/Life-Reflection/blob/main/docs/work-items/PC-001/P0-PC-001-COUNCIL-READINESS.md | https://github.com/arunpr614/Life-Reflection/blob/main/docs/council/UX-DESIGN-REVIEW.md | https://github.com/arunpr614/Life-Reflection/blob/main/docs/architecture/PHASE1-IMPLEMENTATION-PLAN.md | Reconcile Product, Design, Architecture, and Project Management decisions into one delivery baseline. | Historical four-seat planning evidence and the five-seat P0 execution-control review, decision record, 58-task manifest, validated workbook, and live roadmap reconcile without inflating planning Done. | Planning evidence only; no production data mutation. Any later implementation still needs its own migration, restore, and rollback proof. | This planning artifact is complete; it does not claim feature implementation, deployment, production readiness, or release acceptance. | https://github.com/arunpr614/Life-Reflection/issues/3
SPK-R0-001 | Shared-host Coexistence & Rollback Spike | In progress | Incomplete | No | local-synthetic-artifact-authoring-only | R0 | Spike | Technical Architect | High | 2026-08-17 | 2026-08-19 | 3 | LID-SCP-001, LID-OPS-001, LID-OPS-002, LID-OPS-003, LID-OPS-004, LID-OPS-008, LID-OPS-011, LID-OPS-012, LID-OPS-014, LID-OPS-016, LID-OPS-018 | PC-001 | https://github.com/arunpr614/Life-Reflection/blob/main/docs/product/releases/PRD-R0-SHARED-HOST-PRIVATE-FOUNDATION.md | https://github.com/arunpr614/Life-Reflection/blob/main/docs/work-items/SPK-R0-001/P0-SPK-R0-001-PRD.md | https://github.com/arunpr614/Life-Reflection/blob/main/docs/work-items/SPK-R0-001/P0-SPK-R0-001-TECHNICAL-PLAN.md | https://github.com/arunpr614/Life-Reflection/blob/main/docs/work-items/SPK-R0-001/P0-SPK-R0-001-DESIGN-SPEC.md | https://github.com/arunpr614/Life-Reflection/blob/main/docs/work-items/SPK-R0-001/P0-SPK-R0-001-QA-PLAN.md | https://github.com/arunpr614/Life-Reflection/blob/main/docs/work-items/SPK-R0-001/P0-SPK-R0-001-DELIVERY-CHECKLIST.md | https://github.com/arunpr614/Life-Reflection/blob/main/docs/work-items/SPK-R0-001/P0-SPK-R0-001-COUNCIL-READINESS.md | https://github.com/arunpr614/Life-Reflection/blob/main/docs/council/UX-DESIGN-REVIEW.md | https://github.com/arunpr614/Life-Reflection/blob/main/docs/architecture/PHASE1-IMPLEMENTATION-PLAN.md | Prove namespaced shared-host fit with synthetic data, explicit capacity assumptions, non-regression, restore, and rollback. | Research report plus sanitized live host capacity/topology, collision, restart, backup/restore, rollback, and co-resident non-regression evidence. | No personal-data mutation is authorized by this task; it must define or prove reversible deployment and recovery before dependent implementation. | Move to Done only when the named task evidence exists; prototype or document intent cannot prove implementation or release completion. | https://github.com/arunpr614/Life-Reflection/issues/4
PRD-R0-001 | Private Foundation PRD | Done | Incomplete | No | planning-only-historical | R0 | Product definition | Product Manager | High | 2026-08-17 | 2026-08-20 | 4 | LID-SCP-001, LID-OPS-001, LID-OPS-002, LID-OPS-003, LID-OPS-004, LID-OPS-008, LID-OPS-011, LID-OPS-012, LID-OPS-014, LID-OPS-016, LID-OPS-018 | PC-001 | https://github.com/arunpr614/Life-Reflection/blob/main/docs/product/releases/PRD-R0-SHARED-HOST-PRIVATE-FOUNDATION.md | https://github.com/arunpr614/Life-Reflection/blob/main/docs/work-items/PRD-R0-001/P0-PRD-R0-001-PRD.md | https://github.com/arunpr614/Life-Reflection/blob/main/docs/work-items/PRD-R0-001/P0-PRD-R0-001-TECHNICAL-PLAN.md | https://github.com/arunpr614/Life-Reflection/blob/main/docs/work-items/PRD-R0-001/P0-PRD-R0-001-DESIGN-SPEC.md | https://github.com/arunpr614/Life-Reflection/blob/main/docs/work-items/PRD-R0-001/P0-PRD-R0-001-QA-PLAN.md | https://github.com/arunpr614/Life-Reflection/blob/main/docs/work-items/PRD-R0-001/P0-PRD-R0-001-DELIVERY-CHECKLIST.md | https://github.com/arunpr614/Life-Reflection/blob/main/docs/work-items/PRD-R0-001/P0-PRD-R0-001-COUNCIL-READINESS.md | https://github.com/arunpr614/Life-Reflection/blob/main/docs/council/UX-DESIGN-REVIEW.md | https://github.com/arunpr614/Life-Reflection/blob/main/docs/architecture/PHASE1-IMPLEMENTATION-PLAN.md | Define the synthetic-only private foundation outcome and prohibit authentic memory ingestion before R0 acceptance. | Release document docs/product/releases/PRD-R0-SHARED-HOST-PRIVATE-FOUNDATION.md exists, passes link/requirement validation, and separates council-delegated evidence gates from specifically named non-delegable human acts. | Planning evidence only; no production data mutation. Any later implementation still needs its own migration, restore, and rollback proof. | This planning artifact is complete; it does not claim feature implementation, deployment, production readiness, or release acceptance. | https://github.com/arunpr614/Life-Reflection/issues/5
UX-R0-001 | First-use/Access/Health States | Next | Incomplete | No | local-synthetic-artifact-authoring-only | R0 | Design | UI/UX Designer | High | 2026-08-18 | 2026-08-21 | 4 | LID-SCP-001, LID-OPS-001, LID-OPS-012, LID-OPS-014, LID-OPS-018 | PRD-R0-001, SPK-R0-001 | https://github.com/arunpr614/Life-Reflection/blob/main/docs/product/releases/PRD-R0-SHARED-HOST-PRIVATE-FOUNDATION.md | https://github.com/arunpr614/Life-Reflection/blob/main/docs/work-items/UX-R0-001/P0-UX-R0-001-PRD.md | https://github.com/arunpr614/Life-Reflection/blob/main/docs/work-items/UX-R0-001/P0-UX-R0-001-TECHNICAL-PLAN.md | https://github.com/arunpr614/Life-Reflection/blob/main/docs/work-items/UX-R0-001/P0-UX-R0-001-DESIGN-SPEC.md | https://github.com/arunpr614/Life-Reflection/blob/main/docs/work-items/UX-R0-001/P0-UX-R0-001-QA-PLAN.md | https://github.com/arunpr614/Life-Reflection/blob/main/docs/work-items/UX-R0-001/P0-UX-R0-001-DELIVERY-CHECKLIST.md | https://github.com/arunpr614/Life-Reflection/blob/main/docs/work-items/UX-R0-001/P0-UX-R0-001-COUNCIL-READINESS.md | https://github.com/arunpr614/Life-Reflection/blob/main/docs/council/UX-DESIGN-REVIEW.md | https://github.com/arunpr614/Life-Reflection/blob/main/docs/architecture/PHASE1-IMPLEMENTATION-PLAN.md | Design first use, access denial/expiry, System Health, synthetic recovery, failure, and rollback states. | Approved task-specific design for UX-R0-001 — First-use/Access/Health States links complete normal/empty/loading/error/interruption/destructive states, responsive behavior, accessibility annotations, prototype dispositions, and Designer sign-off. | Planning evidence only; no production data mutation. Any later implementation still needs its own migration, restore, and rollback proof. | Move to Done only when the named task evidence exists; prototype or document intent cannot prove implementation or release completion. | https://github.com/arunpr614/Life-Reflection/issues/6
ARCH-R0-001 | Private Shell Architecture & Threat Baseline | Next | Incomplete | No | local-synthetic-artifact-authoring-only | R0 | Architecture | Technical Architect | High | 2026-08-17 | 2026-08-21 | 5 | LID-SCP-001, LID-OPS-001, LID-OPS-002, LID-OPS-003, LID-OPS-004, LID-OPS-008, LID-OPS-011, LID-OPS-012, LID-OPS-014, LID-OPS-016, LID-OPS-018 | PRD-R0-001, SPK-R0-001 | https://github.com/arunpr614/Life-Reflection/blob/main/docs/product/releases/PRD-R0-SHARED-HOST-PRIVATE-FOUNDATION.md | https://github.com/arunpr614/Life-Reflection/blob/main/docs/work-items/ARCH-R0-001/P0-ARCH-R0-001-PRD.md | https://github.com/arunpr614/Life-Reflection/blob/main/docs/work-items/ARCH-R0-001/P0-ARCH-R0-001-TECHNICAL-PLAN.md | https://github.com/arunpr614/Life-Reflection/blob/main/docs/work-items/ARCH-R0-001/P0-ARCH-R0-001-DESIGN-SPEC.md | https://github.com/arunpr614/Life-Reflection/blob/main/docs/work-items/ARCH-R0-001/P0-ARCH-R0-001-QA-PLAN.md | https://github.com/arunpr614/Life-Reflection/blob/main/docs/work-items/ARCH-R0-001/P0-ARCH-R0-001-DELIVERY-CHECKLIST.md | https://github.com/arunpr614/Life-Reflection/blob/main/docs/work-items/ARCH-R0-001/P0-ARCH-R0-001-COUNCIL-READINESS.md | https://github.com/arunpr614/Life-Reflection/blob/main/docs/council/UX-DESIGN-REVIEW.md | https://github.com/arunpr614/Life-Reflection/blob/main/docs/architecture/PHASE1-IMPLEMENTATION-PLAN.md | Freeze namespaced processes, loopback ingress, callback isolation, encryption, secrets, logging, backup, and recovery architecture. | Approved task-specific technical plan for ARCH-R0-001 — Private Shell Architecture & Threat Baseline links owned modules, ADRs, threats/data flows, interfaces/data shapes, capacity, migration, restore, rollback, and Architect sign-off. | No personal-data mutation is authorized by this task; it must define or prove reversible deployment and recovery before dependent implementation. | Move to Done only when the named task evidence exists; prototype or document intent cannot prove implementation or release completion. | https://github.com/arunpr614/Life-Reflection/issues/7
ENG-R0-001 | Deploy Synthetic Private Shell | Next | Incomplete | No | local-synthetic-artifact-authoring-only | R0 | Implementation | Engineering | High | 2026-08-21 | 2026-08-26 | 6 | LID-SCP-001, LID-OPS-001, LID-OPS-002, LID-OPS-003, LID-OPS-004, LID-OPS-008, LID-OPS-011, LID-OPS-012, LID-OPS-014, LID-OPS-016, LID-OPS-018 | UX-R0-001, ARCH-R0-001 | https://github.com/arunpr614/Life-Reflection/blob/main/docs/product/releases/PRD-R0-SHARED-HOST-PRIVATE-FOUNDATION.md | https://github.com/arunpr614/Life-Reflection/blob/main/docs/work-items/ENG-R0-001/P0-ENG-R0-001-PRD.md | https://github.com/arunpr614/Life-Reflection/blob/main/docs/work-items/ENG-R0-001/P0-ENG-R0-001-TECHNICAL-PLAN.md | https://github.com/arunpr614/Life-Reflection/blob/main/docs/work-items/ENG-R0-001/P0-ENG-R0-001-DESIGN-SPEC.md | https://github.com/arunpr614/Life-Reflection/blob/main/docs/work-items/ENG-R0-001/P0-ENG-R0-001-QA-PLAN.md | https://github.com/arunpr614/Life-Reflection/blob/main/docs/work-items/ENG-R0-001/P0-ENG-R0-001-DELIVERY-CHECKLIST.md | https://github.com/arunpr614/Life-Reflection/blob/main/docs/work-items/ENG-R0-001/P0-ENG-R0-001-COUNCIL-READINESS.md | https://github.com/arunpr614/Life-Reflection/blob/main/docs/council/UX-DESIGN-REVIEW.md | https://github.com/arunpr614/Life-Reflection/blob/main/docs/architecture/PHASE1-IMPLEMENTATION-PLAN.md | Build and deploy an authenticated synthetic shell with health evidence and no route or data path for real memories. | Merged implementation for ENG-R0-001 — Deploy Synthetic Private Shell proves “Build and deploy an authenticated synthetic shell with health evidence and no route or data path for real memories.” with task-specific tests, immutable build/SBOM, migrations, sanitized deployment evidence when authorized, separate-path restore, rollback, and no-regression results. | Adds synthetic encrypted database/configuration and job state only; migration must be reversible and backup/restore coverage must pass before release acceptance. | Move to Done only when the named task evidence exists; prototype or document intent cannot prove implementation or release completion. | https://github.com/arunpr614/Life-Reflection/issues/8
REL-R0-001 | Restore/Rollback/Non-regression Acceptance | Next | Incomplete | No | future-release-gated | R0 | Release acceptance | Project Manager + Independent QA | High | 2026-08-27 | 2026-08-28 | 2 | LID-SCP-001, LID-OPS-001, LID-OPS-002, LID-OPS-003, LID-OPS-004, LID-OPS-008, LID-OPS-011, LID-OPS-012, LID-OPS-014, LID-OPS-016, LID-OPS-018 | ENG-R0-001 | https://github.com/arunpr614/Life-Reflection/blob/main/docs/product/releases/PRD-R0-SHARED-HOST-PRIVATE-FOUNDATION.md | https://github.com/arunpr614/Life-Reflection/blob/main/docs/work-items/REL-R0-001/P0-REL-R0-001-PRD.md | https://github.com/arunpr614/Life-Reflection/blob/main/docs/work-items/REL-R0-001/P0-REL-R0-001-TECHNICAL-PLAN.md | https://github.com/arunpr614/Life-Reflection/blob/main/docs/work-items/REL-R0-001/P0-REL-R0-001-DESIGN-SPEC.md | https://github.com/arunpr614/Life-Reflection/blob/main/docs/work-items/REL-R0-001/P0-REL-R0-001-QA-PLAN.md | https://github.com/arunpr614/Life-Reflection/blob/main/docs/work-items/REL-R0-001/P0-REL-R0-001-DELIVERY-CHECKLIST.md | https://github.com/arunpr614/Life-Reflection/blob/main/docs/work-items/REL-R0-001/P0-REL-R0-001-COUNCIL-READINESS.md | https://github.com/arunpr614/Life-Reflection/blob/main/docs/council/UX-DESIGN-REVIEW.md | https://github.com/arunpr614/Life-Reflection/blob/main/docs/architecture/PHASE1-IMPLEMENTATION-PLAN.md | Execute access, coexistence, encrypted synthetic restore, restart, rollback, and co-resident non-regression gates. | Release acceptance for REL-R0-001 — Restore/Rollback/Non-regression Acceptance links independent QA, five-seat review, every task-specific dossier, backup/separate-path restore for each new shape, rollback, defect gate, and proceed/hold/rollback record; a human attestation is included only for a named non-delegable act. | Validates rollback and restore for every persistent shape introduced by the milestone; acceptance never substitutes a successful backup upload for restore evidence. | Move to Done only when the named task evidence exists; prototype or document intent cannot prove implementation or release completion. | https://github.com/arunpr614/Life-Reflection/issues/9
PRD-R1-001 | Manual Archive PRD | Done | Incomplete | No | planning-only-historical | R1 | Product definition | Product Manager | High | 2026-08-31 | 2026-09-02 | 3 | LID-SCP-002, LID-SCP-003, LID-UP-001, LID-UP-002, LID-UP-003, LID-REF-001, LID-REF-004, LID-REF-005, LID-REF-006, LID-OPS-011, LID-OPS-018 | PC-001 | https://github.com/arunpr614/Life-Reflection/blob/main/docs/product/releases/PRD-R1-MANUAL-JOURNAL-ARCHIVE.md | https://github.com/arunpr614/Life-Reflection/blob/main/docs/work-items/PRD-R1-001/P0-PRD-R1-001-PRD.md | https://github.com/arunpr614/Life-Reflection/blob/main/docs/work-items/PRD-R1-001/P0-PRD-R1-001-TECHNICAL-PLAN.md | https://github.com/arunpr614/Life-Reflection/blob/main/docs/work-items/PRD-R1-001/P0-PRD-R1-001-DESIGN-SPEC.md | https://github.com/arunpr614/Life-Reflection/blob/main/docs/work-items/PRD-R1-001/P0-PRD-R1-001-QA-PLAN.md | https://github.com/arunpr614/Life-Reflection/blob/main/docs/work-items/PRD-R1-001/P0-PRD-R1-001-DELIVERY-CHECKLIST.md | https://github.com/arunpr614/Life-Reflection/blob/main/docs/work-items/PRD-R1-001/P0-PRD-R1-001-COUNCIL-READINESS.md | https://github.com/arunpr614/Life-Reflection/blob/main/docs/council/UX-DESIGN-REVIEW.md | https://github.com/arunpr614/Life-Reflection/blob/main/docs/architecture/PHASE1-IMPLEMENTATION-PLAN.md | Define the first memory-creating release with explicit-date text upload and authentic Calendar/Journal Day recall. | Release document docs/product/releases/PRD-R1-MANUAL-JOURNAL-ARCHIVE.md exists, passes link/requirement validation, and separates council-delegated evidence gates from specifically named non-delegable human acts. | Planning evidence only; no production data mutation. Any later implementation still needs its own migration, restore, and rollback proof. | This planning artifact is complete; it does not claim feature implementation, deployment, production readiness, or release acceptance. | https://github.com/arunpr614/Life-Reflection/issues/10
UX-R1-001 | Calendar/Day/Upload Designs | Backlog | Incomplete | No | future-release-gated | R1 | Design | UI/UX Designer | High | 2026-08-31 | 2026-09-04 | 5 | LID-SCP-002, LID-SCP-003, LID-UP-001, LID-UP-003, LID-REF-001, LID-REF-004, LID-REF-005, LID-REF-006 | PRD-R1-001 | https://github.com/arunpr614/Life-Reflection/blob/main/docs/product/releases/PRD-R1-MANUAL-JOURNAL-ARCHIVE.md | https://github.com/arunpr614/Life-Reflection/blob/main/docs/work-items/UX-R1-001/P0-UX-R1-001-PRD.md | https://github.com/arunpr614/Life-Reflection/blob/main/docs/work-items/UX-R1-001/P0-UX-R1-001-TECHNICAL-PLAN.md | https://github.com/arunpr614/Life-Reflection/blob/main/docs/work-items/UX-R1-001/P0-UX-R1-001-DESIGN-SPEC.md | https://github.com/arunpr614/Life-Reflection/blob/main/docs/work-items/UX-R1-001/P0-UX-R1-001-QA-PLAN.md | https://github.com/arunpr614/Life-Reflection/blob/main/docs/work-items/UX-R1-001/P0-UX-R1-001-DELIVERY-CHECKLIST.md | https://github.com/arunpr614/Life-Reflection/blob/main/docs/work-items/UX-R1-001/P0-UX-R1-001-COUNCIL-READINESS.md | https://github.com/arunpr614/Life-Reflection/blob/main/docs/council/UX-DESIGN-REVIEW.md | https://github.com/arunpr614/Life-Reflection/blob/main/docs/architecture/PHASE1-IMPLEMENTATION-PLAN.md | Finalize Calendar, Journal Day, upload, empty/loading/error, responsive, theme, and accessibility states. | Approved task-specific design for UX-R1-001 — Calendar/Day/Upload Designs links complete normal/empty/loading/error/interruption/destructive states, responsive behavior, accessibility annotations, prototype dispositions, and Designer sign-off. | Planning evidence only; no production data mutation. Any later implementation still needs its own migration, restore, and rollback proof. | Move to Done only when the named task evidence exists; prototype or document intent cannot prove implementation or release completion. | https://github.com/arunpr614/Life-Reflection/issues/11
ARCH-R1-001 | Journal/Source/Encryption Schema | Backlog | Incomplete | No | future-release-gated | R1 | Architecture | Technical Architect | High | 2026-08-31 | 2026-09-04 | 5 | LID-SCP-002, LID-SCP-003, LID-UP-001, LID-UP-002, LID-UP-003, LID-OPS-011, LID-OPS-018 | PRD-R1-001, REL-R0-001 | https://github.com/arunpr614/Life-Reflection/blob/main/docs/product/releases/PRD-R1-MANUAL-JOURNAL-ARCHIVE.md | https://github.com/arunpr614/Life-Reflection/blob/main/docs/work-items/ARCH-R1-001/P0-ARCH-R1-001-PRD.md | https://github.com/arunpr614/Life-Reflection/blob/main/docs/work-items/ARCH-R1-001/P0-ARCH-R1-001-TECHNICAL-PLAN.md | https://github.com/arunpr614/Life-Reflection/blob/main/docs/work-items/ARCH-R1-001/P0-ARCH-R1-001-DESIGN-SPEC.md | https://github.com/arunpr614/Life-Reflection/blob/main/docs/work-items/ARCH-R1-001/P0-ARCH-R1-001-QA-PLAN.md | https://github.com/arunpr614/Life-Reflection/blob/main/docs/work-items/ARCH-R1-001/P0-ARCH-R1-001-DELIVERY-CHECKLIST.md | https://github.com/arunpr614/Life-Reflection/blob/main/docs/work-items/ARCH-R1-001/P0-ARCH-R1-001-COUNCIL-READINESS.md | https://github.com/arunpr614/Life-Reflection/blob/main/docs/council/UX-DESIGN-REVIEW.md | https://github.com/arunpr614/Life-Reflection/blob/main/docs/architecture/PHASE1-IMPLEMENTATION-PLAN.md | Define Journal Day, immutable source file, checksum, encryption, index, backup, restore, and migration contracts. | Approved task-specific technical plan for ARCH-R1-001 — Journal/Source/Encryption Schema links owned modules, ADRs, threats/data flows, interfaces/data shapes, capacity, migration, restore, rollback, and Architect sign-off. | No personal-data mutation is authorized by this task; it must define or prove reversible deployment and recovery before dependent implementation. | Move to Done only when the named task evidence exists; prototype or document intent cannot prove implementation or release completion. | https://github.com/arunpr614/Life-Reflection/issues/12
ENG-R1-001 | Manual Upload & Reflection Core | Backlog | Incomplete | No | future-release-gated | R1 | Implementation | Engineering | High | 2026-09-03 | 2026-09-15 | 13 | LID-SCP-002, LID-SCP-003, LID-UP-001, LID-UP-002, LID-UP-003, LID-REF-001, LID-REF-004, LID-REF-005, LID-REF-006, LID-OPS-011, LID-OPS-018 | UX-R1-001, ARCH-R1-001, REL-R0-001 | https://github.com/arunpr614/Life-Reflection/blob/main/docs/product/releases/PRD-R1-MANUAL-JOURNAL-ARCHIVE.md | https://github.com/arunpr614/Life-Reflection/blob/main/docs/work-items/ENG-R1-001/P0-ENG-R1-001-PRD.md | https://github.com/arunpr614/Life-Reflection/blob/main/docs/work-items/ENG-R1-001/P0-ENG-R1-001-TECHNICAL-PLAN.md | https://github.com/arunpr614/Life-Reflection/blob/main/docs/work-items/ENG-R1-001/P0-ENG-R1-001-DESIGN-SPEC.md | https://github.com/arunpr614/Life-Reflection/blob/main/docs/work-items/ENG-R1-001/P0-ENG-R1-001-QA-PLAN.md | https://github.com/arunpr614/Life-Reflection/blob/main/docs/work-items/ENG-R1-001/P0-ENG-R1-001-DELIVERY-CHECKLIST.md | https://github.com/arunpr614/Life-Reflection/blob/main/docs/work-items/ENG-R1-001/P0-ENG-R1-001-COUNCIL-READINESS.md | https://github.com/arunpr614/Life-Reflection/blob/main/docs/council/UX-DESIGN-REVIEW.md | https://github.com/arunpr614/Life-Reflection/blob/main/docs/architecture/PHASE1-IMPLEMENTATION-PLAN.md | Implement durable explicit-date text upload, duplicate override, Calendar, and authentic Journal Day display. | Merged implementation for ENG-R1-001 — Manual Upload & Reflection Core proves “Implement durable explicit-date text upload, duplicate override, Calendar, and authentic Journal Day display.” with task-specific tests, immutable build/SBOM, migrations, sanitized deployment evidence when authorized, separate-path restore, rollback, and no-regression results. | Adds journal-day, source-file, checksum, and correction-ready records; migration must be reversible and backup/restore coverage must pass before release acceptance. | Move to Done only when the named task evidence exists; prototype or document intent cannot prove implementation or release completion. | https://github.com/arunpr614/Life-Reflection/issues/13
REL-R1-001 | First-memory Restore/Rollback Acceptance | Backlog | Incomplete | No | future-release-gated | R1 | Release acceptance | Project Manager + Independent QA | High | 2026-09-16 | 2026-09-18 | 3 | LID-SCP-002, LID-SCP-003, LID-UP-001, LID-UP-002, LID-UP-003, LID-REF-001, LID-REF-004, LID-REF-005, LID-REF-006, LID-OPS-011, LID-OPS-018 | ENG-R1-001 | https://github.com/arunpr614/Life-Reflection/blob/main/docs/product/releases/PRD-R1-MANUAL-JOURNAL-ARCHIVE.md | https://github.com/arunpr614/Life-Reflection/blob/main/docs/work-items/REL-R1-001/P0-REL-R1-001-PRD.md | https://github.com/arunpr614/Life-Reflection/blob/main/docs/work-items/REL-R1-001/P0-REL-R1-001-TECHNICAL-PLAN.md | https://github.com/arunpr614/Life-Reflection/blob/main/docs/work-items/REL-R1-001/P0-REL-R1-001-DESIGN-SPEC.md | https://github.com/arunpr614/Life-Reflection/blob/main/docs/work-items/REL-R1-001/P0-REL-R1-001-QA-PLAN.md | https://github.com/arunpr614/Life-Reflection/blob/main/docs/work-items/REL-R1-001/P0-REL-R1-001-DELIVERY-CHECKLIST.md | https://github.com/arunpr614/Life-Reflection/blob/main/docs/work-items/REL-R1-001/P0-REL-R1-001-COUNCIL-READINESS.md | https://github.com/arunpr614/Life-Reflection/blob/main/docs/council/UX-DESIGN-REVIEW.md | https://github.com/arunpr614/Life-Reflection/blob/main/docs/architecture/PHASE1-IMPLEMENTATION-PLAN.md | Verify one owner-approved source survives upload, restart, export, backup, restore, and rollback without time/date drift. | Release acceptance for REL-R1-001 — First-memory Restore/Rollback Acceptance links independent QA, five-seat review, every task-specific dossier, backup/separate-path restore for each new shape, rollback, defect gate, and proceed/hold/rollback record; a human attestation is included only for a named non-delegable act. | Validates rollback and restore for every persistent shape introduced by the milestone; acceptance never substitutes a successful backup upload for restore evidence. | Move to Done only when the named task evidence exists; prototype or document intent cannot prove implementation or release completion. | https://github.com/arunpr614/Life-Reflection/issues/14
PRD-R2-001 | Telegram Capture PRD | Done | Incomplete | No | planning-only-historical | R2 | Product definition | Product Manager | High | 2026-09-21 | 2026-09-23 | 3 | LID-TG-001, LID-TG-002, LID-TG-003, LID-TG-004, LID-TG-005, LID-TG-006, LID-TG-007, LID-TG-008, LID-TG-009, LID-TG-010, LID-OPS-005, LID-OPS-009, LID-OPS-011, LID-OPS-015, LID-OPS-018 | PC-001 | https://github.com/arunpr614/Life-Reflection/blob/main/docs/product/releases/PRD-R2-TELEGRAM-PHOTO-CAPTURE.md | https://github.com/arunpr614/Life-Reflection/blob/main/docs/work-items/PRD-R2-001/P0-PRD-R2-001-PRD.md | https://github.com/arunpr614/Life-Reflection/blob/main/docs/work-items/PRD-R2-001/P0-PRD-R2-001-TECHNICAL-PLAN.md | https://github.com/arunpr614/Life-Reflection/blob/main/docs/work-items/PRD-R2-001/P0-PRD-R2-001-DESIGN-SPEC.md | https://github.com/arunpr614/Life-Reflection/blob/main/docs/work-items/PRD-R2-001/P0-PRD-R2-001-QA-PLAN.md | https://github.com/arunpr614/Life-Reflection/blob/main/docs/work-items/PRD-R2-001/P0-PRD-R2-001-DELIVERY-CHECKLIST.md | https://github.com/arunpr614/Life-Reflection/blob/main/docs/work-items/PRD-R2-001/P0-PRD-R2-001-COUNCIL-READINESS.md | https://github.com/arunpr614/Life-Reflection/blob/main/docs/council/UX-DESIGN-REVIEW.md | https://github.com/arunpr614/Life-Reflection/blob/main/docs/architecture/PHASE1-IMPLEMENTATION-PLAN.md | Define authorized media forms, dating/review, durable acknowledgement, gallery, duplicate, caption, and privacy behavior. | Release document docs/product/releases/PRD-R2-TELEGRAM-PHOTO-CAPTURE.md exists, passes link/requirement validation, and separates council-delegated evidence gates from specifically named non-delegable human acts. | Planning evidence only; no production data mutation. Any later implementation still needs its own migration, restore, and rollback proof. | This planning artifact is complete; it does not claim feature implementation, deployment, production readiness, or release acceptance. | https://github.com/arunpr614/Life-Reflection/issues/15
UX-R2-001 | Telegram/Date Review/Gallery Designs | Backlog | Incomplete | No | future-release-gated | R2 | Design | UI/UX Designer | High | 2026-09-21 | 2026-09-25 | 5 | LID-TG-002, LID-TG-003, LID-TG-004, LID-TG-005, LID-TG-006, LID-TG-007, LID-TG-008, LID-TG-009, LID-OPS-015 | PRD-R2-001 | https://github.com/arunpr614/Life-Reflection/blob/main/docs/product/releases/PRD-R2-TELEGRAM-PHOTO-CAPTURE.md | https://github.com/arunpr614/Life-Reflection/blob/main/docs/work-items/UX-R2-001/P0-UX-R2-001-PRD.md | https://github.com/arunpr614/Life-Reflection/blob/main/docs/work-items/UX-R2-001/P0-UX-R2-001-TECHNICAL-PLAN.md | https://github.com/arunpr614/Life-Reflection/blob/main/docs/work-items/UX-R2-001/P0-UX-R2-001-DESIGN-SPEC.md | https://github.com/arunpr614/Life-Reflection/blob/main/docs/work-items/UX-R2-001/P0-UX-R2-001-QA-PLAN.md | https://github.com/arunpr614/Life-Reflection/blob/main/docs/work-items/UX-R2-001/P0-UX-R2-001-DELIVERY-CHECKLIST.md | https://github.com/arunpr614/Life-Reflection/blob/main/docs/work-items/UX-R2-001/P0-UX-R2-001-COUNCIL-READINESS.md | https://github.com/arunpr614/Life-Reflection/blob/main/docs/council/UX-DESIGN-REVIEW.md | https://github.com/arunpr614/Life-Reflection/blob/main/docs/architecture/PHASE1-IMPLEMENTATION-PLAN.md | Design companion messages, media/date failures, Needs Date Review, gallery, cover, duplicates, and media management. | Approved task-specific design for UX-R2-001 — Telegram/Date Review/Gallery Designs links complete normal/empty/loading/error/interruption/destructive states, responsive behavior, accessibility annotations, prototype dispositions, and Designer sign-off. | Planning evidence only; no production data mutation. Any later implementation still needs its own migration, restore, and rollback proof. | Move to Done only when the named task evidence exists; prototype or document intent cannot prove implementation or release completion. | https://github.com/arunpr614/Life-Reflection/issues/16
ARCH-R2-001 | Media Pipeline & Asset Lifecycle | Backlog | Incomplete | No | future-release-gated | R2 | Architecture | Technical Architect | High | 2026-09-21 | 2026-09-25 | 5 | LID-TG-001, LID-TG-002, LID-TG-003, LID-TG-004, LID-TG-005, LID-TG-006, LID-TG-007, LID-TG-008, LID-TG-009, LID-TG-010, LID-OPS-005, LID-OPS-009, LID-OPS-011, LID-OPS-015, LID-OPS-018 | PRD-R2-001, REL-R1-001 | https://github.com/arunpr614/Life-Reflection/blob/main/docs/product/releases/PRD-R2-TELEGRAM-PHOTO-CAPTURE.md | https://github.com/arunpr614/Life-Reflection/blob/main/docs/work-items/ARCH-R2-001/P0-ARCH-R2-001-PRD.md | https://github.com/arunpr614/Life-Reflection/blob/main/docs/work-items/ARCH-R2-001/P0-ARCH-R2-001-TECHNICAL-PLAN.md | https://github.com/arunpr614/Life-Reflection/blob/main/docs/work-items/ARCH-R2-001/P0-ARCH-R2-001-DESIGN-SPEC.md | https://github.com/arunpr614/Life-Reflection/blob/main/docs/work-items/ARCH-R2-001/P0-ARCH-R2-001-QA-PLAN.md | https://github.com/arunpr614/Life-Reflection/blob/main/docs/work-items/ARCH-R2-001/P0-ARCH-R2-001-DELIVERY-CHECKLIST.md | https://github.com/arunpr614/Life-Reflection/blob/main/docs/work-items/ARCH-R2-001/P0-ARCH-R2-001-COUNCIL-READINESS.md | https://github.com/arunpr614/Life-Reflection/blob/main/docs/council/UX-DESIGN-REVIEW.md | https://github.com/arunpr614/Life-Reflection/blob/main/docs/architecture/PHASE1-IMPLEMENTATION-PLAN.md | Define callback authorization, bounded staging/decoding, ciphertext/derivative flow, media references, deduplication, and restore. | Approved task-specific technical plan for ARCH-R2-001 — Media Pipeline & Asset Lifecycle links owned modules, ADRs, threats/data flows, interfaces/data shapes, capacity, migration, restore, rollback, and Architect sign-off. | No personal-data mutation is authorized by this task; it must define or prove reversible deployment and recovery before dependent implementation. | Move to Done only when the named task evidence exists; prototype or document intent cannot prove implementation or release completion. | https://github.com/arunpr614/Life-Reflection/issues/17
ENG-R2-001 | Telegram Authorization & Durable Capture | Backlog | Incomplete | No | future-release-gated | R2 | Implementation | Engineering | High | 2026-09-24 | 2026-10-02 | 9 | LID-TG-001, LID-TG-002, LID-TG-003, LID-TG-004, LID-TG-005, LID-TG-006, LID-OPS-005, LID-OPS-011, LID-OPS-015, LID-OPS-018 | UX-R2-001, ARCH-R2-001, REL-R1-001 | https://github.com/arunpr614/Life-Reflection/blob/main/docs/product/releases/PRD-R2-TELEGRAM-PHOTO-CAPTURE.md | https://github.com/arunpr614/Life-Reflection/blob/main/docs/work-items/ENG-R2-001/P0-ENG-R2-001-PRD.md | https://github.com/arunpr614/Life-Reflection/blob/main/docs/work-items/ENG-R2-001/P0-ENG-R2-001-TECHNICAL-PLAN.md | https://github.com/arunpr614/Life-Reflection/blob/main/docs/work-items/ENG-R2-001/P0-ENG-R2-001-DESIGN-SPEC.md | https://github.com/arunpr614/Life-Reflection/blob/main/docs/work-items/ENG-R2-001/P0-ENG-R2-001-QA-PLAN.md | https://github.com/arunpr614/Life-Reflection/blob/main/docs/work-items/ENG-R2-001/P0-ENG-R2-001-DELIVERY-CHECKLIST.md | https://github.com/arunpr614/Life-Reflection/blob/main/docs/work-items/ENG-R2-001/P0-ENG-R2-001-COUNCIL-READINESS.md | https://github.com/arunpr614/Life-Reflection/blob/main/docs/council/UX-DESIGN-REVIEW.md | https://github.com/arunpr614/Life-Reflection/blob/main/docs/architecture/PHASE1-IMPLEMENTATION-PLAN.md | Implement secret/sender/chat authorization, media validation, exact dating, review holding, and post-commit acknowledgement. | Merged implementation for ENG-R2-001 — Telegram Authorization & Durable Capture proves “Implement secret/sender/chat authorization, media validation, exact dating, review holding, and post-commit acknowledgement.” with task-specific tests, immutable build/SBOM, migrations, sanitized deployment evidence when authorized, separate-path restore, rollback, and no-regression results. | Adds encrypted media, derivative, gallery, duplicate-reference, and review-queue state; migration must be reversible and backup/restore coverage must pass before release acceptance. | Move to Done only when the named task evidence exists; prototype or document intent cannot prove implementation or release completion. | https://github.com/arunpr614/Life-Reflection/issues/18
ENG-R2-002 | Gallery/Cover/Dedup/Derivatives | Backlog | Incomplete | No | future-release-gated | R2 | Implementation | Engineering | High | 2026-09-28 | 2026-10-06 | 9 | LID-TG-007, LID-TG-008, LID-TG-009, LID-TG-010, LID-OPS-009, LID-OPS-011, LID-OPS-018 | ENG-R2-001 | https://github.com/arunpr614/Life-Reflection/blob/main/docs/product/releases/PRD-R2-TELEGRAM-PHOTO-CAPTURE.md | https://github.com/arunpr614/Life-Reflection/blob/main/docs/work-items/ENG-R2-002/P0-ENG-R2-002-PRD.md | https://github.com/arunpr614/Life-Reflection/blob/main/docs/work-items/ENG-R2-002/P0-ENG-R2-002-TECHNICAL-PLAN.md | https://github.com/arunpr614/Life-Reflection/blob/main/docs/work-items/ENG-R2-002/P0-ENG-R2-002-DESIGN-SPEC.md | https://github.com/arunpr614/Life-Reflection/blob/main/docs/work-items/ENG-R2-002/P0-ENG-R2-002-QA-PLAN.md | https://github.com/arunpr614/Life-Reflection/blob/main/docs/work-items/ENG-R2-002/P0-ENG-R2-002-DELIVERY-CHECKLIST.md | https://github.com/arunpr614/Life-Reflection/blob/main/docs/work-items/ENG-R2-002/P0-ENG-R2-002-COUNCIL-READINESS.md | https://github.com/arunpr614/Life-Reflection/blob/main/docs/council/UX-DESIGN-REVIEW.md | https://github.com/arunpr614/Life-Reflection/blob/main/docs/architecture/PHASE1-IMPLEMENTATION-PLAN.md | Implement durable gallery order, real-photo cover, global checksum references, captions, byte-preserved Originals, and local metadata-free thumbnails. | Merged implementation for ENG-R2-002 — Gallery/Cover/Dedup/Derivatives proves “Implement durable gallery order, real-photo cover, global checksum references, captions, byte-preserved Originals, and local metadata-free thumbnails.” with task-specific tests, immutable build/SBOM, migrations, sanitized deployment evidence when authorized, separate-path restore, rollback, and no-regression results. | Adds encrypted media, derivative, gallery, duplicate-reference, and review-queue state; migration must be reversible and backup/restore coverage must pass before release acceptance. | Move to Done only when the named task evidence exists; prototype or document intent cannot prove implementation or release completion. | https://github.com/arunpr614/Life-Reflection/issues/19
REL-R2-001 | Media Privacy/Restore Acceptance | Backlog | Incomplete | No | future-release-gated | R2 | Release acceptance | Project Manager + Independent QA | High | 2026-10-07 | 2026-10-09 | 3 | LID-TG-001, LID-TG-002, LID-TG-003, LID-TG-004, LID-TG-005, LID-TG-006, LID-TG-007, LID-TG-008, LID-TG-009, LID-TG-010, LID-OPS-005, LID-OPS-009, LID-OPS-011, LID-OPS-015, LID-OPS-018 | ENG-R2-001, ENG-R2-002 | https://github.com/arunpr614/Life-Reflection/blob/main/docs/product/releases/PRD-R2-TELEGRAM-PHOTO-CAPTURE.md | https://github.com/arunpr614/Life-Reflection/blob/main/docs/work-items/REL-R2-001/P0-REL-R2-001-PRD.md | https://github.com/arunpr614/Life-Reflection/blob/main/docs/work-items/REL-R2-001/P0-REL-R2-001-TECHNICAL-PLAN.md | https://github.com/arunpr614/Life-Reflection/blob/main/docs/work-items/REL-R2-001/P0-REL-R2-001-DESIGN-SPEC.md | https://github.com/arunpr614/Life-Reflection/blob/main/docs/work-items/REL-R2-001/P0-REL-R2-001-QA-PLAN.md | https://github.com/arunpr614/Life-Reflection/blob/main/docs/work-items/REL-R2-001/P0-REL-R2-001-DELIVERY-CHECKLIST.md | https://github.com/arunpr614/Life-Reflection/blob/main/docs/work-items/REL-R2-001/P0-REL-R2-001-COUNCIL-READINESS.md | https://github.com/arunpr614/Life-Reflection/blob/main/docs/council/UX-DESIGN-REVIEW.md | https://github.com/arunpr614/Life-Reflection/blob/main/docs/architecture/PHASE1-IMPLEMENTATION-PLAN.md | Execute capture, invalid input/date, album, duplicate, cover, Original, AI-exclusion, media restore, and rollback fixtures. | Release acceptance for REL-R2-001 — Media Privacy/Restore Acceptance links independent QA, five-seat review, every task-specific dossier, backup/separate-path restore for each new shape, rollback, defect gate, and proceed/hold/rollback record; a human attestation is included only for a named non-delegable act. | Validates rollback and restore for every persistent shape introduced by the milestone; acceptance never substitutes a successful backup upload for restore evidence. | Move to Done only when the named task evidence exists; prototype or document intent cannot prove implementation or release completion. | https://github.com/arunpr614/Life-Reflection/issues/20
PRD-R3-001 | Retrieval & Date Integrity PRD | Done | Incomplete | No | planning-only-historical | R3 | Product definition | Product Manager | High | 2026-10-12 | 2026-10-14 | 3 | LID-SRC-003, LID-REF-002, LID-REF-003, LID-REF-006, LID-OPS-011, LID-OPS-018 | PC-001 | https://github.com/arunpr614/Life-Reflection/blob/main/docs/product/releases/PRD-R3-RETRIEVAL-DATE-INTEGRITY.md | https://github.com/arunpr614/Life-Reflection/blob/main/docs/work-items/PRD-R3-001/P0-PRD-R3-001-PRD.md | https://github.com/arunpr614/Life-Reflection/blob/main/docs/work-items/PRD-R3-001/P0-PRD-R3-001-TECHNICAL-PLAN.md | https://github.com/arunpr614/Life-Reflection/blob/main/docs/work-items/PRD-R3-001/P0-PRD-R3-001-DESIGN-SPEC.md | https://github.com/arunpr614/Life-Reflection/blob/main/docs/work-items/PRD-R3-001/P0-PRD-R3-001-QA-PLAN.md | https://github.com/arunpr614/Life-Reflection/blob/main/docs/work-items/PRD-R3-001/P0-PRD-R3-001-DELIVERY-CHECKLIST.md | https://github.com/arunpr614/Life-Reflection/blob/main/docs/work-items/PRD-R3-001/P0-PRD-R3-001-COUNCIL-READINESS.md | https://github.com/arunpr614/Life-Reflection/blob/main/docs/council/UX-DESIGN-REVIEW.md | https://github.com/arunpr614/Life-Reflection/blob/main/docs/architecture/PHASE1-IMPLEMENTATION-PLAN.md | Define the cross-month Monthly Almanac, exact retrieval, query privacy, Date Review, and atomic redating invariants. | Release document docs/product/releases/PRD-R3-RETRIEVAL-DATE-INTEGRITY.md exists, passes link/requirement validation, and separates council-delegated evidence gates from specifically named non-delegable human acts. | Planning evidence only; no production data mutation. Any later implementation still needs its own migration, restore, and rollback proof. | This planning artifact is complete; it does not claim feature implementation, deployment, production readiness, or release acceptance. | https://github.com/arunpr614/Life-Reflection/issues/21
UX-R3-001 | Almanac/Search/Date Review Designs | Backlog | Incomplete | No | future-release-gated | R3 | Design | UI/UX Designer | High | 2026-10-12 | 2026-10-16 | 5 | LID-SRC-003, LID-REF-002, LID-REF-003, LID-REF-006 | PRD-R3-001 | https://github.com/arunpr614/Life-Reflection/blob/main/docs/product/releases/PRD-R3-RETRIEVAL-DATE-INTEGRITY.md | https://github.com/arunpr614/Life-Reflection/blob/main/docs/work-items/UX-R3-001/P0-UX-R3-001-PRD.md | https://github.com/arunpr614/Life-Reflection/blob/main/docs/work-items/UX-R3-001/P0-UX-R3-001-TECHNICAL-PLAN.md | https://github.com/arunpr614/Life-Reflection/blob/main/docs/work-items/UX-R3-001/P0-UX-R3-001-DESIGN-SPEC.md | https://github.com/arunpr614/Life-Reflection/blob/main/docs/work-items/UX-R3-001/P0-UX-R3-001-QA-PLAN.md | https://github.com/arunpr614/Life-Reflection/blob/main/docs/work-items/UX-R3-001/P0-UX-R3-001-DELIVERY-CHECKLIST.md | https://github.com/arunpr614/Life-Reflection/blob/main/docs/work-items/UX-R3-001/P0-UX-R3-001-COUNCIL-READINESS.md | https://github.com/arunpr614/Life-Reflection/blob/main/docs/council/UX-DESIGN-REVIEW.md | https://github.com/arunpr614/Life-Reflection/blob/main/docs/architecture/PHASE1-IMPLEMENTATION-PLAN.md | Design the Monthly Almanac, search scope/results/history, Date Review, redating preview, interruption, and failure states. | Approved task-specific design for UX-R3-001 — Almanac/Search/Date Review Designs links complete normal/empty/loading/error/interruption/destructive states, responsive behavior, accessibility annotations, prototype dispositions, and Designer sign-off. | Planning evidence only; no production data mutation. Any later implementation still needs its own migration, restore, and rollback proof. | Move to Done only when the named task evidence exists; prototype or document intent cannot prove implementation or release completion. | https://github.com/arunpr614/Life-Reflection/issues/22
ARCH-R3-001 | Search Index & Redating Transaction | Backlog | Incomplete | No | future-release-gated | R3 | Architecture | Technical Architect | High | 2026-10-12 | 2026-10-16 | 5 | LID-SRC-003, LID-REF-002, LID-REF-003, LID-REF-006, LID-OPS-011, LID-OPS-018 | PRD-R3-001, REL-R2-001 | https://github.com/arunpr614/Life-Reflection/blob/main/docs/product/releases/PRD-R3-RETRIEVAL-DATE-INTEGRITY.md | https://github.com/arunpr614/Life-Reflection/blob/main/docs/work-items/ARCH-R3-001/P0-ARCH-R3-001-PRD.md | https://github.com/arunpr614/Life-Reflection/blob/main/docs/work-items/ARCH-R3-001/P0-ARCH-R3-001-TECHNICAL-PLAN.md | https://github.com/arunpr614/Life-Reflection/blob/main/docs/work-items/ARCH-R3-001/P0-ARCH-R3-001-DESIGN-SPEC.md | https://github.com/arunpr614/Life-Reflection/blob/main/docs/work-items/ARCH-R3-001/P0-ARCH-R3-001-QA-PLAN.md | https://github.com/arunpr614/Life-Reflection/blob/main/docs/work-items/ARCH-R3-001/P0-ARCH-R3-001-DELIVERY-CHECKLIST.md | https://github.com/arunpr614/Life-Reflection/blob/main/docs/work-items/ARCH-R3-001/P0-ARCH-R3-001-COUNCIL-READINESS.md | https://github.com/arunpr614/Life-Reflection/blob/main/docs/council/UX-DESIGN-REVIEW.md | https://github.com/arunpr614/Life-Reflection/blob/main/docs/architecture/PHASE1-IMPLEMENTATION-PLAN.md | Define encrypted lexical indexes, query/log privacy, date-review storage, and one-transaction old/new-day redating. | Approved task-specific technical plan for ARCH-R3-001 — Search Index & Redating Transaction links owned modules, ADRs, threats/data flows, interfaces/data shapes, capacity, migration, restore, rollback, and Architect sign-off. | No personal-data mutation is authorized by this task; it must define or prove reversible deployment and recovery before dependent implementation. | Move to Done only when the named task evidence exists; prototype or document intent cannot prove implementation or release completion. | https://github.com/arunpr614/Life-Reflection/issues/23
ENG-R3-001 | Almanac/Search/Date Review/Redating | Backlog | Incomplete | No | future-release-gated | R3 | Implementation | Engineering | High | 2026-10-15 | 2026-10-28 | 14 | LID-SRC-003, LID-REF-002, LID-REF-003, LID-REF-006, LID-OPS-011, LID-OPS-018 | UX-R3-001, ARCH-R3-001, REL-R2-001 | https://github.com/arunpr614/Life-Reflection/blob/main/docs/product/releases/PRD-R3-RETRIEVAL-DATE-INTEGRITY.md | https://github.com/arunpr614/Life-Reflection/blob/main/docs/work-items/ENG-R3-001/P0-ENG-R3-001-PRD.md | https://github.com/arunpr614/Life-Reflection/blob/main/docs/work-items/ENG-R3-001/P0-ENG-R3-001-TECHNICAL-PLAN.md | https://github.com/arunpr614/Life-Reflection/blob/main/docs/work-items/ENG-R3-001/P0-ENG-R3-001-DESIGN-SPEC.md | https://github.com/arunpr614/Life-Reflection/blob/main/docs/work-items/ENG-R3-001/P0-ENG-R3-001-QA-PLAN.md | https://github.com/arunpr614/Life-Reflection/blob/main/docs/work-items/ENG-R3-001/P0-ENG-R3-001-DELIVERY-CHECKLIST.md | https://github.com/arunpr614/Life-Reflection/blob/main/docs/work-items/ENG-R3-001/P0-ENG-R3-001-COUNCIL-READINESS.md | https://github.com/arunpr614/Life-Reflection/blob/main/docs/council/UX-DESIGN-REVIEW.md | https://github.com/arunpr614/Life-Reflection/blob/main/docs/architecture/PHASE1-IMPLEMENTATION-PLAN.md | Implement cross-month Almanac browsing, deterministic lexical/date/tag/caption retrieval, review resolution, and atomic redating. | Merged implementation for ENG-R3-001 — Almanac/Search/Date Review/Redating proves “Implement cross-month Almanac browsing, deterministic lexical/date/tag/caption retrieval, review resolution, and atomic redating.” with task-specific tests, immutable build/SBOM, migrations, sanitized deployment evidence when authorized, separate-path restore, rollback, and no-regression results. | Adds search index, date-review, and atomic redating state; migration must be reversible and backup/restore coverage must pass before release acceptance. | Move to Done only when the named task evidence exists; prototype or document intent cannot prove implementation or release completion. | https://github.com/arunpr614/Life-Reflection/issues/24
REL-R3-001 | Query Privacy & Date Atomicity Acceptance | Backlog | Incomplete | No | future-release-gated | R3 | Release acceptance | Project Manager + Independent QA | High | 2026-10-29 | 2026-10-30 | 2 | LID-SRC-003, LID-REF-002, LID-REF-003, LID-REF-006, LID-OPS-011, LID-OPS-018 | ENG-R3-001 | https://github.com/arunpr614/Life-Reflection/blob/main/docs/product/releases/PRD-R3-RETRIEVAL-DATE-INTEGRITY.md | https://github.com/arunpr614/Life-Reflection/blob/main/docs/work-items/REL-R3-001/P0-REL-R3-001-PRD.md | https://github.com/arunpr614/Life-Reflection/blob/main/docs/work-items/REL-R3-001/P0-REL-R3-001-TECHNICAL-PLAN.md | https://github.com/arunpr614/Life-Reflection/blob/main/docs/work-items/REL-R3-001/P0-REL-R3-001-DESIGN-SPEC.md | https://github.com/arunpr614/Life-Reflection/blob/main/docs/work-items/REL-R3-001/P0-REL-R3-001-QA-PLAN.md | https://github.com/arunpr614/Life-Reflection/blob/main/docs/work-items/REL-R3-001/P0-REL-R3-001-DELIVERY-CHECKLIST.md | https://github.com/arunpr614/Life-Reflection/blob/main/docs/work-items/REL-R3-001/P0-REL-R3-001-COUNCIL-READINESS.md | https://github.com/arunpr614/Life-Reflection/blob/main/docs/council/UX-DESIGN-REVIEW.md | https://github.com/arunpr614/Life-Reflection/blob/main/docs/architecture/PHASE1-IMPLEMENTATION-PLAN.md | Verify exact results, opt-in history, zero query leakage, two-day atomicity, index recovery, restore, and rollback. | Release acceptance for REL-R3-001 — Query Privacy & Date Atomicity Acceptance links independent QA, five-seat review, every task-specific dossier, backup/separate-path restore for each new shape, rollback, defect gate, and proceed/hold/rollback record; a human attestation is included only for a named non-delegable act. | Validates rollback and restore for every persistent shape introduced by the milestone; acceptance never substitutes a successful backup upload for restore evidence. | Move to Done only when the named task evidence exists; prototype or document intent cannot prove implementation or release completion. | https://github.com/arunpr614/Life-Reflection/issues/25
PRD-R4-001 | Lifecycle PRD | Done | Incomplete | No | planning-only-historical | R4 | Product definition | Product Manager | High | 2026-11-02 | 2026-11-04 | 3 | LID-SCP-004, LID-SRC-001, LID-SRC-002, LID-SRC-004, LID-REF-007, LID-OPS-010, LID-OPS-011, LID-OPS-013, LID-OPS-018 | PC-001 | https://github.com/arunpr614/Life-Reflection/blob/main/docs/product/releases/PRD-R4-SOURCE-HISTORY-LIFECYCLE.md | https://github.com/arunpr614/Life-Reflection/blob/main/docs/work-items/PRD-R4-001/P0-PRD-R4-001-PRD.md | https://github.com/arunpr614/Life-Reflection/blob/main/docs/work-items/PRD-R4-001/P0-PRD-R4-001-TECHNICAL-PLAN.md | https://github.com/arunpr614/Life-Reflection/blob/main/docs/work-items/PRD-R4-001/P0-PRD-R4-001-DESIGN-SPEC.md | https://github.com/arunpr614/Life-Reflection/blob/main/docs/work-items/PRD-R4-001/P0-PRD-R4-001-QA-PLAN.md | https://github.com/arunpr614/Life-Reflection/blob/main/docs/work-items/PRD-R4-001/P0-PRD-R4-001-DELIVERY-CHECKLIST.md | https://github.com/arunpr614/Life-Reflection/blob/main/docs/work-items/PRD-R4-001/P0-PRD-R4-001-COUNCIL-READINESS.md | https://github.com/arunpr614/Life-Reflection/blob/main/docs/council/UX-DESIGN-REVIEW.md | https://github.com/arunpr614/Life-Reflection/blob/main/docs/architecture/PHASE1-IMPLEMENTATION-PLAN.md | Define Corrections, conflict choices, source binding, History, Trash, suppressions, confirmations, and complete export. | Release document docs/product/releases/PRD-R4-SOURCE-HISTORY-LIFECYCLE.md exists, passes link/requirement validation, and separates council-delegated evidence gates from specifically named non-delegable human acts. | Planning evidence only; no production data mutation. Any later implementation still needs its own migration, restore, and rollback proof. | This planning artifact is complete; it does not claim feature implementation, deployment, production readiness, or release acceptance. | https://github.com/arunpr614/Life-Reflection/issues/26
UX-R4-001 | Diff/History/Trash/Export Designs | Backlog | Incomplete | No | future-release-gated | R4 | Design | UI/UX Designer | High | 2026-11-02 | 2026-11-06 | 5 | LID-SCP-004, LID-SRC-001, LID-SRC-002, LID-SRC-004, LID-REF-007, LID-OPS-010, LID-OPS-013 | PRD-R4-001 | https://github.com/arunpr614/Life-Reflection/blob/main/docs/product/releases/PRD-R4-SOURCE-HISTORY-LIFECYCLE.md | https://github.com/arunpr614/Life-Reflection/blob/main/docs/work-items/UX-R4-001/P0-UX-R4-001-PRD.md | https://github.com/arunpr614/Life-Reflection/blob/main/docs/work-items/UX-R4-001/P0-UX-R4-001-TECHNICAL-PLAN.md | https://github.com/arunpr614/Life-Reflection/blob/main/docs/work-items/UX-R4-001/P0-UX-R4-001-DESIGN-SPEC.md | https://github.com/arunpr614/Life-Reflection/blob/main/docs/work-items/UX-R4-001/P0-UX-R4-001-QA-PLAN.md | https://github.com/arunpr614/Life-Reflection/blob/main/docs/work-items/UX-R4-001/P0-UX-R4-001-DELIVERY-CHECKLIST.md | https://github.com/arunpr614/Life-Reflection/blob/main/docs/work-items/UX-R4-001/P0-UX-R4-001-COUNCIL-READINESS.md | https://github.com/arunpr614/Life-Reflection/blob/main/docs/council/UX-DESIGN-REVIEW.md | https://github.com/arunpr614/Life-Reflection/blob/main/docs/architecture/PHASE1-IMPLEMENTATION-PLAN.md | Design accessible diff, Correction, History, Trash, suppression, confirmation, and encrypted-export workflows. | Approved task-specific design for UX-R4-001 — Diff/History/Trash/Export Designs links complete normal/empty/loading/error/interruption/destructive states, responsive behavior, accessibility annotations, prototype dispositions, and Designer sign-off. | Planning evidence only; no production data mutation. Any later implementation still needs its own migration, restore, and rollback proof. | Move to Done only when the named task evidence exists; prototype or document intent cannot prove implementation or release completion. | https://github.com/arunpr614/Life-Reflection/issues/27
ARCH-R4-001 | Revision/Suppression/Export Lifecycle | Backlog | Incomplete | No | future-release-gated | R4 | Architecture | Technical Architect | High | 2026-11-02 | 2026-11-06 | 5 | LID-SCP-004, LID-SRC-001, LID-SRC-002, LID-SRC-004, LID-REF-007, LID-OPS-010, LID-OPS-011, LID-OPS-013, LID-OPS-018 | PRD-R4-001, REL-R3-001 | https://github.com/arunpr614/Life-Reflection/blob/main/docs/product/releases/PRD-R4-SOURCE-HISTORY-LIFECYCLE.md | https://github.com/arunpr614/Life-Reflection/blob/main/docs/work-items/ARCH-R4-001/P0-ARCH-R4-001-PRD.md | https://github.com/arunpr614/Life-Reflection/blob/main/docs/work-items/ARCH-R4-001/P0-ARCH-R4-001-TECHNICAL-PLAN.md | https://github.com/arunpr614/Life-Reflection/blob/main/docs/work-items/ARCH-R4-001/P0-ARCH-R4-001-DESIGN-SPEC.md | https://github.com/arunpr614/Life-Reflection/blob/main/docs/work-items/ARCH-R4-001/P0-ARCH-R4-001-QA-PLAN.md | https://github.com/arunpr614/Life-Reflection/blob/main/docs/work-items/ARCH-R4-001/P0-ARCH-R4-001-DELIVERY-CHECKLIST.md | https://github.com/arunpr614/Life-Reflection/blob/main/docs/work-items/ARCH-R4-001/P0-ARCH-R4-001-COUNCIL-READINESS.md | https://github.com/arunpr614/Life-Reflection/blob/main/docs/council/UX-DESIGN-REVIEW.md | https://github.com/arunpr614/Life-Reflection/blob/main/docs/architecture/PHASE1-IMPLEMENTATION-PLAN.md | Define immutable revisions/Corrections, active display binding, Trash/suppression state machine, passphrase handoff, export cleanup, and restore. | Approved task-specific technical plan for ARCH-R4-001 — Revision/Suppression/Export Lifecycle links owned modules, ADRs, threats/data flows, interfaces/data shapes, capacity, migration, restore, rollback, and Architect sign-off. | No personal-data mutation is authorized by this task; it must define or prove reversible deployment and recovery before dependent implementation. | Move to Done only when the named task evidence exists; prototype or document intent cannot prove implementation or release completion. | https://github.com/arunpr614/Life-Reflection/issues/28
ENG-R4-001 | Corrections/Conflict/History | Backlog | Incomplete | No | future-release-gated | R4 | Implementation | Engineering | High | 2026-11-05 | 2026-11-13 | 9 | LID-SCP-004, LID-SRC-001, LID-SRC-002, LID-SRC-004, LID-REF-007, LID-OPS-011, LID-OPS-018 | UX-R4-001, ARCH-R4-001, REL-R3-001 | https://github.com/arunpr614/Life-Reflection/blob/main/docs/product/releases/PRD-R4-SOURCE-HISTORY-LIFECYCLE.md | https://github.com/arunpr614/Life-Reflection/blob/main/docs/work-items/ENG-R4-001/P0-ENG-R4-001-PRD.md | https://github.com/arunpr614/Life-Reflection/blob/main/docs/work-items/ENG-R4-001/P0-ENG-R4-001-TECHNICAL-PLAN.md | https://github.com/arunpr614/Life-Reflection/blob/main/docs/work-items/ENG-R4-001/P0-ENG-R4-001-DESIGN-SPEC.md | https://github.com/arunpr614/Life-Reflection/blob/main/docs/work-items/ENG-R4-001/P0-ENG-R4-001-QA-PLAN.md | https://github.com/arunpr614/Life-Reflection/blob/main/docs/work-items/ENG-R4-001/P0-ENG-R4-001-DELIVERY-CHECKLIST.md | https://github.com/arunpr614/Life-Reflection/blob/main/docs/work-items/ENG-R4-001/P0-ENG-R4-001-COUNCIL-READINESS.md | https://github.com/arunpr614/Life-Reflection/blob/main/docs/council/UX-DESIGN-REVIEW.md | https://github.com/arunpr614/Life-Reflection/blob/main/docs/architecture/PHASE1-IMPLEMENTATION-PLAN.md | Implement immutable Corrections, retained revisions, exactly three conflict outcomes, exact source-set binding, and inspectable History. | Merged implementation for ENG-R4-001 — Corrections/Conflict/History proves “Implement immutable Corrections, retained revisions, exactly three conflict outcomes, exact source-set binding, and inspectable History.” with task-specific tests, immutable build/SBOM, migrations, sanitized deployment evidence when authorized, separate-path restore, rollback, and no-regression results. | Adds revision, Correction, conflict, Trash, suppression, and export state; migration must be reversible and backup/restore coverage must pass before release acceptance. | Move to Done only when the named task evidence exists; prototype or document intent cannot prove implementation or release completion. | https://github.com/arunpr614/Life-Reflection/issues/29
ENG-R4-002 | Trash/Suppressions/Export | Backlog | Incomplete | No | future-release-gated | R4 | Implementation | Engineering | High | 2026-11-09 | 2026-11-18 | 10 | LID-SCP-004, LID-REF-007, LID-OPS-010, LID-OPS-011, LID-OPS-013, LID-OPS-018 | ENG-R4-001 | https://github.com/arunpr614/Life-Reflection/blob/main/docs/product/releases/PRD-R4-SOURCE-HISTORY-LIFECYCLE.md | https://github.com/arunpr614/Life-Reflection/blob/main/docs/work-items/ENG-R4-002/P0-ENG-R4-002-PRD.md | https://github.com/arunpr614/Life-Reflection/blob/main/docs/work-items/ENG-R4-002/P0-ENG-R4-002-TECHNICAL-PLAN.md | https://github.com/arunpr614/Life-Reflection/blob/main/docs/work-items/ENG-R4-002/P0-ENG-R4-002-DESIGN-SPEC.md | https://github.com/arunpr614/Life-Reflection/blob/main/docs/work-items/ENG-R4-002/P0-ENG-R4-002-QA-PLAN.md | https://github.com/arunpr614/Life-Reflection/blob/main/docs/work-items/ENG-R4-002/P0-ENG-R4-002-DELIVERY-CHECKLIST.md | https://github.com/arunpr614/Life-Reflection/blob/main/docs/work-items/ENG-R4-002/P0-ENG-R4-002-COUNCIL-READINESS.md | https://github.com/arunpr614/Life-Reflection/blob/main/docs/council/UX-DESIGN-REVIEW.md | https://github.com/arunpr614/Life-Reflection/blob/main/docs/architecture/PHASE1-IMPLEMENTATION-PLAN.md | Implement 30-day Trash, restoration/permanent deletion, suppressions, complete encrypted export, cleanup, and import validation. | Merged implementation for ENG-R4-002 — Trash/Suppressions/Export proves “Implement 30-day Trash, restoration/permanent deletion, suppressions, complete encrypted export, cleanup, and import validation.” with task-specific tests, immutable build/SBOM, migrations, sanitized deployment evidence when authorized, separate-path restore, rollback, and no-regression results. | Adds revision, Correction, conflict, Trash, suppression, and export state; migration must be reversible and backup/restore coverage must pass before release acceptance. | Move to Done only when the named task evidence exists; prototype or document intent cannot prove implementation or release completion. | https://github.com/arunpr614/Life-Reflection/issues/30
REL-R4-001 | Lifecycle/Export Restore Acceptance | Backlog | Incomplete | No | future-release-gated | R4 | Release acceptance | Project Manager + Independent QA | High | 2026-11-19 | 2026-11-20 | 2 | LID-SCP-004, LID-SRC-001, LID-SRC-002, LID-SRC-004, LID-REF-007, LID-OPS-010, LID-OPS-011, LID-OPS-013, LID-OPS-018 | ENG-R4-001, ENG-R4-002 | https://github.com/arunpr614/Life-Reflection/blob/main/docs/product/releases/PRD-R4-SOURCE-HISTORY-LIFECYCLE.md | https://github.com/arunpr614/Life-Reflection/blob/main/docs/work-items/REL-R4-001/P0-REL-R4-001-PRD.md | https://github.com/arunpr614/Life-Reflection/blob/main/docs/work-items/REL-R4-001/P0-REL-R4-001-TECHNICAL-PLAN.md | https://github.com/arunpr614/Life-Reflection/blob/main/docs/work-items/REL-R4-001/P0-REL-R4-001-DESIGN-SPEC.md | https://github.com/arunpr614/Life-Reflection/blob/main/docs/work-items/REL-R4-001/P0-REL-R4-001-QA-PLAN.md | https://github.com/arunpr614/Life-Reflection/blob/main/docs/work-items/REL-R4-001/P0-REL-R4-001-DELIVERY-CHECKLIST.md | https://github.com/arunpr614/Life-Reflection/blob/main/docs/work-items/REL-R4-001/P0-REL-R4-001-COUNCIL-READINESS.md | https://github.com/arunpr614/Life-Reflection/blob/main/docs/council/UX-DESIGN-REVIEW.md | https://github.com/arunpr614/Life-Reflection/blob/main/docs/architecture/PHASE1-IMPLEMENTATION-PLAN.md | Verify conflict outcomes, deletion/restoration, day visibility, suppression, export completeness, import/restore, and rollback. | Release acceptance for REL-R4-001 — Lifecycle/Export Restore Acceptance links independent QA, five-seat review, every task-specific dossier, backup/separate-path restore for each new shape, rollback, defect gate, and proceed/hold/rollback record; a human attestation is included only for a named non-delegable act. | Validates rollback and restore for every persistent shape introduced by the milestone; acceptance never substitutes a successful backup upload for restore evidence. | Move to Done only when the named task evidence exists; prototype or document intent cannot prove implementation or release completion. | https://github.com/arunpr614/Life-Reflection/issues/31
SPK-R5-001 | VoiceNotes Synthetic Contract Spike | Backlog | Incomplete | No | future-synthetic-contract-gated | R5 | Spike | Technical Architect | High | 2026-11-23 | 2026-11-25 | 3 | LID-VN-001, LID-VN-002, LID-VN-003, LID-VN-004, LID-VN-005 | REL-R4-001 | https://github.com/arunpr614/Life-Reflection/blob/main/docs/product/releases/PRD-R5-PROSPECTIVE-VOICENOTES-SYNC.md | https://github.com/arunpr614/Life-Reflection/blob/main/docs/work-items/SPK-R5-001/P0-SPK-R5-001-PRD.md | https://github.com/arunpr614/Life-Reflection/blob/main/docs/work-items/SPK-R5-001/P0-SPK-R5-001-TECHNICAL-PLAN.md | https://github.com/arunpr614/Life-Reflection/blob/main/docs/work-items/SPK-R5-001/P0-SPK-R5-001-DESIGN-SPEC.md | https://github.com/arunpr614/Life-Reflection/blob/main/docs/work-items/SPK-R5-001/P0-SPK-R5-001-QA-PLAN.md | https://github.com/arunpr614/Life-Reflection/blob/main/docs/work-items/SPK-R5-001/P0-SPK-R5-001-DELIVERY-CHECKLIST.md | https://github.com/arunpr614/Life-Reflection/blob/main/docs/work-items/SPK-R5-001/P0-SPK-R5-001-COUNCIL-READINESS.md | https://github.com/arunpr614/Life-Reflection/blob/main/docs/council/UX-DESIGN-REVIEW.md | https://github.com/arunpr614/Life-Reflection/blob/main/docs/architecture/PHASE1-IMPLEMENTATION-PLAN.md | Prove exact note/revision identity, unattended authorization, authoritative retrieval, tag/date/transcript, wakeups, reconciliation, and failure behavior using synthetic data. | Synthetic VoiceNotes contract report proves identity, OAuth renewal, authoritative retrieval, tag/date/transcript, replay, reconciliation, and failure behavior. | No personal-data mutation is authorized by this task; it must define or prove reversible deployment and recovery before dependent implementation. | Move to Done only when the named task evidence exists; prototype or document intent cannot prove implementation or release completion. | https://github.com/arunpr614/Life-Reflection/issues/32
PRD-R5-001 | VoiceNotes PRD | Done | Incomplete | No | planning-only-historical | R5 | Product definition | Product Manager | High | 2026-11-23 | 2026-11-27 | 5 | LID-VN-001, LID-VN-002, LID-VN-003, LID-VN-004, LID-VN-005, LID-VN-006, LID-VN-007, LID-OPS-011, LID-OPS-015, LID-OPS-018 | PC-001 | https://github.com/arunpr614/Life-Reflection/blob/main/docs/product/releases/PRD-R5-PROSPECTIVE-VOICENOTES-SYNC.md | https://github.com/arunpr614/Life-Reflection/blob/main/docs/work-items/PRD-R5-001/P0-PRD-R5-001-PRD.md | https://github.com/arunpr614/Life-Reflection/blob/main/docs/work-items/PRD-R5-001/P0-PRD-R5-001-TECHNICAL-PLAN.md | https://github.com/arunpr614/Life-Reflection/blob/main/docs/work-items/PRD-R5-001/P0-PRD-R5-001-DESIGN-SPEC.md | https://github.com/arunpr614/Life-Reflection/blob/main/docs/work-items/PRD-R5-001/P0-PRD-R5-001-QA-PLAN.md | https://github.com/arunpr614/Life-Reflection/blob/main/docs/work-items/PRD-R5-001/P0-PRD-R5-001-DELIVERY-CHECKLIST.md | https://github.com/arunpr614/Life-Reflection/blob/main/docs/work-items/PRD-R5-001/P0-PRD-R5-001-COUNCIL-READINESS.md | https://github.com/arunpr614/Life-Reflection/blob/main/docs/council/UX-DESIGN-REVIEW.md | https://github.com/arunpr614/Life-Reflection/blob/main/docs/architecture/PHASE1-IMPLEMENTATION-PLAN.md | Define spike-gated prospective eligibility, activation, dating, reconciliation, revisions, suppression, and lifecycle behavior. | Release document docs/product/releases/PRD-R5-PROSPECTIVE-VOICENOTES-SYNC.md exists, passes link/requirement validation, and separates council-delegated evidence gates from specifically named non-delegable human acts. | Planning evidence only; no production data mutation. Any later implementation still needs its own migration, restore, and rollback proof. | This planning artifact is complete; it does not claim feature implementation, deployment, production readiness, or release acceptance. | https://github.com/arunpr614/Life-Reflection/issues/33
UX-R5-001 | Integration/Reconciliation/Lifecycle Designs | Backlog | Incomplete | No | future-synthetic-contract-gated | R5 | Design | UI/UX Designer | High | 2026-11-24 | 2026-11-27 | 4 | LID-VN-002, LID-VN-003, LID-VN-004, LID-VN-005, LID-VN-006, LID-VN-007, LID-OPS-015 | PRD-R5-001, SPK-R5-001 | https://github.com/arunpr614/Life-Reflection/blob/main/docs/product/releases/PRD-R5-PROSPECTIVE-VOICENOTES-SYNC.md | https://github.com/arunpr614/Life-Reflection/blob/main/docs/work-items/UX-R5-001/P0-UX-R5-001-PRD.md | https://github.com/arunpr614/Life-Reflection/blob/main/docs/work-items/UX-R5-001/P0-UX-R5-001-TECHNICAL-PLAN.md | https://github.com/arunpr614/Life-Reflection/blob/main/docs/work-items/UX-R5-001/P0-UX-R5-001-DESIGN-SPEC.md | https://github.com/arunpr614/Life-Reflection/blob/main/docs/work-items/UX-R5-001/P0-UX-R5-001-QA-PLAN.md | https://github.com/arunpr614/Life-Reflection/blob/main/docs/work-items/UX-R5-001/P0-UX-R5-001-DELIVERY-CHECKLIST.md | https://github.com/arunpr614/Life-Reflection/blob/main/docs/work-items/UX-R5-001/P0-UX-R5-001-COUNCIL-READINESS.md | https://github.com/arunpr614/Life-Reflection/blob/main/docs/council/UX-DESIGN-REVIEW.md | https://github.com/arunpr614/Life-Reflection/blob/main/docs/architecture/PHASE1-IMPLEMENTATION-PLAN.md | Design activation, integration health, Date Review, reconciliation, upstream revision/conflict, suppression, and re-import states. | Approved task-specific design for UX-R5-001 — Integration/Reconciliation/Lifecycle Designs links complete normal/empty/loading/error/interruption/destructive states, responsive behavior, accessibility annotations, prototype dispositions, and Designer sign-off. | Planning evidence only; no production data mutation. Any later implementation still needs its own migration, restore, and rollback proof. | Move to Done only when the named task evidence exists; prototype or document intent cannot prove implementation or release completion. | https://github.com/arunpr614/Life-Reflection/issues/34
ARCH-R5-001 | VoiceNotes Adapter & Reconciliation Contract | Backlog | Incomplete | No | future-synthetic-contract-gated | R5 | Architecture | Technical Architect | High | 2026-11-24 | 2026-11-27 | 4 | LID-VN-001, LID-VN-002, LID-VN-003, LID-VN-004, LID-VN-005, LID-VN-006, LID-VN-007, LID-OPS-011, LID-OPS-015, LID-OPS-018 | PRD-R5-001, SPK-R5-001, REL-R4-001 | https://github.com/arunpr614/Life-Reflection/blob/main/docs/product/releases/PRD-R5-PROSPECTIVE-VOICENOTES-SYNC.md | https://github.com/arunpr614/Life-Reflection/blob/main/docs/work-items/ARCH-R5-001/P0-ARCH-R5-001-PRD.md | https://github.com/arunpr614/Life-Reflection/blob/main/docs/work-items/ARCH-R5-001/P0-ARCH-R5-001-TECHNICAL-PLAN.md | https://github.com/arunpr614/Life-Reflection/blob/main/docs/work-items/ARCH-R5-001/P0-ARCH-R5-001-DESIGN-SPEC.md | https://github.com/arunpr614/Life-Reflection/blob/main/docs/work-items/ARCH-R5-001/P0-ARCH-R5-001-QA-PLAN.md | https://github.com/arunpr614/Life-Reflection/blob/main/docs/work-items/ARCH-R5-001/P0-ARCH-R5-001-DELIVERY-CHECKLIST.md | https://github.com/arunpr614/Life-Reflection/blob/main/docs/work-items/ARCH-R5-001/P0-ARCH-R5-001-COUNCIL-READINESS.md | https://github.com/arunpr614/Life-Reflection/blob/main/docs/council/UX-DESIGN-REVIEW.md | https://github.com/arunpr614/Life-Reflection/blob/main/docs/architecture/PHASE1-IMPLEMENTATION-PLAN.md | Freeze the spike-proven adapter, opaque identities, authorization renewal, fail-closed paging, durable jobs, reconciliation, and restore design. | Approved task-specific technical plan for ARCH-R5-001 — VoiceNotes Adapter & Reconciliation Contract links owned modules, ADRs, threats/data flows, interfaces/data shapes, capacity, migration, restore, rollback, and Architect sign-off. | No personal-data mutation is authorized by this task; it must define or prove reversible deployment and recovery before dependent implementation. | Move to Done only when the named task evidence exists; prototype or document intent cannot prove implementation or release completion. | https://github.com/arunpr614/Life-Reflection/issues/35
ENG-R5-001 | Prospective Import & Revisions | Backlog | Incomplete | No | future-synthetic-contract-gated | R5 | Implementation | Engineering | High | 2026-11-26 | 2026-12-09 | 14 | LID-VN-001, LID-VN-002, LID-VN-003, LID-VN-004, LID-VN-005, LID-VN-006, LID-VN-007, LID-OPS-011, LID-OPS-015, LID-OPS-018 | UX-R5-001, ARCH-R5-001, REL-R4-001 | https://github.com/arunpr614/Life-Reflection/blob/main/docs/product/releases/PRD-R5-PROSPECTIVE-VOICENOTES-SYNC.md | https://github.com/arunpr614/Life-Reflection/blob/main/docs/work-items/ENG-R5-001/P0-ENG-R5-001-PRD.md | https://github.com/arunpr614/Life-Reflection/blob/main/docs/work-items/ENG-R5-001/P0-ENG-R5-001-TECHNICAL-PLAN.md | https://github.com/arunpr614/Life-Reflection/blob/main/docs/work-items/ENG-R5-001/P0-ENG-R5-001-DESIGN-SPEC.md | https://github.com/arunpr614/Life-Reflection/blob/main/docs/work-items/ENG-R5-001/P0-ENG-R5-001-QA-PLAN.md | https://github.com/arunpr614/Life-Reflection/blob/main/docs/work-items/ENG-R5-001/P0-ENG-R5-001-DELIVERY-CHECKLIST.md | https://github.com/arunpr614/Life-Reflection/blob/main/docs/work-items/ENG-R5-001/P0-ENG-R5-001-COUNCIL-READINESS.md | https://github.com/arunpr614/Life-Reflection/blob/main/docs/council/UX-DESIGN-REVIEW.md | https://github.com/arunpr614/Life-Reflection/blob/main/docs/architecture/PHASE1-IMPLEMENTATION-PLAN.md | Implement exact post-activation import, creation-time dating/review, replay-safe reconciliation, revisions, upstream status, suppression, and alerts. | Merged implementation for ENG-R5-001 — Prospective Import & Revisions proves “Implement exact post-activation import, creation-time dating/review, replay-safe reconciliation, revisions, upstream status, suppression, and alerts.” with task-specific tests, immutable build/SBOM, migrations, sanitized deployment evidence when authorized, separate-path restore, rollback, and no-regression results. | Adds VoiceNotes identity, activation, revision, reconciliation, and suppression state; migration must be reversible and backup/restore coverage must pass before release acceptance. | Move to Done only when the named task evidence exists; prototype or document intent cannot prove implementation or release completion. | https://github.com/arunpr614/Life-Reflection/issues/36
REL-R5-001 | Replay/Suppression/Restore Acceptance | Backlog | Incomplete | No | future-synthetic-contract-gated | R5 | Release acceptance | Project Manager + Independent QA | High | 2026-12-10 | 2026-12-11 | 2 | LID-VN-001, LID-VN-002, LID-VN-003, LID-VN-004, LID-VN-005, LID-VN-006, LID-VN-007, LID-OPS-011, LID-OPS-015, LID-OPS-018 | ENG-R5-001 | https://github.com/arunpr614/Life-Reflection/blob/main/docs/product/releases/PRD-R5-PROSPECTIVE-VOICENOTES-SYNC.md | https://github.com/arunpr614/Life-Reflection/blob/main/docs/work-items/REL-R5-001/P0-REL-R5-001-PRD.md | https://github.com/arunpr614/Life-Reflection/blob/main/docs/work-items/REL-R5-001/P0-REL-R5-001-TECHNICAL-PLAN.md | https://github.com/arunpr614/Life-Reflection/blob/main/docs/work-items/REL-R5-001/P0-REL-R5-001-DESIGN-SPEC.md | https://github.com/arunpr614/Life-Reflection/blob/main/docs/work-items/REL-R5-001/P0-REL-R5-001-QA-PLAN.md | https://github.com/arunpr614/Life-Reflection/blob/main/docs/work-items/REL-R5-001/P0-REL-R5-001-DELIVERY-CHECKLIST.md | https://github.com/arunpr614/Life-Reflection/blob/main/docs/work-items/REL-R5-001/P0-REL-R5-001-COUNCIL-READINESS.md | https://github.com/arunpr614/Life-Reflection/blob/main/docs/council/UX-DESIGN-REVIEW.md | https://github.com/arunpr614/Life-Reflection/blob/main/docs/architecture/PHASE1-IMPLEMENTATION-PLAN.md | Verify activation boundaries, missed/duplicate/out-of-order replay, revisions, suppression/re-import, integration failure isolation, restore, and rollback. | Release acceptance for REL-R5-001 — Replay/Suppression/Restore Acceptance links independent QA, five-seat review, every task-specific dossier, backup/separate-path restore for each new shape, rollback, defect gate, and proceed/hold/rollback record; a human attestation is included only for a named non-delegable act. | Validates rollback and restore for every persistent shape introduced by the milestone; acceptance never substitutes a successful backup upload for restore evidence. | Move to Done only when the named task evidence exists; prototype or document intent cannot prove implementation or release completion. | https://github.com/arunpr614/Life-Reflection/issues/37
EVAL-R6-001 | Text Model Evaluation | Backlog | Incomplete | No | future-evaluation-and-human-approval-gated | R6 | Evaluation | Product Manager + Technical Architect | Medium | 2026-12-14 | 2026-12-18 | 5 | LID-AIT-001, LID-AIT-002, LID-AIT-003, LID-AIT-006, LID-AIT-007, LID-OPS-017 | REL-R5-001 | https://github.com/arunpr614/Life-Reflection/blob/main/docs/product/releases/PRD-R6-GENERATED-TEXT-REFLECTION.md | https://github.com/arunpr614/Life-Reflection/blob/main/docs/work-items/EVAL-R6-001/P0-EVAL-R6-001-PRD.md | https://github.com/arunpr614/Life-Reflection/blob/main/docs/work-items/EVAL-R6-001/P0-EVAL-R6-001-TECHNICAL-PLAN.md | https://github.com/arunpr614/Life-Reflection/blob/main/docs/work-items/EVAL-R6-001/P0-EVAL-R6-001-DESIGN-SPEC.md | https://github.com/arunpr614/Life-Reflection/blob/main/docs/work-items/EVAL-R6-001/P0-EVAL-R6-001-QA-PLAN.md | https://github.com/arunpr614/Life-Reflection/blob/main/docs/work-items/EVAL-R6-001/P0-EVAL-R6-001-DELIVERY-CHECKLIST.md | https://github.com/arunpr614/Life-Reflection/blob/main/docs/work-items/EVAL-R6-001/P0-EVAL-R6-001-COUNCIL-READINESS.md | https://github.com/arunpr614/Life-Reflection/blob/main/docs/council/UX-DESIGN-REVIEW.md | https://github.com/arunpr614/Life-Reflection/blob/main/docs/architecture/PHASE1-IMPLEMENTATION-PLAN.md | Evaluate exact text provider/model snapshots against privacy, fidelity, schema, language, latency, and measured-cost hard gates. | Signed task-specific evaluation for EVAL-R6-001 — Text Model Evaluation records frozen fixtures/protocol, exact provider/model snapshots, hard-gate outcomes, measured cost/latency, privacy checks, and council decision. | Planning evidence only; no production data mutation. Any later implementation still needs its own migration, restore, and rollback proof. | Move to Done only when the named task evidence exists; prototype or document intent cannot prove implementation or release completion. | https://github.com/arunpr614/Life-Reflection/issues/38
PRD-R6-001 | Generated Text PRD | Done | Incomplete | No | planning-only-historical | R6 | Product definition | Product Manager | Medium | 2026-12-14 | 2026-12-18 | 5 | LID-AIT-001, LID-AIT-002, LID-AIT-003, LID-AIT-004, LID-AIT-005, LID-AIT-006, LID-AIT-007, LID-REF-006, LID-OPS-011, LID-OPS-017, LID-OPS-018 | PC-001 | https://github.com/arunpr614/Life-Reflection/blob/main/docs/product/releases/PRD-R6-GENERATED-TEXT-REFLECTION.md | https://github.com/arunpr614/Life-Reflection/blob/main/docs/work-items/PRD-R6-001/P0-PRD-R6-001-PRD.md | https://github.com/arunpr614/Life-Reflection/blob/main/docs/work-items/PRD-R6-001/P0-PRD-R6-001-TECHNICAL-PLAN.md | https://github.com/arunpr614/Life-Reflection/blob/main/docs/work-items/PRD-R6-001/P0-PRD-R6-001-DESIGN-SPEC.md | https://github.com/arunpr614/Life-Reflection/blob/main/docs/work-items/PRD-R6-001/P0-PRD-R6-001-QA-PLAN.md | https://github.com/arunpr614/Life-Reflection/blob/main/docs/work-items/PRD-R6-001/P0-PRD-R6-001-DELIVERY-CHECKLIST.md | https://github.com/arunpr614/Life-Reflection/blob/main/docs/work-items/PRD-R6-001/P0-PRD-R6-001-COUNCIL-READINESS.md | https://github.com/arunpr614/Life-Reflection/blob/main/docs/council/UX-DESIGN-REVIEW.md | https://github.com/arunpr614/Life-Reflection/blob/main/docs/architecture/PHASE1-IMPLEMENTATION-PLAN.md | Define evaluated optional text derivation, typed inputs, quiet/final refresh, protection, provenance, failures, and budgets. | Release document docs/product/releases/PRD-R6-GENERATED-TEXT-REFLECTION.md exists, passes link/requirement validation, and separates council-delegated evidence gates from specifically named non-delegable human acts. | Planning evidence only; no production data mutation. Any later implementation still needs its own migration, restore, and rollback proof. | This planning artifact is complete; it does not claim feature implementation, deployment, production readiness, or release acceptance. | https://github.com/arunpr614/Life-Reflection/issues/39
UX-R6-001 | Text/Provider/Budget States | Backlog | Incomplete | No | future-evaluation-and-human-approval-gated | R6 | Design | UI/UX Designer | Medium | 2026-12-16 | 2026-12-22 | 7 | LID-AIT-002, LID-AIT-003, LID-AIT-004, LID-AIT-005, LID-AIT-007, LID-REF-006, LID-OPS-017 | PRD-R6-001, EVAL-R6-001 | https://github.com/arunpr614/Life-Reflection/blob/main/docs/product/releases/PRD-R6-GENERATED-TEXT-REFLECTION.md | https://github.com/arunpr614/Life-Reflection/blob/main/docs/work-items/UX-R6-001/P0-UX-R6-001-PRD.md | https://github.com/arunpr614/Life-Reflection/blob/main/docs/work-items/UX-R6-001/P0-UX-R6-001-TECHNICAL-PLAN.md | https://github.com/arunpr614/Life-Reflection/blob/main/docs/work-items/UX-R6-001/P0-UX-R6-001-DESIGN-SPEC.md | https://github.com/arunpr614/Life-Reflection/blob/main/docs/work-items/UX-R6-001/P0-UX-R6-001-QA-PLAN.md | https://github.com/arunpr614/Life-Reflection/blob/main/docs/work-items/UX-R6-001/P0-UX-R6-001-DELIVERY-CHECKLIST.md | https://github.com/arunpr614/Life-Reflection/blob/main/docs/work-items/UX-R6-001/P0-UX-R6-001-COUNCIL-READINESS.md | https://github.com/arunpr614/Life-Reflection/blob/main/docs/council/UX-DESIGN-REVIEW.md | https://github.com/arunpr614/Life-Reflection/blob/main/docs/architecture/PHASE1-IMPLEMENTATION-PLAN.md | Design title/summary/tag/brief review, field protection, stale suggestions, provenance, provider health, budget, and failure states. | Approved task-specific design for UX-R6-001 — Text/Provider/Budget States links complete normal/empty/loading/error/interruption/destructive states, responsive behavior, accessibility annotations, prototype dispositions, and Designer sign-off. | Planning evidence only; no production data mutation. Any later implementation still needs its own migration, restore, and rollback proof. | Move to Done only when the named task evidence exists; prototype or document intent cannot prove implementation or release completion. | https://github.com/arunpr614/Life-Reflection/issues/40
ARCH-R6-001 | Text Adapter/Jobs/Budget/Provenance | Backlog | Incomplete | No | future-evaluation-and-human-approval-gated | R6 | Architecture | Technical Architect | Medium | 2026-12-16 | 2026-12-22 | 7 | LID-AIT-001, LID-AIT-002, LID-AIT-003, LID-AIT-004, LID-AIT-005, LID-AIT-006, LID-AIT-007, LID-REF-006, LID-OPS-011, LID-OPS-017, LID-OPS-018 | PRD-R6-001, EVAL-R6-001, REL-R5-001 | https://github.com/arunpr614/Life-Reflection/blob/main/docs/product/releases/PRD-R6-GENERATED-TEXT-REFLECTION.md | https://github.com/arunpr614/Life-Reflection/blob/main/docs/work-items/ARCH-R6-001/P0-ARCH-R6-001-PRD.md | https://github.com/arunpr614/Life-Reflection/blob/main/docs/work-items/ARCH-R6-001/P0-ARCH-R6-001-TECHNICAL-PLAN.md | https://github.com/arunpr614/Life-Reflection/blob/main/docs/work-items/ARCH-R6-001/P0-ARCH-R6-001-DESIGN-SPEC.md | https://github.com/arunpr614/Life-Reflection/blob/main/docs/work-items/ARCH-R6-001/P0-ARCH-R6-001-QA-PLAN.md | https://github.com/arunpr614/Life-Reflection/blob/main/docs/work-items/ARCH-R6-001/P0-ARCH-R6-001-DELIVERY-CHECKLIST.md | https://github.com/arunpr614/Life-Reflection/blob/main/docs/work-items/ARCH-R6-001/P0-ARCH-R6-001-COUNCIL-READINESS.md | https://github.com/arunpr614/Life-Reflection/blob/main/docs/council/UX-DESIGN-REVIEW.md | https://github.com/arunpr614/Life-Reflection/blob/main/docs/architecture/PHASE1-IMPLEMENTATION-PLAN.md | Define typed allowlist serialization, exact adapter configuration, source-race-safe jobs, independent protection, provenance, usage ledger, and restore. | Approved task-specific technical plan for ARCH-R6-001 — Text Adapter/Jobs/Budget/Provenance links owned modules, ADRs, threats/data flows, interfaces/data shapes, capacity, migration, restore, rollback, and Architect sign-off. | No personal-data mutation is authorized by this task; it must define or prove reversible deployment and recovery before dependent implementation. | Move to Done only when the named task evidence exists; prototype or document intent cannot prove implementation or release completion. | https://github.com/arunpr614/Life-Reflection/issues/41
ENG-R6-001 | Text Derivation & Protected Fields | Backlog | Incomplete | No | future-evaluation-and-human-approval-gated | R6 | Implementation | Engineering | Medium | 2026-12-21 | 2027-01-06 | 17 | LID-AIT-001, LID-AIT-002, LID-AIT-003, LID-AIT-004, LID-AIT-005, LID-AIT-006, LID-AIT-007, LID-REF-006, LID-OPS-011, LID-OPS-017, LID-OPS-018 | UX-R6-001, ARCH-R6-001, REL-R5-001 | https://github.com/arunpr614/Life-Reflection/blob/main/docs/product/releases/PRD-R6-GENERATED-TEXT-REFLECTION.md | https://github.com/arunpr614/Life-Reflection/blob/main/docs/work-items/ENG-R6-001/P0-ENG-R6-001-PRD.md | https://github.com/arunpr614/Life-Reflection/blob/main/docs/work-items/ENG-R6-001/P0-ENG-R6-001-TECHNICAL-PLAN.md | https://github.com/arunpr614/Life-Reflection/blob/main/docs/work-items/ENG-R6-001/P0-ENG-R6-001-DESIGN-SPEC.md | https://github.com/arunpr614/Life-Reflection/blob/main/docs/work-items/ENG-R6-001/P0-ENG-R6-001-QA-PLAN.md | https://github.com/arunpr614/Life-Reflection/blob/main/docs/work-items/ENG-R6-001/P0-ENG-R6-001-DELIVERY-CHECKLIST.md | https://github.com/arunpr614/Life-Reflection/blob/main/docs/work-items/ENG-R6-001/P0-ENG-R6-001-COUNCIL-READINESS.md | https://github.com/arunpr614/Life-Reflection/blob/main/docs/council/UX-DESIGN-REVIEW.md | https://github.com/arunpr614/Life-Reflection/blob/main/docs/architecture/PHASE1-IMPLEMENTATION-PLAN.md | Implement evaluated title/summary/tag/Visual Brief derivation, quiet/final refresh, field protection, version choice, provenance, and budget enforcement. | Merged implementation for ENG-R6-001 — Text Derivation & Protected Fields proves “Implement evaluated title/summary/tag/Visual Brief derivation, quiet/final refresh, field protection, version choice, provenance, and budget enforcement.” with task-specific tests, immutable build/SBOM, migrations, sanitized deployment evidence when authorized, separate-path restore, rollback, and no-regression results. | Adds derived-text versions, protection, provenance, job, and usage-ledger state; migration must be reversible and backup/restore coverage must pass before release acceptance. | Move to Done only when the named task evidence exists; prototype or document intent cannot prove implementation or release completion. | https://github.com/arunpr614/Life-Reflection/issues/42
REL-R6-001 | Text Privacy/Quality/Restore Acceptance | Backlog | Incomplete | No | future-evaluation-and-human-approval-gated | R6 | Release acceptance | Project Manager + Independent QA | Medium | 2027-01-07 | 2027-01-08 | 2 | LID-AIT-001, LID-AIT-002, LID-AIT-003, LID-AIT-004, LID-AIT-005, LID-AIT-006, LID-AIT-007, LID-REF-006, LID-OPS-011, LID-OPS-017, LID-OPS-018 | ENG-R6-001 | https://github.com/arunpr614/Life-Reflection/blob/main/docs/product/releases/PRD-R6-GENERATED-TEXT-REFLECTION.md | https://github.com/arunpr614/Life-Reflection/blob/main/docs/work-items/REL-R6-001/P0-REL-R6-001-PRD.md | https://github.com/arunpr614/Life-Reflection/blob/main/docs/work-items/REL-R6-001/P0-REL-R6-001-TECHNICAL-PLAN.md | https://github.com/arunpr614/Life-Reflection/blob/main/docs/work-items/REL-R6-001/P0-REL-R6-001-DESIGN-SPEC.md | https://github.com/arunpr614/Life-Reflection/blob/main/docs/work-items/REL-R6-001/P0-REL-R6-001-QA-PLAN.md | https://github.com/arunpr614/Life-Reflection/blob/main/docs/work-items/REL-R6-001/P0-REL-R6-001-DELIVERY-CHECKLIST.md | https://github.com/arunpr614/Life-Reflection/blob/main/docs/work-items/REL-R6-001/P0-REL-R6-001-COUNCIL-READINESS.md | https://github.com/arunpr614/Life-Reflection/blob/main/docs/council/UX-DESIGN-REVIEW.md | https://github.com/arunpr614/Life-Reflection/blob/main/docs/architecture/PHASE1-IMPLEMENTATION-PLAN.md | Verify hard-gate model quality, photo/caption exclusion, source races, protected fields, failures, monthly ceiling, derived restore, and rollback. | Release acceptance for REL-R6-001 — Text Privacy/Quality/Restore Acceptance links independent QA, five-seat review, every task-specific dossier, backup/separate-path restore for each new shape, rollback, defect gate, and proceed/hold/rollback record; a human attestation is included only for a named non-delegable act. | Validates rollback and restore for every persistent shape introduced by the milestone; acceptance never substitutes a successful backup upload for restore evidence. | Move to Done only when the named task evidence exists; prototype or document intent cannot prove implementation or release completion. | https://github.com/arunpr614/Life-Reflection/issues/43
EVAL-R7-001 | Artwork Model Evaluation | Backlog | Incomplete | No | future-evaluation-and-human-approval-gated | R7 | Evaluation | Product Manager + Technical Architect | Medium | 2027-01-11 | 2027-01-13 | 3 | LID-AIA-001, LID-AIA-003, LID-AIA-005, LID-AIA-006, LID-AIA-011, LID-OPS-017 | REL-R6-001 | https://github.com/arunpr614/Life-Reflection/blob/main/docs/product/releases/PRD-R7-GENERATED-ARTWORK.md | https://github.com/arunpr614/Life-Reflection/blob/main/docs/work-items/EVAL-R7-001/P0-EVAL-R7-001-PRD.md | https://github.com/arunpr614/Life-Reflection/blob/main/docs/work-items/EVAL-R7-001/P0-EVAL-R7-001-TECHNICAL-PLAN.md | https://github.com/arunpr614/Life-Reflection/blob/main/docs/work-items/EVAL-R7-001/P0-EVAL-R7-001-DESIGN-SPEC.md | https://github.com/arunpr614/Life-Reflection/blob/main/docs/work-items/EVAL-R7-001/P0-EVAL-R7-001-QA-PLAN.md | https://github.com/arunpr614/Life-Reflection/blob/main/docs/work-items/EVAL-R7-001/P0-EVAL-R7-001-DELIVERY-CHECKLIST.md | https://github.com/arunpr614/Life-Reflection/blob/main/docs/work-items/EVAL-R7-001/P0-EVAL-R7-001-COUNCIL-READINESS.md | https://github.com/arunpr614/Life-Reflection/blob/main/docs/council/UX-DESIGN-REVIEW.md | https://github.com/arunpr614/Life-Reflection/blob/main/docs/architecture/PHASE1-IMPLEMENTATION-PLAN.md | Evaluate exact artwork provider/model configurations against non-photorealism, safety, quality, latency, cost, and automatic-sweep eligibility gates. | Signed task-specific evaluation for EVAL-R7-001 — Artwork Model Evaluation records frozen fixtures/protocol, exact provider/model snapshots, hard-gate outcomes, measured cost/latency, privacy checks, and council decision. | Planning evidence only; no production data mutation. Any later implementation still needs its own migration, restore, and rollback proof. | Move to Done only when the named task evidence exists; prototype or document intent cannot prove implementation or release completion. | https://github.com/arunpr614/Life-Reflection/issues/44
PRD-R7-001 | Artwork PRD | Done | Incomplete | No | planning-only-historical | R7 | Product definition | Product Manager | Medium | 2027-01-11 | 2027-01-13 | 3 | LID-AIA-001, LID-AIA-002, LID-AIA-003, LID-AIA-004, LID-AIA-005, LID-AIA-006, LID-AIA-007, LID-AIA-008, LID-AIA-009, LID-AIA-010, LID-AIA-011, LID-REF-006, LID-OPS-011, LID-OPS-017, LID-OPS-018 | PC-001 | https://github.com/arunpr614/Life-Reflection/blob/main/docs/product/releases/PRD-R7-GENERATED-ARTWORK.md | https://github.com/arunpr614/Life-Reflection/blob/main/docs/work-items/PRD-R7-001/P0-PRD-R7-001-PRD.md | https://github.com/arunpr614/Life-Reflection/blob/main/docs/work-items/PRD-R7-001/P0-PRD-R7-001-TECHNICAL-PLAN.md | https://github.com/arunpr614/Life-Reflection/blob/main/docs/work-items/PRD-R7-001/P0-PRD-R7-001-DESIGN-SPEC.md | https://github.com/arunpr614/Life-Reflection/blob/main/docs/work-items/PRD-R7-001/P0-PRD-R7-001-QA-PLAN.md | https://github.com/arunpr614/Life-Reflection/blob/main/docs/work-items/PRD-R7-001/P0-PRD-R7-001-DELIVERY-CHECKLIST.md | https://github.com/arunpr614/Life-Reflection/blob/main/docs/work-items/PRD-R7-001/P0-PRD-R7-001-COUNCIL-READINESS.md | https://github.com/arunpr614/Life-Reflection/blob/main/docs/council/UX-DESIGN-REVIEW.md | https://github.com/arunpr614/Life-Reflection/blob/main/docs/architecture/PHASE1-IMPLEMENTATION-PLAN.md | Define evaluated Visual Brief, manual/sweep generation, safety/failure, labeling, versions, cover precedence, suppression, and configuration. | Release document docs/product/releases/PRD-R7-GENERATED-ARTWORK.md exists, passes link/requirement validation, and separates council-delegated evidence gates from specifically named non-delegable human acts. | Planning evidence only; no production data mutation. Any later implementation still needs its own migration, restore, and rollback proof. | This planning artifact is complete; it does not claim feature implementation, deployment, production readiness, or release acceptance. | https://github.com/arunpr614/Life-Reflection/issues/45
UX-R7-001 | Artwork/Version/Suppression Designs | Backlog | Incomplete | No | future-evaluation-and-human-approval-gated | R7 | Design | UI/UX Designer | Medium | 2027-01-12 | 2027-01-15 | 4 | LID-AIA-002, LID-AIA-003, LID-AIA-005, LID-AIA-006, LID-AIA-007, LID-AIA-008, LID-AIA-009, LID-AIA-010, LID-REF-006, LID-OPS-017 | PRD-R7-001, EVAL-R7-001 | https://github.com/arunpr614/Life-Reflection/blob/main/docs/product/releases/PRD-R7-GENERATED-ARTWORK.md | https://github.com/arunpr614/Life-Reflection/blob/main/docs/work-items/UX-R7-001/P0-UX-R7-001-PRD.md | https://github.com/arunpr614/Life-Reflection/blob/main/docs/work-items/UX-R7-001/P0-UX-R7-001-TECHNICAL-PLAN.md | https://github.com/arunpr614/Life-Reflection/blob/main/docs/work-items/UX-R7-001/P0-UX-R7-001-DESIGN-SPEC.md | https://github.com/arunpr614/Life-Reflection/blob/main/docs/work-items/UX-R7-001/P0-UX-R7-001-QA-PLAN.md | https://github.com/arunpr614/Life-Reflection/blob/main/docs/work-items/UX-R7-001/P0-UX-R7-001-DELIVERY-CHECKLIST.md | https://github.com/arunpr614/Life-Reflection/blob/main/docs/work-items/UX-R7-001/P0-UX-R7-001-COUNCIL-READINESS.md | https://github.com/arunpr614/Life-Reflection/blob/main/docs/council/UX-DESIGN-REVIEW.md | https://github.com/arunpr614/Life-Reflection/blob/main/docs/architecture/PHASE1-IMPLEMENTATION-PLAN.md | Design preflight, meaningful-word, safety/failure, persistent label, versions, stale, suppression, and real-photo-cover states. | Approved task-specific design for UX-R7-001 — Artwork/Version/Suppression Designs links complete normal/empty/loading/error/interruption/destructive states, responsive behavior, accessibility annotations, prototype dispositions, and Designer sign-off. | Planning evidence only; no production data mutation. Any later implementation still needs its own migration, restore, and rollback proof. | Move to Done only when the named task evidence exists; prototype or document intent cannot prove implementation or release completion. | https://github.com/arunpr614/Life-Reflection/issues/46
ARCH-R7-001 | Artwork Adapter/Sweep/Budget/Provenance | Backlog | Incomplete | No | future-evaluation-and-human-approval-gated | R7 | Architecture | Technical Architect | Medium | 2027-01-12 | 2027-01-15 | 4 | LID-AIA-001, LID-AIA-002, LID-AIA-003, LID-AIA-004, LID-AIA-005, LID-AIA-006, LID-AIA-007, LID-AIA-008, LID-AIA-009, LID-AIA-010, LID-AIA-011, LID-REF-006, LID-OPS-011, LID-OPS-017, LID-OPS-018 | PRD-R7-001, EVAL-R7-001, REL-R6-001 | https://github.com/arunpr614/Life-Reflection/blob/main/docs/product/releases/PRD-R7-GENERATED-ARTWORK.md | https://github.com/arunpr614/Life-Reflection/blob/main/docs/work-items/ARCH-R7-001/P0-ARCH-R7-001-PRD.md | https://github.com/arunpr614/Life-Reflection/blob/main/docs/work-items/ARCH-R7-001/P0-ARCH-R7-001-TECHNICAL-PLAN.md | https://github.com/arunpr614/Life-Reflection/blob/main/docs/work-items/ARCH-R7-001/P0-ARCH-R7-001-DESIGN-SPEC.md | https://github.com/arunpr614/Life-Reflection/blob/main/docs/work-items/ARCH-R7-001/P0-ARCH-R7-001-QA-PLAN.md | https://github.com/arunpr614/Life-Reflection/blob/main/docs/work-items/ARCH-R7-001/P0-ARCH-R7-001-DELIVERY-CHECKLIST.md | https://github.com/arunpr614/Life-Reflection/blob/main/docs/work-items/ARCH-R7-001/P0-ARCH-R7-001-COUNCIL-READINESS.md | https://github.com/arunpr614/Life-Reflection/blob/main/docs/council/UX-DESIGN-REVIEW.md | https://github.com/arunpr614/Life-Reflection/blob/main/docs/architecture/PHASE1-IMPLEMENTATION-PLAN.md | Define exact adapter/configuration, preflight, idempotent sweep, artifact lifecycle, provenance, budget reservation, suppression, and restore. | Approved task-specific technical plan for ARCH-R7-001 — Artwork Adapter/Sweep/Budget/Provenance links owned modules, ADRs, threats/data flows, interfaces/data shapes, capacity, migration, restore, rollback, and Architect sign-off. | No personal-data mutation is authorized by this task; it must define or prove reversible deployment and recovery before dependent implementation. | Move to Done only when the named task evidence exists; prototype or document intent cannot prove implementation or release completion. | https://github.com/arunpr614/Life-Reflection/issues/47
ENG-R7-001 | Manual & Sweep Artwork Lifecycle | Backlog | Incomplete | No | future-evaluation-and-human-approval-gated | R7 | Implementation | Engineering | Medium | 2027-01-14 | 2027-01-27 | 14 | LID-AIA-001, LID-AIA-002, LID-AIA-003, LID-AIA-004, LID-AIA-005, LID-AIA-006, LID-AIA-007, LID-AIA-008, LID-AIA-009, LID-AIA-010, LID-AIA-011, LID-REF-006, LID-OPS-011, LID-OPS-017, LID-OPS-018 | UX-R7-001, ARCH-R7-001, REL-R6-001 | https://github.com/arunpr614/Life-Reflection/blob/main/docs/product/releases/PRD-R7-GENERATED-ARTWORK.md | https://github.com/arunpr614/Life-Reflection/blob/main/docs/work-items/ENG-R7-001/P0-ENG-R7-001-PRD.md | https://github.com/arunpr614/Life-Reflection/blob/main/docs/work-items/ENG-R7-001/P0-ENG-R7-001-TECHNICAL-PLAN.md | https://github.com/arunpr614/Life-Reflection/blob/main/docs/work-items/ENG-R7-001/P0-ENG-R7-001-DESIGN-SPEC.md | https://github.com/arunpr614/Life-Reflection/blob/main/docs/work-items/ENG-R7-001/P0-ENG-R7-001-QA-PLAN.md | https://github.com/arunpr614/Life-Reflection/blob/main/docs/work-items/ENG-R7-001/P0-ENG-R7-001-DELIVERY-CHECKLIST.md | https://github.com/arunpr614/Life-Reflection/blob/main/docs/work-items/ENG-R7-001/P0-ENG-R7-001-COUNCIL-READINESS.md | https://github.com/arunpr614/Life-Reflection/blob/main/docs/council/UX-DESIGN-REVIEW.md | https://github.com/arunpr614/Life-Reflection/blob/main/docs/architecture/PHASE1-IMPLEMENTATION-PLAN.md | Implement evaluated explicit/sweep generation, versions, labeling, stale state, suppression, cover precedence, failures, and spend control. | Merged implementation for ENG-R7-001 — Manual & Sweep Artwork Lifecycle proves “Implement evaluated explicit/sweep generation, versions, labeling, stale state, suppression, cover precedence, failures, and spend control.” with task-specific tests, immutable build/SBOM, migrations, sanitized deployment evidence when authorized, separate-path restore, rollback, and no-regression results. | Adds artwork versions, job, provenance, suppression, and cover-selection state; migration must be reversible and backup/restore coverage must pass before release acceptance. | Move to Done only when the named task evidence exists; prototype or document intent cannot prove implementation or release completion. | https://github.com/arunpr614/Life-Reflection/issues/48
REL-R7-001 | Artwork Privacy/Cover/Restore Acceptance | Backlog | Incomplete | No | future-evaluation-and-human-approval-gated | R7 | Release acceptance | Project Manager + Independent QA | Medium | 2027-01-28 | 2027-01-29 | 2 | LID-AIA-001, LID-AIA-002, LID-AIA-003, LID-AIA-004, LID-AIA-005, LID-AIA-006, LID-AIA-007, LID-AIA-008, LID-AIA-009, LID-AIA-010, LID-AIA-011, LID-REF-006, LID-OPS-011, LID-OPS-017, LID-OPS-018 | ENG-R7-001 | https://github.com/arunpr614/Life-Reflection/blob/main/docs/product/releases/PRD-R7-GENERATED-ARTWORK.md | https://github.com/arunpr614/Life-Reflection/blob/main/docs/work-items/REL-R7-001/P0-REL-R7-001-PRD.md | https://github.com/arunpr614/Life-Reflection/blob/main/docs/work-items/REL-R7-001/P0-REL-R7-001-TECHNICAL-PLAN.md | https://github.com/arunpr614/Life-Reflection/blob/main/docs/work-items/REL-R7-001/P0-REL-R7-001-DESIGN-SPEC.md | https://github.com/arunpr614/Life-Reflection/blob/main/docs/work-items/REL-R7-001/P0-REL-R7-001-QA-PLAN.md | https://github.com/arunpr614/Life-Reflection/blob/main/docs/work-items/REL-R7-001/P0-REL-R7-001-DELIVERY-CHECKLIST.md | https://github.com/arunpr614/Life-Reflection/blob/main/docs/work-items/REL-R7-001/P0-REL-R7-001-COUNCIL-READINESS.md | https://github.com/arunpr614/Life-Reflection/blob/main/docs/council/UX-DESIGN-REVIEW.md | https://github.com/arunpr614/Life-Reflection/blob/main/docs/architecture/PHASE1-IMPLEMENTATION-PLAN.md | Verify privacy, evaluation gates, preflight, failures, versions, suppression, real-photo cover, budget, artifact restore, and rollback. | Release acceptance for REL-R7-001 — Artwork Privacy/Cover/Restore Acceptance links independent QA, five-seat review, every task-specific dossier, backup/separate-path restore for each new shape, rollback, defect gate, and proceed/hold/rollback record; a human attestation is included only for a named non-delegable act. | Validates rollback and restore for every persistent shape introduced by the milestone; acceptance never substitutes a successful backup upload for restore evidence. | Move to Done only when the named task evidence exists; prototype or document intent cannot prove implementation or release completion. | https://github.com/arunpr614/Life-Reflection/issues/49
PRD-R8-001 | Resilience PRD | Done | Incomplete | No | planning-only-historical | R8 | Product definition | Product Manager | High | 2027-02-01 | 2027-02-03 | 3 | LID-OPS-006, LID-OPS-011, LID-OPS-014, LID-OPS-018, LID-REF-006 | PC-001 | https://github.com/arunpr614/Life-Reflection/blob/main/docs/product/releases/PRD-R8-OPERATIONAL-SCALE-RESILIENCE.md | https://github.com/arunpr614/Life-Reflection/blob/main/docs/work-items/PRD-R8-001/P0-PRD-R8-001-PRD.md | https://github.com/arunpr614/Life-Reflection/blob/main/docs/work-items/PRD-R8-001/P0-PRD-R8-001-TECHNICAL-PLAN.md | https://github.com/arunpr614/Life-Reflection/blob/main/docs/work-items/PRD-R8-001/P0-PRD-R8-001-DESIGN-SPEC.md | https://github.com/arunpr614/Life-Reflection/blob/main/docs/work-items/PRD-R8-001/P0-PRD-R8-001-QA-PLAN.md | https://github.com/arunpr614/Life-Reflection/blob/main/docs/work-items/PRD-R8-001/P0-PRD-R8-001-DELIVERY-CHECKLIST.md | https://github.com/arunpr614/Life-Reflection/blob/main/docs/work-items/PRD-R8-001/P0-PRD-R8-001-COUNCIL-READINESS.md | https://github.com/arunpr614/Life-Reflection/blob/main/docs/council/UX-DESIGN-REVIEW.md | https://github.com/arunpr614/Life-Reflection/blob/main/docs/architecture/PHASE1-IMPLEMENTATION-PLAN.md | Define measured capacity, safe degradation, health, alerts, failure isolation, integrated recovery, and hardening outcomes. | Release document docs/product/releases/PRD-R8-OPERATIONAL-SCALE-RESILIENCE.md exists, passes link/requirement validation, and separates council-delegated evidence gates from specifically named non-delegable human acts. | Planning evidence only; no production data mutation. Any later implementation still needs its own migration, restore, and rollback proof. | This planning artifact is complete; it does not claim feature implementation, deployment, production readiness, or release acceptance. | https://github.com/arunpr614/Life-Reflection/issues/50
ARCH-R8-001 | Capacity/Health/Alert/Fault Hardening | Backlog | Incomplete | No | future-integrated-evidence-gated | R8 | Architecture | Technical Architect | High | 2027-02-01 | 2027-02-05 | 5 | LID-OPS-006, LID-OPS-011, LID-OPS-014, LID-OPS-018, LID-REF-006 | PRD-R8-001, REL-R7-001 | https://github.com/arunpr614/Life-Reflection/blob/main/docs/product/releases/PRD-R8-OPERATIONAL-SCALE-RESILIENCE.md | https://github.com/arunpr614/Life-Reflection/blob/main/docs/work-items/ARCH-R8-001/P0-ARCH-R8-001-PRD.md | https://github.com/arunpr614/Life-Reflection/blob/main/docs/work-items/ARCH-R8-001/P0-ARCH-R8-001-TECHNICAL-PLAN.md | https://github.com/arunpr614/Life-Reflection/blob/main/docs/work-items/ARCH-R8-001/P0-ARCH-R8-001-DESIGN-SPEC.md | https://github.com/arunpr614/Life-Reflection/blob/main/docs/work-items/ARCH-R8-001/P0-ARCH-R8-001-QA-PLAN.md | https://github.com/arunpr614/Life-Reflection/blob/main/docs/work-items/ARCH-R8-001/P0-ARCH-R8-001-DELIVERY-CHECKLIST.md | https://github.com/arunpr614/Life-Reflection/blob/main/docs/work-items/ARCH-R8-001/P0-ARCH-R8-001-COUNCIL-READINESS.md | https://github.com/arunpr614/Life-Reflection/blob/main/docs/council/UX-DESIGN-REVIEW.md | https://github.com/arunpr614/Life-Reflection/blob/main/docs/architecture/PHASE1-IMPLEMENTATION-PLAN.md | Harden measured watermarks, process/job supervision, durable health, alert transitions, dependency isolation, and recovery operations. | Approved task-specific technical plan for ARCH-R8-001 — Capacity/Health/Alert/Fault Hardening links owned modules, ADRs, threats/data flows, interfaces/data shapes, capacity, migration, restore, rollback, and Architect sign-off. | No personal-data mutation is authorized by this task; it must define or prove reversible deployment and recovery before dependent implementation. | Move to Done only when the named task evidence exists; prototype or document intent cannot prove implementation or release completion. | https://github.com/arunpr614/Life-Reflection/issues/51
QA-R8-001 | Integrated Fault/Security/Browser/Accessibility Suite | Backlog | Incomplete | No | future-integrated-evidence-gated | R8 | Quality | Independent QA + Project Manager | High | 2027-02-04 | 2027-02-17 | 14 | LID-SCP-001, LID-SCP-002, LID-SCP-003, LID-SCP-004, LID-TG-001, LID-TG-002, LID-TG-003, LID-TG-004, LID-TG-005, LID-TG-006, LID-TG-007, LID-TG-008, LID-TG-009, LID-TG-010, LID-VN-001, LID-VN-002, LID-VN-003, LID-VN-004, LID-VN-005, LID-VN-006, LID-VN-007, LID-UP-001, LID-UP-002, LID-UP-003, LID-SRC-001, LID-SRC-002, LID-SRC-003, LID-SRC-004, LID-REF-001, LID-REF-002, LID-REF-003, LID-REF-004, LID-REF-005, LID-REF-006, LID-REF-007, LID-AIT-001, LID-AIT-002, LID-AIT-003, LID-AIT-004, LID-AIT-005, LID-AIT-006, LID-AIT-007, LID-AIA-001, LID-AIA-002, LID-AIA-003, LID-AIA-004, LID-AIA-005, LID-AIA-006, LID-AIA-007, LID-AIA-008, LID-AIA-009, LID-AIA-010, LID-AIA-011, LID-OPS-001, LID-OPS-002, LID-OPS-003, LID-OPS-004, LID-OPS-005, LID-OPS-006, LID-OPS-007, LID-OPS-008, LID-OPS-009, LID-OPS-010, LID-OPS-011, LID-OPS-012, LID-OPS-013, LID-OPS-014, LID-OPS-015, LID-OPS-016, LID-OPS-017, LID-OPS-018 | ARCH-R8-001, REL-R7-001 | https://github.com/arunpr614/Life-Reflection/blob/main/docs/product/releases/PRD-R8-OPERATIONAL-SCALE-RESILIENCE.md | https://github.com/arunpr614/Life-Reflection/blob/main/docs/work-items/QA-R8-001/P0-QA-R8-001-PRD.md | https://github.com/arunpr614/Life-Reflection/blob/main/docs/work-items/QA-R8-001/P0-QA-R8-001-TECHNICAL-PLAN.md | https://github.com/arunpr614/Life-Reflection/blob/main/docs/work-items/QA-R8-001/P0-QA-R8-001-DESIGN-SPEC.md | https://github.com/arunpr614/Life-Reflection/blob/main/docs/work-items/QA-R8-001/P0-QA-R8-001-QA-PLAN.md | https://github.com/arunpr614/Life-Reflection/blob/main/docs/work-items/QA-R8-001/P0-QA-R8-001-DELIVERY-CHECKLIST.md | https://github.com/arunpr614/Life-Reflection/blob/main/docs/work-items/QA-R8-001/P0-QA-R8-001-COUNCIL-READINESS.md | https://github.com/arunpr614/Life-Reflection/blob/main/docs/council/UX-DESIGN-REVIEW.md | https://github.com/arunpr614/Life-Reflection/blob/main/docs/architecture/PHASE1-IMPLEMENTATION-PLAN.md | Execute integrated capacity, restart, dependency, privacy, security, browser, keyboard, screen-reader, zoom, theme, and restore tests. | Independent task-specific matrix for QA-R8-001 — Integrated Fault/Security/Browser/Accessibility Suite links executed scenarios, defects/retests, privacy/security/accessibility/browser evidence, restore/rollback results, reviewer independence, and permitted claim. | Validates rollback and restore for every persistent shape introduced by the milestone; acceptance never substitutes a successful backup upload for restore evidence. | Move to Done only when the named task evidence exists; prototype or document intent cannot prove implementation or release completion. | https://github.com/arunpr614/Life-Reflection/issues/52
REL-R8-001 | Resilience Release Acceptance | Backlog | Incomplete | No | future-integrated-evidence-gated | R8 | Release acceptance | Project Manager + Independent QA | High | 2027-02-18 | 2027-02-19 | 2 | LID-SCP-001, LID-SCP-002, LID-SCP-003, LID-SCP-004, LID-TG-001, LID-TG-002, LID-TG-003, LID-TG-004, LID-TG-005, LID-TG-006, LID-TG-007, LID-TG-008, LID-TG-009, LID-TG-010, LID-VN-001, LID-VN-002, LID-VN-003, LID-VN-004, LID-VN-005, LID-VN-006, LID-VN-007, LID-UP-001, LID-UP-002, LID-UP-003, LID-SRC-001, LID-SRC-002, LID-SRC-003, LID-SRC-004, LID-REF-001, LID-REF-002, LID-REF-003, LID-REF-004, LID-REF-005, LID-REF-006, LID-REF-007, LID-AIT-001, LID-AIT-002, LID-AIT-003, LID-AIT-004, LID-AIT-005, LID-AIT-006, LID-AIT-007, LID-AIA-001, LID-AIA-002, LID-AIA-003, LID-AIA-004, LID-AIA-005, LID-AIA-006, LID-AIA-007, LID-AIA-008, LID-AIA-009, LID-AIA-010, LID-AIA-011, LID-OPS-001, LID-OPS-002, LID-OPS-003, LID-OPS-004, LID-OPS-005, LID-OPS-006, LID-OPS-007, LID-OPS-008, LID-OPS-009, LID-OPS-010, LID-OPS-011, LID-OPS-012, LID-OPS-013, LID-OPS-014, LID-OPS-015, LID-OPS-016, LID-OPS-017, LID-OPS-018 | QA-R8-001 | https://github.com/arunpr614/Life-Reflection/blob/main/docs/product/releases/PRD-R8-OPERATIONAL-SCALE-RESILIENCE.md | https://github.com/arunpr614/Life-Reflection/blob/main/docs/work-items/REL-R8-001/P0-REL-R8-001-PRD.md | https://github.com/arunpr614/Life-Reflection/blob/main/docs/work-items/REL-R8-001/P0-REL-R8-001-TECHNICAL-PLAN.md | https://github.com/arunpr614/Life-Reflection/blob/main/docs/work-items/REL-R8-001/P0-REL-R8-001-DESIGN-SPEC.md | https://github.com/arunpr614/Life-Reflection/blob/main/docs/work-items/REL-R8-001/P0-REL-R8-001-QA-PLAN.md | https://github.com/arunpr614/Life-Reflection/blob/main/docs/work-items/REL-R8-001/P0-REL-R8-001-DELIVERY-CHECKLIST.md | https://github.com/arunpr614/Life-Reflection/blob/main/docs/work-items/REL-R8-001/P0-REL-R8-001-COUNCIL-READINESS.md | https://github.com/arunpr614/Life-Reflection/blob/main/docs/council/UX-DESIGN-REVIEW.md | https://github.com/arunpr614/Life-Reflection/blob/main/docs/architecture/PHASE1-IMPLEMENTATION-PLAN.md | Accept the integrated operating envelope only after faults, alerts, capacity, backup/restore, rollback, and regressions pass. | Release acceptance for REL-R8-001 — Resilience Release Acceptance links independent QA, five-seat review, every task-specific dossier, backup/separate-path restore for each new shape, rollback, defect gate, and proceed/hold/rollback record; a human attestation is included only for a named non-delegable act. | Validates rollback and restore for every persistent shape introduced by the milestone; acceptance never substitutes a successful backup upload for restore evidence. | Move to Done only when the named task evidence exists; prototype or document intent cannot prove implementation or release completion. | https://github.com/arunpr614/Life-Reflection/issues/53
PRD-R9-001 | Launch Acceptance Plan | Done | Incomplete | No | planning-only-historical | R9 | Product definition | Product Manager | High | 2027-02-22 | 2027-02-24 | 3 | LID-SCP-001, LID-SCP-002, LID-SCP-003, LID-SCP-004, LID-TG-001, LID-TG-002, LID-TG-003, LID-TG-004, LID-TG-005, LID-TG-006, LID-TG-007, LID-TG-008, LID-TG-009, LID-TG-010, LID-VN-001, LID-VN-002, LID-VN-003, LID-VN-004, LID-VN-005, LID-VN-006, LID-VN-007, LID-UP-001, LID-UP-002, LID-UP-003, LID-SRC-001, LID-SRC-002, LID-SRC-003, LID-SRC-004, LID-REF-001, LID-REF-002, LID-REF-003, LID-REF-004, LID-REF-005, LID-REF-006, LID-REF-007, LID-AIT-001, LID-AIT-002, LID-AIT-003, LID-AIT-004, LID-AIT-005, LID-AIT-006, LID-AIT-007, LID-AIA-001, LID-AIA-002, LID-AIA-003, LID-AIA-004, LID-AIA-005, LID-AIA-006, LID-AIA-007, LID-AIA-008, LID-AIA-009, LID-AIA-010, LID-AIA-011, LID-OPS-001, LID-OPS-002, LID-OPS-003, LID-OPS-004, LID-OPS-005, LID-OPS-006, LID-OPS-007, LID-OPS-008, LID-OPS-009, LID-OPS-010, LID-OPS-011, LID-OPS-012, LID-OPS-013, LID-OPS-014, LID-OPS-015, LID-OPS-016, LID-OPS-017, LID-OPS-018 | PC-001 | https://github.com/arunpr614/Life-Reflection/blob/main/docs/product/releases/PRD-R9-PRIVATE-LAUNCH-ACCEPTANCE.md | https://github.com/arunpr614/Life-Reflection/blob/main/docs/work-items/PRD-R9-001/P0-PRD-R9-001-PRD.md | https://github.com/arunpr614/Life-Reflection/blob/main/docs/work-items/PRD-R9-001/P0-PRD-R9-001-TECHNICAL-PLAN.md | https://github.com/arunpr614/Life-Reflection/blob/main/docs/work-items/PRD-R9-001/P0-PRD-R9-001-DESIGN-SPEC.md | https://github.com/arunpr614/Life-Reflection/blob/main/docs/work-items/PRD-R9-001/P0-PRD-R9-001-QA-PLAN.md | https://github.com/arunpr614/Life-Reflection/blob/main/docs/work-items/PRD-R9-001/P0-PRD-R9-001-DELIVERY-CHECKLIST.md | https://github.com/arunpr614/Life-Reflection/blob/main/docs/work-items/PRD-R9-001/P0-PRD-R9-001-COUNCIL-READINESS.md | https://github.com/arunpr614/Life-Reflection/blob/main/docs/council/UX-DESIGN-REVIEW.md | https://github.com/arunpr614/Life-Reflection/blob/main/docs/architecture/PHASE1-IMPLEMENTATION-PLAN.md | Define the owner UAT, Recovery Ceremony, severity gate, observation window, explicit authority, go/no-go, and rollback plan with no feature growth. | Release document docs/product/releases/PRD-R9-PRIVATE-LAUNCH-ACCEPTANCE.md exists, passes link/requirement validation, and separates council-delegated evidence gates from specifically named non-delegable human acts. | Planning evidence only; no production data mutation. Any later implementation still needs its own migration, restore, and rollback proof. | This planning artifact is complete; it does not claim feature implementation, deployment, production readiness, or release acceptance. | https://github.com/arunpr614/Life-Reflection/issues/54
QA-R9-001 | Owner UAT/Recovery Ceremony/Stabilization | Backlog | Incomplete | No | future-human-launch-gated | R9 | Quality | Independent QA + Project Manager | High | 2027-02-22 | 2027-03-10 | 17 | LID-SCP-001, LID-SCP-002, LID-SCP-003, LID-SCP-004, LID-TG-001, LID-TG-002, LID-TG-003, LID-TG-004, LID-TG-005, LID-TG-006, LID-TG-007, LID-TG-008, LID-TG-009, LID-TG-010, LID-VN-001, LID-VN-002, LID-VN-003, LID-VN-004, LID-VN-005, LID-VN-006, LID-VN-007, LID-UP-001, LID-UP-002, LID-UP-003, LID-SRC-001, LID-SRC-002, LID-SRC-003, LID-SRC-004, LID-REF-001, LID-REF-002, LID-REF-003, LID-REF-004, LID-REF-005, LID-REF-006, LID-REF-007, LID-AIT-001, LID-AIT-002, LID-AIT-003, LID-AIT-004, LID-AIT-005, LID-AIT-006, LID-AIT-007, LID-AIA-001, LID-AIA-002, LID-AIA-003, LID-AIA-004, LID-AIA-005, LID-AIA-006, LID-AIA-007, LID-AIA-008, LID-AIA-009, LID-AIA-010, LID-AIA-011, LID-OPS-001, LID-OPS-002, LID-OPS-003, LID-OPS-004, LID-OPS-005, LID-OPS-006, LID-OPS-007, LID-OPS-008, LID-OPS-009, LID-OPS-010, LID-OPS-011, LID-OPS-012, LID-OPS-013, LID-OPS-014, LID-OPS-015, LID-OPS-016, LID-OPS-017, LID-OPS-018 | PRD-R9-001, REL-R8-001 | https://github.com/arunpr614/Life-Reflection/blob/main/docs/product/releases/PRD-R9-PRIVATE-LAUNCH-ACCEPTANCE.md | https://github.com/arunpr614/Life-Reflection/blob/main/docs/work-items/QA-R9-001/P0-QA-R9-001-PRD.md | https://github.com/arunpr614/Life-Reflection/blob/main/docs/work-items/QA-R9-001/P0-QA-R9-001-TECHNICAL-PLAN.md | https://github.com/arunpr614/Life-Reflection/blob/main/docs/work-items/QA-R9-001/P0-QA-R9-001-DESIGN-SPEC.md | https://github.com/arunpr614/Life-Reflection/blob/main/docs/work-items/QA-R9-001/P0-QA-R9-001-QA-PLAN.md | https://github.com/arunpr614/Life-Reflection/blob/main/docs/work-items/QA-R9-001/P0-QA-R9-001-DELIVERY-CHECKLIST.md | https://github.com/arunpr614/Life-Reflection/blob/main/docs/work-items/QA-R9-001/P0-QA-R9-001-COUNCIL-READINESS.md | https://github.com/arunpr614/Life-Reflection/blob/main/docs/council/UX-DESIGN-REVIEW.md | https://github.com/arunpr614/Life-Reflection/blob/main/docs/architecture/PHASE1-IMPLEMENTATION-PLAN.md | Execute complete owner journeys, full representative recovery, defect stabilization, accessibility, privacy, spend, capacity, and failure scenarios. | Independent task-specific matrix for QA-R9-001 — Owner UAT/Recovery Ceremony/Stabilization links executed scenarios, defects/retests, privacy/security/accessibility/browser evidence, restore/rollback results, reviewer independence, and permitted claim. | Validates rollback and restore for every persistent shape introduced by the milestone; acceptance never substitutes a successful backup upload for restore evidence. | Move to Done only when the named task evidence exists; prototype or document intent cannot prove implementation or release completion. | https://github.com/arunpr614/Life-Reflection/issues/55
REL-R9-001 | Private Launch Go/No-go & Observation | Backlog | Incomplete | No | future-human-launch-gated | R9 | Release acceptance | Project Manager + Independent QA | High | 2027-03-11 | 2027-03-12 | 2 | LID-SCP-001, LID-SCP-002, LID-SCP-003, LID-SCP-004, LID-TG-001, LID-TG-002, LID-TG-003, LID-TG-004, LID-TG-005, LID-TG-006, LID-TG-007, LID-TG-008, LID-TG-009, LID-TG-010, LID-VN-001, LID-VN-002, LID-VN-003, LID-VN-004, LID-VN-005, LID-VN-006, LID-VN-007, LID-UP-001, LID-UP-002, LID-UP-003, LID-SRC-001, LID-SRC-002, LID-SRC-003, LID-SRC-004, LID-REF-001, LID-REF-002, LID-REF-003, LID-REF-004, LID-REF-005, LID-REF-006, LID-REF-007, LID-AIT-001, LID-AIT-002, LID-AIT-003, LID-AIT-004, LID-AIT-005, LID-AIT-006, LID-AIT-007, LID-AIA-001, LID-AIA-002, LID-AIA-003, LID-AIA-004, LID-AIA-005, LID-AIA-006, LID-AIA-007, LID-AIA-008, LID-AIA-009, LID-AIA-010, LID-AIA-011, LID-OPS-001, LID-OPS-002, LID-OPS-003, LID-OPS-004, LID-OPS-005, LID-OPS-006, LID-OPS-007, LID-OPS-008, LID-OPS-009, LID-OPS-010, LID-OPS-011, LID-OPS-012, LID-OPS-013, LID-OPS-014, LID-OPS-015, LID-OPS-016, LID-OPS-017, LID-OPS-018 | QA-R9-001 | https://github.com/arunpr614/Life-Reflection/blob/main/docs/product/releases/PRD-R9-PRIVATE-LAUNCH-ACCEPTANCE.md | https://github.com/arunpr614/Life-Reflection/blob/main/docs/work-items/REL-R9-001/P0-REL-R9-001-PRD.md | https://github.com/arunpr614/Life-Reflection/blob/main/docs/work-items/REL-R9-001/P0-REL-R9-001-TECHNICAL-PLAN.md | https://github.com/arunpr614/Life-Reflection/blob/main/docs/work-items/REL-R9-001/P0-REL-R9-001-DESIGN-SPEC.md | https://github.com/arunpr614/Life-Reflection/blob/main/docs/work-items/REL-R9-001/P0-REL-R9-001-QA-PLAN.md | https://github.com/arunpr614/Life-Reflection/blob/main/docs/work-items/REL-R9-001/P0-REL-R9-001-DELIVERY-CHECKLIST.md | https://github.com/arunpr614/Life-Reflection/blob/main/docs/work-items/REL-R9-001/P0-REL-R9-001-COUNCIL-READINESS.md | https://github.com/arunpr614/Life-Reflection/blob/main/docs/council/UX-DESIGN-REVIEW.md | https://github.com/arunpr614/Life-Reflection/blob/main/docs/architecture/PHASE1-IMPLEMENTATION-PLAN.md | Record explicit owner authority, severity status, Recovery Ceremony, observation evidence, and go/no-go or rollback decision. | Release acceptance for REL-R9-001 — Private Launch Go/No-go & Observation links independent QA, five-seat review, every task-specific dossier, backup/separate-path restore for each new shape, rollback, defect gate, and proceed/hold/rollback record; a human attestation is included only for a named non-delegable act. | Validates rollback and restore for every persistent shape introduced by the milestone; acceptance never substitutes a successful backup upload for restore evidence. | Move to Done only when the named task evidence exists; prototype or document intent cannot prove implementation or release completion. | https://github.com/arunpr614/Life-Reflection/issues/56
PID-R10-001 | Object-store Transition PID | Done | Incomplete | No | planning-only-historical | R10 | Product definition | Product Manager | Medium |  |  |  | LID-OPS-006, LID-OPS-007, LID-OPS-008, LID-OPS-011, LID-OPS-014, LID-OPS-018 | PC-001 | https://github.com/arunpr614/Life-Reflection/blob/main/docs/product/releases/PID-R10-OBJECT-STORE-TRANSITION.md | https://github.com/arunpr614/Life-Reflection/blob/main/docs/work-items/PID-R10-001/P0-PID-R10-001-PRD.md | https://github.com/arunpr614/Life-Reflection/blob/main/docs/work-items/PID-R10-001/P0-PID-R10-001-TECHNICAL-PLAN.md | https://github.com/arunpr614/Life-Reflection/blob/main/docs/work-items/PID-R10-001/P0-PID-R10-001-DESIGN-SPEC.md | https://github.com/arunpr614/Life-Reflection/blob/main/docs/work-items/PID-R10-001/P0-PID-R10-001-QA-PLAN.md | https://github.com/arunpr614/Life-Reflection/blob/main/docs/work-items/PID-R10-001/P0-PID-R10-001-DELIVERY-CHECKLIST.md | https://github.com/arunpr614/Life-Reflection/blob/main/docs/work-items/PID-R10-001/P0-PID-R10-001-COUNCIL-READINESS.md | https://github.com/arunpr614/Life-Reflection/blob/main/docs/council/UX-DESIGN-REVIEW.md | https://github.com/arunpr614/Life-Reflection/blob/main/docs/architecture/PHASE1-IMPLEMENTATION-PLAN.md | Define the date-free capacity trigger, user-visible states, outcomes, non-goals, cutover, recovery, rollback, and owner acceptance boundary. | Release document docs/product/releases/PID-R10-OBJECT-STORE-TRANSITION.md exists, passes link/requirement validation, and separates council-delegated evidence gates from specifically named non-delegable human acts. | Planning evidence only; no production data mutation. Any later implementation still needs its own migration, restore, and rollback proof. | This planning artifact is complete; it does not claim feature implementation, deployment, production readiness, or release acceptance. | https://github.com/arunpr614/Life-Reflection/issues/57
ARCH-R10-001 | Migration/Inventory/Backup/Rollback Runbook | Backlog | Incomplete | No | trigger-only-no-execution | R10 | Architecture | Technical Architect | Medium |  |  |  | LID-OPS-006, LID-OPS-007, LID-OPS-008, LID-OPS-011, LID-OPS-014, LID-OPS-018 | PID-R10-001, REL-R9-001 | https://github.com/arunpr614/Life-Reflection/blob/main/docs/product/releases/PID-R10-OBJECT-STORE-TRANSITION.md | https://github.com/arunpr614/Life-Reflection/blob/main/docs/work-items/ARCH-R10-001/P0-ARCH-R10-001-PRD.md | https://github.com/arunpr614/Life-Reflection/blob/main/docs/work-items/ARCH-R10-001/P0-ARCH-R10-001-TECHNICAL-PLAN.md | https://github.com/arunpr614/Life-Reflection/blob/main/docs/work-items/ARCH-R10-001/P0-ARCH-R10-001-DESIGN-SPEC.md | https://github.com/arunpr614/Life-Reflection/blob/main/docs/work-items/ARCH-R10-001/P0-ARCH-R10-001-QA-PLAN.md | https://github.com/arunpr614/Life-Reflection/blob/main/docs/work-items/ARCH-R10-001/P0-ARCH-R10-001-DELIVERY-CHECKLIST.md | https://github.com/arunpr614/Life-Reflection/blob/main/docs/work-items/ARCH-R10-001/P0-ARCH-R10-001-COUNCIL-READINESS.md | https://github.com/arunpr614/Life-Reflection/blob/main/docs/council/UX-DESIGN-REVIEW.md | https://github.com/arunpr614/Life-Reflection/blob/main/docs/architecture/PHASE1-IMPLEMENTATION-PLAN.md | Define complete pagination/inventory, encrypted keys, dual-write/copy, reconciliation, remote backup/restore, reversible pointers, observation, and rollback. | Approved task-specific technical plan for ARCH-R10-001 — Migration/Inventory/Backup/Rollback Runbook links owned modules, ADRs, threats/data flows, interfaces/data shapes, capacity, migration, restore, rollback, and Architect sign-off. | No personal-data mutation is authorized by this task; it must define or prove reversible deployment and recovery before dependent implementation. | Move to Done only when the named task evidence exists; prototype or document intent cannot prove implementation or release completion. | https://github.com/arunpr614/Life-Reflection/issues/58
REL-R10-001 | Conditional Transition Acceptance | Backlog | Incomplete | No | trigger-only-no-execution | R10 | Release acceptance | Project Manager + Independent QA | Medium |  |  |  | LID-OPS-006, LID-OPS-007, LID-OPS-008, LID-OPS-011, LID-OPS-014, LID-OPS-018 | ARCH-R10-001 | https://github.com/arunpr614/Life-Reflection/blob/main/docs/product/releases/PID-R10-OBJECT-STORE-TRANSITION.md | https://github.com/arunpr614/Life-Reflection/blob/main/docs/work-items/REL-R10-001/P0-REL-R10-001-PRD.md | https://github.com/arunpr614/Life-Reflection/blob/main/docs/work-items/REL-R10-001/P0-REL-R10-001-TECHNICAL-PLAN.md | https://github.com/arunpr614/Life-Reflection/blob/main/docs/work-items/REL-R10-001/P0-REL-R10-001-DESIGN-SPEC.md | https://github.com/arunpr614/Life-Reflection/blob/main/docs/work-items/REL-R10-001/P0-REL-R10-001-QA-PLAN.md | https://github.com/arunpr614/Life-Reflection/blob/main/docs/work-items/REL-R10-001/P0-REL-R10-001-DELIVERY-CHECKLIST.md | https://github.com/arunpr614/Life-Reflection/blob/main/docs/work-items/REL-R10-001/P0-REL-R10-001-COUNCIL-READINESS.md | https://github.com/arunpr614/Life-Reflection/blob/main/docs/council/UX-DESIGN-REVIEW.md | https://github.com/arunpr614/Life-Reflection/blob/main/docs/architecture/PHASE1-IMPLEMENTATION-PLAN.md | After an approved trigger, execute and verify reversible object-store transition before retiring any local authoritative copy. | Release acceptance for REL-R10-001 — Conditional Transition Acceptance links independent QA, five-seat review, every task-specific dossier, backup/separate-path restore for each new shape, rollback, defect gate, and proceed/hold/rollback record; a human attestation is included only for a named non-delegable act. | Validates rollback and restore for every persistent shape introduced by the milestone; acceptance never substitutes a successful backup upload for restore evidence. | Move to Done only when the named task evidence exists; prototype or document intent cannot prove implementation or release completion. | https://github.com/arunpr614/Life-Reflection/issues/59

## Roadmap Timeline
Task Roadmap Timeline — Weekly Planning View | Task Roadmap Timeline — Weekly Planning View | Task Roadmap Timeline — Weekly Planning View | Task Roadmap Timeline — Weekly Planning View | Task Roadmap Timeline — Weekly Planning View | Task Roadmap Timeline — Weekly Planning View | Task Roadmap Timeline — Weekly Planning View | Task Roadmap Timeline — Weekly Planning View | Task Roadmap Timeline — Weekly Planning View | Task Roadmap Timeline — Weekly Planning View | Task Roadmap Timeline — Weekly Planning View | Task Roadmap Timeline — Weekly Planning View | Task Roadmap Timeline — Weekly Planning View | Task Roadmap Timeline — Weekly Planning View | Task Roadmap Timeline — Weekly Planning View | Task Roadmap Timeline — Weekly Planning View | Task Roadmap Timeline — Weekly Planning View | Task Roadmap Timeline — Weekly Planning View | Task Roadmap Timeline — Weekly Planning View | Task Roadmap Timeline — Weekly Planning View | Task Roadmap Timeline — Weekly Planning View | Task Roadmap Timeline — Weekly Planning View | Task Roadmap Timeline — Weekly Planning View | Task Roadmap Timeline — Weekly Planning View | Task Roadmap Timeline — Weekly Planning View | Task Roadmap Timeline — Weekly Planning View | Task Roadmap Timeline — Weekly Planning View | Task Roadmap Timeline — Weekly Planning View | Task Roadmap Timeline — Weekly Planning View | Task Roadmap Timeline — Weekly Planning View | Task Roadmap Timeline — Weekly Planning View | Task Roadmap Timeline — Weekly Planning View | Task Roadmap Timeline — Weekly Planning View | Task Roadmap Timeline — Weekly Planning View | Task Roadmap Timeline — Weekly Planning View | Task Roadmap Timeline — Weekly Planning View | Task Roadmap Timeline — Weekly Planning View | Task Roadmap Timeline — Weekly Planning View | Task Roadmap Timeline — Weekly Planning View
Task Roadmap Timeline — Weekly Planning View | Task Roadmap Timeline — Weekly Planning View | Task Roadmap Timeline — Weekly Planning View | Task Roadmap Timeline — Weekly Planning View | Task Roadmap Timeline — Weekly Planning View | Task Roadmap Timeline — Weekly Planning View | Task Roadmap Timeline — Weekly Planning View | Task Roadmap Timeline — Weekly Planning View | Task Roadmap Timeline — Weekly Planning View | Task Roadmap Timeline — Weekly Planning View | Task Roadmap Timeline — Weekly Planning View | Task Roadmap Timeline — Weekly Planning View | Task Roadmap Timeline — Weekly Planning View | Task Roadmap Timeline — Weekly Planning View | Task Roadmap Timeline — Weekly Planning View | Task Roadmap Timeline — Weekly Planning View | Task Roadmap Timeline — Weekly Planning View | Task Roadmap Timeline — Weekly Planning View | Task Roadmap Timeline — Weekly Planning View | Task Roadmap Timeline — Weekly Planning View | Task Roadmap Timeline — Weekly Planning View | Task Roadmap Timeline — Weekly Planning View | Task Roadmap Timeline — Weekly Planning View | Task Roadmap Timeline — Weekly Planning View | Task Roadmap Timeline — Weekly Planning View | Task Roadmap Timeline — Weekly Planning View | Task Roadmap Timeline — Weekly Planning View | Task Roadmap Timeline — Weekly Planning View | Task Roadmap Timeline — Weekly Planning View | Task Roadmap Timeline — Weekly Planning View | Task Roadmap Timeline — Weekly Planning View | Task Roadmap Timeline — Weekly Planning View | Task Roadmap Timeline — Weekly Planning View | Task Roadmap Timeline — Weekly Planning View | Task Roadmap Timeline — Weekly Planning View | Task Roadmap Timeline — Weekly Planning View | Task Roadmap Timeline — Weekly Planning View | Task Roadmap Timeline — Weekly Planning View | Task Roadmap Timeline — Weekly Planning View
Bars show proposed task windows only; Readiness and Allowed are independent start gates. Blank R10 rows are intentional. Status colors: gray Backlog, blue Next, amber In progress, green Done. | Bars show proposed task windows only; Readiness and Allowed are independent start gates. Blank R10 rows are intentional. Status colors: gray Backlog, blue Next, amber In progress, green Done. | Bars show proposed task windows only; Readiness and Allowed are independent start gates. Blank R10 rows are intentional. Status colors: gray Backlog, blue Next, amber In progress, green Done. | Bars show proposed task windows only; Readiness and Allowed are independent start gates. Blank R10 rows are intentional. Status colors: gray Backlog, blue Next, amber In progress, green Done. | Bars show proposed task windows only; Readiness and Allowed are independent start gates. Blank R10 rows are intentional. Status colors: gray Backlog, blue Next, amber In progress, green Done. | Bars show proposed task windows only; Readiness and Allowed are independent start gates. Blank R10 rows are intentional. Status colors: gray Backlog, blue Next, amber In progress, green Done. | Bars show proposed task windows only; Readiness and Allowed are independent start gates. Blank R10 rows are intentional. Status colors: gray Backlog, blue Next, amber In progress, green Done. | Bars show proposed task windows only; Readiness and Allowed are independent start gates. Blank R10 rows are intentional. Status colors: gray Backlog, blue Next, amber In progress, green Done. | Bars show proposed task windows only; Readiness and Allowed are independent start gates. Blank R10 rows are intentional. Status colors: gray Backlog, blue Next, amber In progress, green Done. | Bars show proposed task windows only; Readiness and Allowed are independent start gates. Blank R10 rows are intentional. Status colors: gray Backlog, blue Next, amber In progress, green Done. | Bars show proposed task windows only; Readiness and Allowed are independent start gates. Blank R10 rows are intentional. Status colors: gray Backlog, blue Next, amber In progress, green Done. | Bars show proposed task windows only; Readiness and Allowed are independent start gates. Blank R10 rows are intentional. Status colors: gray Backlog, blue Next, amber In progress, green Done. | Bars show proposed task windows only; Readiness and Allowed are independent start gates. Blank R10 rows are intentional. Status colors: gray Backlog, blue Next, amber In progress, green Done. | Bars show proposed task windows only; Readiness and Allowed are independent start gates. Blank R10 rows are intentional. Status colors: gray Backlog, blue Next, amber In progress, green Done. | Bars show proposed task windows only; Readiness and Allowed are independent start gates. Blank R10 rows are intentional. Status colors: gray Backlog, blue Next, amber In progress, green Done. | Bars show proposed task windows only; Readiness and Allowed are independent start gates. Blank R10 rows are intentional. Status colors: gray Backlog, blue Next, amber In progress, green Done. | Bars show proposed task windows only; Readiness and Allowed are independent start gates. Blank R10 rows are intentional. Status colors: gray Backlog, blue Next, amber In progress, green Done. | Bars show proposed task windows only; Readiness and Allowed are independent start gates. Blank R10 rows are intentional. Status colors: gray Backlog, blue Next, amber In progress, green Done. | Bars show proposed task windows only; Readiness and Allowed are independent start gates. Blank R10 rows are intentional. Status colors: gray Backlog, blue Next, amber In progress, green Done. | Bars show proposed task windows only; Readiness and Allowed are independent start gates. Blank R10 rows are intentional. Status colors: gray Backlog, blue Next, amber In progress, green Done. | Bars show proposed task windows only; Readiness and Allowed are independent start gates. Blank R10 rows are intentional. Status colors: gray Backlog, blue Next, amber In progress, green Done. | Bars show proposed task windows only; Readiness and Allowed are independent start gates. Blank R10 rows are intentional. Status colors: gray Backlog, blue Next, amber In progress, green Done. | Bars show proposed task windows only; Readiness and Allowed are independent start gates. Blank R10 rows are intentional. Status colors: gray Backlog, blue Next, amber In progress, green Done. | Bars show proposed task windows only; Readiness and Allowed are independent start gates. Blank R10 rows are intentional. Status colors: gray Backlog, blue Next, amber In progress, green Done. | Bars show proposed task windows only; Readiness and Allowed are independent start gates. Blank R10 rows are intentional. Status colors: gray Backlog, blue Next, amber In progress, green Done. | Bars show proposed task windows only; Readiness and Allowed are independent start gates. Blank R10 rows are intentional. Status colors: gray Backlog, blue Next, amber In progress, green Done. | Bars show proposed task windows only; Readiness and Allowed are independent start gates. Blank R10 rows are intentional. Status colors: gray Backlog, blue Next, amber In progress, green Done. | Bars show proposed task windows only; Readiness and Allowed are independent start gates. Blank R10 rows are intentional. Status colors: gray Backlog, blue Next, amber In progress, green Done. | Bars show proposed task windows only; Readiness and Allowed are independent start gates. Blank R10 rows are intentional. Status colors: gray Backlog, blue Next, amber In progress, green Done. | Bars show proposed task windows only; Readiness and Allowed are independent start gates. Blank R10 rows are intentional. Status colors: gray Backlog, blue Next, amber In progress, green Done. | Bars show proposed task windows only; Readiness and Allowed are independent start gates. Blank R10 rows are intentional. Status colors: gray Backlog, blue Next, amber In progress, green Done. | Bars show proposed task windows only; Readiness and Allowed are independent start gates. Blank R10 rows are intentional. Status colors: gray Backlog, blue Next, amber In progress, green Done. | Bars show proposed task windows only; Readiness and Allowed are independent start gates. Blank R10 rows are intentional. Status colors: gray Backlog, blue Next, amber In progress, green Done. | Bars show proposed task windows only; Readiness and Allowed are independent start gates. Blank R10 rows are intentional. Status colors: gray Backlog, blue Next, amber In progress, green Done. | Bars show proposed task windows only; Readiness and Allowed are independent start gates. Blank R10 rows are intentional. Status colors: gray Backlog, blue Next, amber In progress, green Done. | Bars show proposed task windows only; Readiness and Allowed are independent start gates. Blank R10 rows are intentional. Status colors: gray Backlog, blue Next, amber In progress, green Done. | Bars show proposed task windows only; Readiness and Allowed are independent start gates. Blank R10 rows are intentional. Status colors: gray Backlog, blue Next, amber In progress, green Done. | Bars show proposed task windows only; Readiness and Allowed are independent start gates. Blank R10 rows are intentional. Status colors: gray Backlog, blue Next, amber In progress, green Done. | Bars show proposed task windows only; Readiness and Allowed are independent start gates. Blank R10 rows are intentional. Status colors: gray Backlog, blue Next, amber In progress, green Done.
ID | Title | Status | Readiness | Allowed | Milestone | Start | Target | 2026-08-17 | 2026-08-24 | 2026-08-31 | 2026-09-07 | 2026-09-14 | 2026-09-21 | 2026-09-28 | 2026-10-05 | 2026-10-12 | 2026-10-19 | 2026-10-26 | 2026-11-02 | 2026-11-09 | 2026-11-16 | 2026-11-23 | 2026-11-30 | 2026-12-07 | 2026-12-14 | 2026-12-21 | 2026-12-28 | 2027-01-04 | 2027-01-11 | 2027-01-18 | 2027-01-25 | 2027-02-01 | 2027-02-08 | 2027-02-15 | 2027-02-22 | 2027-03-01 | 2027-03-08 | 2027-03-15
AUD-001 | v5 Feature Audit | Done | Incomplete | No | P0 | 2026-08-14 | 2026-08-14
PC-001 | Integrated Council Planning Package | Done | Incomplete | No | P0 | 2026-08-14 | 2026-08-16
SPK-R0-001 | Shared-host Coexistence & Rollback Spike | In progress | Incomplete | No | R0 | 2026-08-17 | 2026-08-19 | bar: 2026-08-17
PRD-R0-001 | Private Foundation PRD | Done | Incomplete | No | R0 | 2026-08-17 | 2026-08-20 | bar: 2026-08-17
UX-R0-001 | First-use/Access/Health States | Next | Incomplete | No | R0 | 2026-08-18 | 2026-08-21 | bar: 2026-08-17
ARCH-R0-001 | Private Shell Architecture & Threat Baseline | Next | Incomplete | No | R0 | 2026-08-17 | 2026-08-21 | bar: 2026-08-17
ENG-R0-001 | Deploy Synthetic Private Shell | Next | Incomplete | No | R0 | 2026-08-21 | 2026-08-26 | bar: 2026-08-17 to 2026-08-24
REL-R0-001 | Restore/Rollback/Non-regression Acceptance | Next | Incomplete | No | R0 | 2026-08-27 | 2026-08-28 | bar: 2026-08-24
PRD-R1-001 | Manual Archive PRD | Done | Incomplete | No | R1 | 2026-08-31 | 2026-09-02 | bar: 2026-08-31
UX-R1-001 | Calendar/Day/Upload Designs | Backlog | Incomplete | No | R1 | 2026-08-31 | 2026-09-04 | bar: 2026-08-31
ARCH-R1-001 | Journal/Source/Encryption Schema | Backlog | Incomplete | No | R1 | 2026-08-31 | 2026-09-04 | bar: 2026-08-31
ENG-R1-001 | Manual Upload & Reflection Core | Backlog | Incomplete | No | R1 | 2026-09-03 | 2026-09-15 | bar: 2026-08-31 to 2026-09-14
REL-R1-001 | First-memory Restore/Rollback Acceptance | Backlog | Incomplete | No | R1 | 2026-09-16 | 2026-09-18 | bar: 2026-09-14
PRD-R2-001 | Telegram Capture PRD | Done | Incomplete | No | R2 | 2026-09-21 | 2026-09-23 | bar: 2026-09-21
UX-R2-001 | Telegram/Date Review/Gallery Designs | Backlog | Incomplete | No | R2 | 2026-09-21 | 2026-09-25 | bar: 2026-09-21
ARCH-R2-001 | Media Pipeline & Asset Lifecycle | Backlog | Incomplete | No | R2 | 2026-09-21 | 2026-09-25 | bar: 2026-09-21
ENG-R2-001 | Telegram Authorization & Durable Capture | Backlog | Incomplete | No | R2 | 2026-09-24 | 2026-10-02 | bar: 2026-09-21 to 2026-09-28
ENG-R2-002 | Gallery/Cover/Dedup/Derivatives | Backlog | Incomplete | No | R2 | 2026-09-28 | 2026-10-06 | bar: 2026-09-28 to 2026-10-05
REL-R2-001 | Media Privacy/Restore Acceptance | Backlog | Incomplete | No | R2 | 2026-10-07 | 2026-10-09 | bar: 2026-10-05
PRD-R3-001 | Retrieval & Date Integrity PRD | Done | Incomplete | No | R3 | 2026-10-12 | 2026-10-14 | bar: 2026-10-12
UX-R3-001 | Almanac/Search/Date Review Designs | Backlog | Incomplete | No | R3 | 2026-10-12 | 2026-10-16 | bar: 2026-10-12
ARCH-R3-001 | Search Index & Redating Transaction | Backlog | Incomplete | No | R3 | 2026-10-12 | 2026-10-16 | bar: 2026-10-12
ENG-R3-001 | Almanac/Search/Date Review/Redating | Backlog | Incomplete | No | R3 | 2026-10-15 | 2026-10-28 | bar: 2026-10-12 to 2026-10-26
REL-R3-001 | Query Privacy & Date Atomicity Acceptance | Backlog | Incomplete | No | R3 | 2026-10-29 | 2026-10-30 | bar: 2026-10-26
PRD-R4-001 | Lifecycle PRD | Done | Incomplete | No | R4 | 2026-11-02 | 2026-11-04 | bar: 2026-11-02
UX-R4-001 | Diff/History/Trash/Export Designs | Backlog | Incomplete | No | R4 | 2026-11-02 | 2026-11-06 | bar: 2026-11-02
ARCH-R4-001 | Revision/Suppression/Export Lifecycle | Backlog | Incomplete | No | R4 | 2026-11-02 | 2026-11-06 | bar: 2026-11-02
ENG-R4-001 | Corrections/Conflict/History | Backlog | Incomplete | No | R4 | 2026-11-05 | 2026-11-13 | bar: 2026-11-02 to 2026-11-09
ENG-R4-002 | Trash/Suppressions/Export | Backlog | Incomplete | No | R4 | 2026-11-09 | 2026-11-18 | bar: 2026-11-09 to 2026-11-16
REL-R4-001 | Lifecycle/Export Restore Acceptance | Backlog | Incomplete | No | R4 | 2026-11-19 | 2026-11-20 | bar: 2026-11-16
SPK-R5-001 | VoiceNotes Synthetic Contract Spike | Backlog | Incomplete | No | R5 | 2026-11-23 | 2026-11-25 | bar: 2026-11-23
PRD-R5-001 | VoiceNotes PRD | Done | Incomplete | No | R5 | 2026-11-23 | 2026-11-27 | bar: 2026-11-23
UX-R5-001 | Integration/Reconciliation/Lifecycle Designs | Backlog | Incomplete | No | R5 | 2026-11-24 | 2026-11-27 | bar: 2026-11-23
ARCH-R5-001 | VoiceNotes Adapter & Reconciliation Contract | Backlog | Incomplete | No | R5 | 2026-11-24 | 2026-11-27 | bar: 2026-11-23
ENG-R5-001 | Prospective Import & Revisions | Backlog | Incomplete | No | R5 | 2026-11-26 | 2026-12-09 | bar: 2026-11-23 to 2026-12-07
REL-R5-001 | Replay/Suppression/Restore Acceptance | Backlog | Incomplete | No | R5 | 2026-12-10 | 2026-12-11 | bar: 2026-12-07
EVAL-R6-001 | Text Model Evaluation | Backlog | Incomplete | No | R6 | 2026-12-14 | 2026-12-18 | bar: 2026-12-14
PRD-R6-001 | Generated Text PRD | Done | Incomplete | No | R6 | 2026-12-14 | 2026-12-18 | bar: 2026-12-14
UX-R6-001 | Text/Provider/Budget States | Backlog | Incomplete | No | R6 | 2026-12-16 | 2026-12-22 | bar: 2026-12-14 to 2026-12-21
ARCH-R6-001 | Text Adapter/Jobs/Budget/Provenance | Backlog | Incomplete | No | R6 | 2026-12-16 | 2026-12-22 | bar: 2026-12-14 to 2026-12-21
ENG-R6-001 | Text Derivation & Protected Fields | Backlog | Incomplete | No | R6 | 2026-12-21 | 2027-01-06 | bar: 2026-12-21 to 2027-01-04
REL-R6-001 | Text Privacy/Quality/Restore Acceptance | Backlog | Incomplete | No | R6 | 2027-01-07 | 2027-01-08 | bar: 2027-01-04
EVAL-R7-001 | Artwork Model Evaluation | Backlog | Incomplete | No | R7 | 2027-01-11 | 2027-01-13 | bar: 2027-01-11
PRD-R7-001 | Artwork PRD | Done | Incomplete | No | R7 | 2027-01-11 | 2027-01-13 | bar: 2027-01-11
UX-R7-001 | Artwork/Version/Suppression Designs | Backlog | Incomplete | No | R7 | 2027-01-12 | 2027-01-15 | bar: 2027-01-11
ARCH-R7-001 | Artwork Adapter/Sweep/Budget/Provenance | Backlog | Incomplete | No | R7 | 2027-01-12 | 2027-01-15 | bar: 2027-01-11
ENG-R7-001 | Manual & Sweep Artwork Lifecycle | Backlog | Incomplete | No | R7 | 2027-01-14 | 2027-01-27 | bar: 2027-01-11 to 2027-01-25
REL-R7-001 | Artwork Privacy/Cover/Restore Acceptance | Backlog | Incomplete | No | R7 | 2027-01-28 | 2027-01-29 | bar: 2027-01-25
PRD-R8-001 | Resilience PRD | Done | Incomplete | No | R8 | 2027-02-01 | 2027-02-03 | bar: 2027-02-01
ARCH-R8-001 | Capacity/Health/Alert/Fault Hardening | Backlog | Incomplete | No | R8 | 2027-02-01 | 2027-02-05 | bar: 2027-02-01
QA-R8-001 | Integrated Fault/Security/Browser/Accessibility Suite | Backlog | Incomplete | No | R8 | 2027-02-04 | 2027-02-17 | bar: 2027-02-01 to 2027-02-15
REL-R8-001 | Resilience Release Acceptance | Backlog | Incomplete | No | R8 | 2027-02-18 | 2027-02-19 | bar: 2027-02-15
PRD-R9-001 | Launch Acceptance Plan | Done | Incomplete | No | R9 | 2027-02-22 | 2027-02-24 | bar: 2027-02-22
QA-R9-001 | Owner UAT/Recovery Ceremony/Stabilization | Backlog | Incomplete | No | R9 | 2027-02-22 | 2027-03-10 | bar: 2027-02-22 to 2027-03-08
REL-R9-001 | Private Launch Go/No-go & Observation | Backlog | Incomplete | No | R9 | 2027-03-11 | 2027-03-12 | bar: 2027-03-08
PID-R10-001 | Object-store Transition PID | Done | Incomplete | No | R10
ARCH-R10-001 | Migration/Inventory/Backup/Rollback Runbook | Backlog | Incomplete | No | R10
REL-R10-001 | Conditional Transition Acceptance | Backlog | Incomplete | No | R10

## Requirement Map
Requirement Traceability — 78 Stable IDs | Requirement Traceability — 78 Stable IDs | Requirement Traceability — 78 Stable IDs | Requirement Traceability — 78 Stable IDs | Requirement Traceability — 78 Stable IDs | Requirement Traceability — 78 Stable IDs
Requirement Traceability — 78 Stable IDs | Requirement Traceability — 78 Stable IDs | Requirement Traceability — 78 Stable IDs | Requirement Traceability — 78 Stable IDs | Requirement Traceability — 78 Stable IDs | Requirement Traceability — 78 Stable IDs
All 71 active requirements map to roadmap tasks. LID-UP-004 and LID-DEF-001 through LID-DEF-006 are explicitly deferred rather than silently omitted. | All 71 active requirements map to roadmap tasks. LID-UP-004 and LID-DEF-001 through LID-DEF-006 are explicitly deferred rather than silently omitted. | All 71 active requirements map to roadmap tasks. LID-UP-004 and LID-DEF-001 through LID-DEF-006 are explicitly deferred rather than silently omitted. | All 71 active requirements map to roadmap tasks. LID-UP-004 and LID-DEF-001 through LID-DEF-006 are explicitly deferred rather than silently omitted. | All 71 active requirements map to roadmap tasks. LID-UP-004 and LID-DEF-001 through LID-DEF-006 are explicitly deferred rather than silently omitted. | All 71 active requirements map to roadmap tasks. LID-UP-004 and LID-DEF-001 through LID-DEF-006 are explicitly deferred rather than silently omitted.
Requirement ID | Primary milestone | Roadmap task IDs | Disposition | Rationale | Task count
LID-SCP-001 | R0 | SPK-R0-001, PRD-R0-001, UX-R0-001, ARCH-R0-001, ENG-R0-001, REL-R0-001, QA-R8-001, REL-R8-001, PRD-R9-001, QA-R9-001, REL-R9-001 | Planned and regression-gated. | Mapped to one or more release-planning, implementation, or acceptance tasks. | 11
LID-SCP-002 | R1 | PRD-R1-001, UX-R1-001, ARCH-R1-001, ENG-R1-001, REL-R1-001, QA-R8-001, REL-R8-001, PRD-R9-001, QA-R9-001, REL-R9-001 | Planned and regression-gated. | Mapped to one or more release-planning, implementation, or acceptance tasks. | 10
LID-SCP-003 | R1 | PRD-R1-001, UX-R1-001, ARCH-R1-001, ENG-R1-001, REL-R1-001, QA-R8-001, REL-R8-001, PRD-R9-001, QA-R9-001, REL-R9-001 | Planned and regression-gated. | Mapped to one or more release-planning, implementation, or acceptance tasks. | 10
LID-SCP-004 | R4 | PRD-R4-001, UX-R4-001, ARCH-R4-001, ENG-R4-001, ENG-R4-002, REL-R4-001, QA-R8-001, REL-R8-001, PRD-R9-001, QA-R9-001, REL-R9-001 | Planned and regression-gated. | Mapped to one or more release-planning, implementation, or acceptance tasks. | 11
LID-TG-001 | R2 | PRD-R2-001, ARCH-R2-001, ENG-R2-001, REL-R2-001, QA-R8-001, REL-R8-001, PRD-R9-001, QA-R9-001, REL-R9-001 | Planned and regression-gated. | Mapped to one or more release-planning, implementation, or acceptance tasks. | 9
LID-TG-002 | R2 | PRD-R2-001, UX-R2-001, ARCH-R2-001, ENG-R2-001, REL-R2-001, QA-R8-001, REL-R8-001, PRD-R9-001, QA-R9-001, REL-R9-001 | Planned and regression-gated. | Mapped to one or more release-planning, implementation, or acceptance tasks. | 10
LID-TG-003 | R2 | PRD-R2-001, UX-R2-001, ARCH-R2-001, ENG-R2-001, REL-R2-001, QA-R8-001, REL-R8-001, PRD-R9-001, QA-R9-001, REL-R9-001 | Planned and regression-gated. | Mapped to one or more release-planning, implementation, or acceptance tasks. | 10
LID-TG-004 | R2 | PRD-R2-001, UX-R2-001, ARCH-R2-001, ENG-R2-001, REL-R2-001, QA-R8-001, REL-R8-001, PRD-R9-001, QA-R9-001, REL-R9-001 | Planned and regression-gated. | Mapped to one or more release-planning, implementation, or acceptance tasks. | 10
LID-TG-005 | R2 | PRD-R2-001, UX-R2-001, ARCH-R2-001, ENG-R2-001, REL-R2-001, QA-R8-001, REL-R8-001, PRD-R9-001, QA-R9-001, REL-R9-001 | Planned and regression-gated. | Mapped to one or more release-planning, implementation, or acceptance tasks. | 10
LID-TG-006 | R2 | PRD-R2-001, UX-R2-001, ARCH-R2-001, ENG-R2-001, REL-R2-001, QA-R8-001, REL-R8-001, PRD-R9-001, QA-R9-001, REL-R9-001 | Planned and regression-gated. | Mapped to one or more release-planning, implementation, or acceptance tasks. | 10
LID-TG-007 | R2 | PRD-R2-001, UX-R2-001, ARCH-R2-001, ENG-R2-002, REL-R2-001, QA-R8-001, REL-R8-001, PRD-R9-001, QA-R9-001, REL-R9-001 | Planned and regression-gated. | Mapped to one or more release-planning, implementation, or acceptance tasks. | 10
LID-TG-008 | R2 | PRD-R2-001, UX-R2-001, ARCH-R2-001, ENG-R2-002, REL-R2-001, QA-R8-001, REL-R8-001, PRD-R9-001, QA-R9-001, REL-R9-001 | Planned and regression-gated. | Mapped to one or more release-planning, implementation, or acceptance tasks. | 10
LID-TG-009 | R2 | PRD-R2-001, UX-R2-001, ARCH-R2-001, ENG-R2-002, REL-R2-001, QA-R8-001, REL-R8-001, PRD-R9-001, QA-R9-001, REL-R9-001 | Planned and regression-gated. | Mapped to one or more release-planning, implementation, or acceptance tasks. | 10
LID-TG-010 | R2 | PRD-R2-001, ARCH-R2-001, ENG-R2-002, REL-R2-001, QA-R8-001, REL-R8-001, PRD-R9-001, QA-R9-001, REL-R9-001 | Planned and regression-gated. | Mapped to one or more release-planning, implementation, or acceptance tasks. | 9
LID-VN-001 | R5 | SPK-R5-001, PRD-R5-001, ARCH-R5-001, ENG-R5-001, REL-R5-001, QA-R8-001, REL-R8-001, PRD-R9-001, QA-R9-001, REL-R9-001 | Planned and regression-gated. | Mapped to one or more release-planning, implementation, or acceptance tasks. | 10
LID-VN-002 | R5 | SPK-R5-001, PRD-R5-001, UX-R5-001, ARCH-R5-001, ENG-R5-001, REL-R5-001, QA-R8-001, REL-R8-001, PRD-R9-001, QA-R9-001, REL-R9-001 | Planned and regression-gated. | Mapped to one or more release-planning, implementation, or acceptance tasks. | 11
LID-VN-003 | R5 | SPK-R5-001, PRD-R5-001, UX-R5-001, ARCH-R5-001, ENG-R5-001, REL-R5-001, QA-R8-001, REL-R8-001, PRD-R9-001, QA-R9-001, REL-R9-001 | Planned and regression-gated. | Mapped to one or more release-planning, implementation, or acceptance tasks. | 11
LID-VN-004 | R5 | SPK-R5-001, PRD-R5-001, UX-R5-001, ARCH-R5-001, ENG-R5-001, REL-R5-001, QA-R8-001, REL-R8-001, PRD-R9-001, QA-R9-001, REL-R9-001 | Planned and regression-gated. | Mapped to one or more release-planning, implementation, or acceptance tasks. | 11
LID-VN-005 | R5 | SPK-R5-001, PRD-R5-001, UX-R5-001, ARCH-R5-001, ENG-R5-001, REL-R5-001, QA-R8-001, REL-R8-001, PRD-R9-001, QA-R9-001, REL-R9-001 | Planned and regression-gated. | Mapped to one or more release-planning, implementation, or acceptance tasks. | 11
LID-VN-006 | R5 | PRD-R5-001, UX-R5-001, ARCH-R5-001, ENG-R5-001, REL-R5-001, QA-R8-001, REL-R8-001, PRD-R9-001, QA-R9-001, REL-R9-001 | Planned and regression-gated. | Mapped to one or more release-planning, implementation, or acceptance tasks. | 10
LID-VN-007 | R5 | PRD-R5-001, UX-R5-001, ARCH-R5-001, ENG-R5-001, REL-R5-001, QA-R8-001, REL-R8-001, PRD-R9-001, QA-R9-001, REL-R9-001 | Planned and regression-gated. | Mapped to one or more release-planning, implementation, or acceptance tasks. | 10
LID-UP-001 | R1 | PRD-R1-001, UX-R1-001, ARCH-R1-001, ENG-R1-001, REL-R1-001, QA-R8-001, REL-R8-001, PRD-R9-001, QA-R9-001, REL-R9-001 | Planned and regression-gated. | Mapped to one or more release-planning, implementation, or acceptance tasks. | 10
LID-UP-002 | R1 | PRD-R1-001, ARCH-R1-001, ENG-R1-001, REL-R1-001, QA-R8-001, REL-R8-001, PRD-R9-001, QA-R9-001, REL-R9-001 | Planned and regression-gated. | Mapped to one or more release-planning, implementation, or acceptance tasks. | 9
LID-UP-003 | R1 | PRD-R1-001, UX-R1-001, ARCH-R1-001, ENG-R1-001, REL-R1-001, QA-R8-001, REL-R8-001, PRD-R9-001, QA-R9-001, REL-R9-001 | Planned and regression-gated. | Mapped to one or more release-planning, implementation, or acceptance tasks. | 10
LID-UP-004 | Deferred | None — explicitly deferred | Explicitly deferred; no R0–R10 implementation task. | Blank composition and unsupported document/OCR ingestion remain outside R0–R10. | 0
LID-SRC-001 | R4 | PRD-R4-001, UX-R4-001, ARCH-R4-001, ENG-R4-001, REL-R4-001, QA-R8-001, REL-R8-001, PRD-R9-001, QA-R9-001, REL-R9-001 | Planned and regression-gated. | Mapped to one or more release-planning, implementation, or acceptance tasks. | 10
LID-SRC-002 | R4 | PRD-R4-001, UX-R4-001, ARCH-R4-001, ENG-R4-001, REL-R4-001, QA-R8-001, REL-R8-001, PRD-R9-001, QA-R9-001, REL-R9-001 | Planned and regression-gated. | Mapped to one or more release-planning, implementation, or acceptance tasks. | 10
LID-SRC-003 | R3 | PRD-R3-001, UX-R3-001, ARCH-R3-001, ENG-R3-001, REL-R3-001, QA-R8-001, REL-R8-001, PRD-R9-001, QA-R9-001, REL-R9-001 | Planned and regression-gated. | Mapped to one or more release-planning, implementation, or acceptance tasks. | 10
LID-SRC-004 | R4 | PRD-R4-001, UX-R4-001, ARCH-R4-001, ENG-R4-001, REL-R4-001, QA-R8-001, REL-R8-001, PRD-R9-001, QA-R9-001, REL-R9-001 | Planned and regression-gated. | Mapped to one or more release-planning, implementation, or acceptance tasks. | 10
LID-REF-001 | R1 | PRD-R1-001, UX-R1-001, ENG-R1-001, REL-R1-001, QA-R8-001, REL-R8-001, PRD-R9-001, QA-R9-001, REL-R9-001 | Planned and regression-gated. | Mapped to one or more release-planning, implementation, or acceptance tasks. | 9
LID-REF-002 | R3 | PRD-R3-001, UX-R3-001, ARCH-R3-001, ENG-R3-001, REL-R3-001, QA-R8-001, REL-R8-001, PRD-R9-001, QA-R9-001, REL-R9-001 | Planned and regression-gated. | Mapped to one or more release-planning, implementation, or acceptance tasks. | 10
LID-REF-003 | R3 | PRD-R3-001, UX-R3-001, ARCH-R3-001, ENG-R3-001, REL-R3-001, QA-R8-001, REL-R8-001, PRD-R9-001, QA-R9-001, REL-R9-001 | Planned and regression-gated. | Mapped to one or more release-planning, implementation, or acceptance tasks. | 10
LID-REF-004 | R1 | PRD-R1-001, UX-R1-001, ENG-R1-001, REL-R1-001, QA-R8-001, REL-R8-001, PRD-R9-001, QA-R9-001, REL-R9-001 | Planned and regression-gated. | Mapped to one or more release-planning, implementation, or acceptance tasks. | 9
LID-REF-005 | R1 | PRD-R1-001, UX-R1-001, ENG-R1-001, REL-R1-001, QA-R8-001, REL-R8-001, PRD-R9-001, QA-R9-001, REL-R9-001 | Planned and regression-gated. | Mapped to one or more release-planning, implementation, or acceptance tasks. | 9
LID-REF-006 | R1 | PRD-R1-001, UX-R1-001, ENG-R1-001, REL-R1-001, PRD-R3-001, UX-R3-001, ARCH-R3-001, ENG-R3-001, REL-R3-001, PRD-R6-001, UX-R6-001, ARCH-R6-001, ENG-R6-001, REL-R6-001, PRD-R7-001, UX-R7-001, ARCH-R7-001, ENG-R7-001, REL-R7-001, PRD-R8-001, ARCH-R8-001, QA-R8-001, REL-R8-001, PRD-R9-001, QA-R9-001, REL-R9-001 | Planned and regression-gated. | Mapped to one or more release-planning, implementation, or acceptance tasks. | 26
LID-REF-007 | R4 | PRD-R4-001, UX-R4-001, ARCH-R4-001, ENG-R4-001, ENG-R4-002, REL-R4-001, QA-R8-001, REL-R8-001, PRD-R9-001, QA-R9-001, REL-R9-001 | Planned and regression-gated. | Mapped to one or more release-planning, implementation, or acceptance tasks. | 11
LID-AIT-001 | R6 | EVAL-R6-001, PRD-R6-001, ARCH-R6-001, ENG-R6-001, REL-R6-001, QA-R8-001, REL-R8-001, PRD-R9-001, QA-R9-001, REL-R9-001 | Planned and regression-gated. | Mapped to one or more release-planning, implementation, or acceptance tasks. | 10
LID-AIT-002 | R6 | EVAL-R6-001, PRD-R6-001, UX-R6-001, ARCH-R6-001, ENG-R6-001, REL-R6-001, QA-R8-001, REL-R8-001, PRD-R9-001, QA-R9-001, REL-R9-001 | Planned and regression-gated. | Mapped to one or more release-planning, implementation, or acceptance tasks. | 11
LID-AIT-003 | R6 | EVAL-R6-001, PRD-R6-001, UX-R6-001, ARCH-R6-001, ENG-R6-001, REL-R6-001, QA-R8-001, REL-R8-001, PRD-R9-001, QA-R9-001, REL-R9-001 | Planned and regression-gated. | Mapped to one or more release-planning, implementation, or acceptance tasks. | 11
LID-AIT-004 | R6 | PRD-R6-001, UX-R6-001, ARCH-R6-001, ENG-R6-001, REL-R6-001, QA-R8-001, REL-R8-001, PRD-R9-001, QA-R9-001, REL-R9-001 | Planned and regression-gated. | Mapped to one or more release-planning, implementation, or acceptance tasks. | 10
LID-AIT-005 | R6 | PRD-R6-001, UX-R6-001, ARCH-R6-001, ENG-R6-001, REL-R6-001, QA-R8-001, REL-R8-001, PRD-R9-001, QA-R9-001, REL-R9-001 | Planned and regression-gated. | Mapped to one or more release-planning, implementation, or acceptance tasks. | 10
LID-AIT-006 | R6 | EVAL-R6-001, PRD-R6-001, ARCH-R6-001, ENG-R6-001, REL-R6-001, QA-R8-001, REL-R8-001, PRD-R9-001, QA-R9-001, REL-R9-001 | Planned and regression-gated. | Mapped to one or more release-planning, implementation, or acceptance tasks. | 10
LID-AIT-007 | R6 | EVAL-R6-001, PRD-R6-001, UX-R6-001, ARCH-R6-001, ENG-R6-001, REL-R6-001, QA-R8-001, REL-R8-001, PRD-R9-001, QA-R9-001, REL-R9-001 | Planned and regression-gated. | Mapped to one or more release-planning, implementation, or acceptance tasks. | 11
LID-AIA-001 | R7 | EVAL-R7-001, PRD-R7-001, ARCH-R7-001, ENG-R7-001, REL-R7-001, QA-R8-001, REL-R8-001, PRD-R9-001, QA-R9-001, REL-R9-001 | Planned and regression-gated. | Mapped to one or more release-planning, implementation, or acceptance tasks. | 10
LID-AIA-002 | R7 | PRD-R7-001, UX-R7-001, ARCH-R7-001, ENG-R7-001, REL-R7-001, QA-R8-001, REL-R8-001, PRD-R9-001, QA-R9-001, REL-R9-001 | Planned and regression-gated. | Mapped to one or more release-planning, implementation, or acceptance tasks. | 10
LID-AIA-003 | R7 | EVAL-R7-001, PRD-R7-001, UX-R7-001, ARCH-R7-001, ENG-R7-001, REL-R7-001, QA-R8-001, REL-R8-001, PRD-R9-001, QA-R9-001, REL-R9-001 | Planned and regression-gated. | Mapped to one or more release-planning, implementation, or acceptance tasks. | 11
LID-AIA-004 | R7 | PRD-R7-001, ARCH-R7-001, ENG-R7-001, REL-R7-001, QA-R8-001, REL-R8-001, PRD-R9-001, QA-R9-001, REL-R9-001 | Planned and regression-gated. | Mapped to one or more release-planning, implementation, or acceptance tasks. | 9
LID-AIA-005 | R7 | EVAL-R7-001, PRD-R7-001, UX-R7-001, ARCH-R7-001, ENG-R7-001, REL-R7-001, QA-R8-001, REL-R8-001, PRD-R9-001, QA-R9-001, REL-R9-001 | Planned and regression-gated. | Mapped to one or more release-planning, implementation, or acceptance tasks. | 11
LID-AIA-006 | R7 | EVAL-R7-001, PRD-R7-001, UX-R7-001, ARCH-R7-001, ENG-R7-001, REL-R7-001, QA-R8-001, REL-R8-001, PRD-R9-001, QA-R9-001, REL-R9-001 | Planned and regression-gated. | Mapped to one or more release-planning, implementation, or acceptance tasks. | 11
LID-AIA-007 | R7 | PRD-R7-001, UX-R7-001, ARCH-R7-001, ENG-R7-001, REL-R7-001, QA-R8-001, REL-R8-001, PRD-R9-001, QA-R9-001, REL-R9-001 | Planned and regression-gated. | Mapped to one or more release-planning, implementation, or acceptance tasks. | 10
LID-AIA-008 | R7 | PRD-R7-001, UX-R7-001, ARCH-R7-001, ENG-R7-001, REL-R7-001, QA-R8-001, REL-R8-001, PRD-R9-001, QA-R9-001, REL-R9-001 | Planned and regression-gated. | Mapped to one or more release-planning, implementation, or acceptance tasks. | 10
LID-AIA-009 | R7 | PRD-R7-001, UX-R7-001, ARCH-R7-001, ENG-R7-001, REL-R7-001, QA-R8-001, REL-R8-001, PRD-R9-001, QA-R9-001, REL-R9-001 | Planned and regression-gated. | Mapped to one or more release-planning, implementation, or acceptance tasks. | 10
LID-AIA-010 | R7 | PRD-R7-001, UX-R7-001, ARCH-R7-001, ENG-R7-001, REL-R7-001, QA-R8-001, REL-R8-001, PRD-R9-001, QA-R9-001, REL-R9-001 | Planned and regression-gated. | Mapped to one or more release-planning, implementation, or acceptance tasks. | 10
LID-AIA-011 | R7 | EVAL-R7-001, PRD-R7-001, ARCH-R7-001, ENG-R7-001, REL-R7-001, QA-R8-001, REL-R8-001, PRD-R9-001, QA-R9-001, REL-R9-001 | Planned and regression-gated. | Mapped to one or more release-planning, implementation, or acceptance tasks. | 10
LID-OPS-001 | R0 | SPK-R0-001, PRD-R0-001, UX-R0-001, ARCH-R0-001, ENG-R0-001, REL-R0-001, QA-R8-001, REL-R8-001, PRD-R9-001, QA-R9-001, REL-R9-001 | Planned and regression-gated. | Mapped to one or more release-planning, implementation, or acceptance tasks. | 11
LID-OPS-002 | R0 | SPK-R0-001, PRD-R0-001, ARCH-R0-001, ENG-R0-001, REL-R0-001, QA-R8-001, REL-R8-001, PRD-R9-001, QA-R9-001, REL-R9-001 | Planned and regression-gated. | Mapped to one or more release-planning, implementation, or acceptance tasks. | 10
LID-OPS-003 | R0 | SPK-R0-001, PRD-R0-001, ARCH-R0-001, ENG-R0-001, REL-R0-001, QA-R8-001, REL-R8-001, PRD-R9-001, QA-R9-001, REL-R9-001 | Planned and regression-gated. | Mapped to one or more release-planning, implementation, or acceptance tasks. | 10
LID-OPS-004 | R0 | SPK-R0-001, PRD-R0-001, ARCH-R0-001, ENG-R0-001, REL-R0-001, QA-R8-001, REL-R8-001, PRD-R9-001, QA-R9-001, REL-R9-001 | Planned and regression-gated. | Mapped to one or more release-planning, implementation, or acceptance tasks. | 10
LID-OPS-005 | R2 | PRD-R2-001, ARCH-R2-001, ENG-R2-001, REL-R2-001, QA-R8-001, REL-R8-001, PRD-R9-001, QA-R9-001, REL-R9-001 | Planned and regression-gated. | Mapped to one or more release-planning, implementation, or acceptance tasks. | 9
LID-OPS-006 | R8 | PRD-R8-001, ARCH-R8-001, QA-R8-001, REL-R8-001, PRD-R9-001, QA-R9-001, REL-R9-001, PID-R10-001, ARCH-R10-001, REL-R10-001 | Planned and regression-gated. | Mapped to one or more release-planning, implementation, or acceptance tasks. | 10
LID-OPS-007 | R9 | QA-R8-001, REL-R8-001, PRD-R9-001, QA-R9-001, REL-R9-001, PID-R10-001, ARCH-R10-001, REL-R10-001 | Planned and regression-gated. | Mapped to one or more release-planning, implementation, or acceptance tasks. | 8
LID-OPS-008 | R0 | SPK-R0-001, PRD-R0-001, ARCH-R0-001, ENG-R0-001, REL-R0-001, QA-R8-001, REL-R8-001, PRD-R9-001, QA-R9-001, REL-R9-001, PID-R10-001, ARCH-R10-001, REL-R10-001 | Planned and regression-gated. | Mapped to one or more release-planning, implementation, or acceptance tasks. | 13
LID-OPS-009 | R2 | PRD-R2-001, ARCH-R2-001, ENG-R2-002, REL-R2-001, QA-R8-001, REL-R8-001, PRD-R9-001, QA-R9-001, REL-R9-001 | Planned and regression-gated. | Mapped to one or more release-planning, implementation, or acceptance tasks. | 9
LID-OPS-010 | R4 | PRD-R4-001, UX-R4-001, ARCH-R4-001, ENG-R4-002, REL-R4-001, QA-R8-001, REL-R8-001, PRD-R9-001, QA-R9-001, REL-R9-001 | Planned and regression-gated. | Mapped to one or more release-planning, implementation, or acceptance tasks. | 10
LID-OPS-011 | R0 | SPK-R0-001, PRD-R0-001, ARCH-R0-001, ENG-R0-001, REL-R0-001, PRD-R1-001, ARCH-R1-001, ENG-R1-001, REL-R1-001, PRD-R2-001, ARCH-R2-001, ENG-R2-001, ENG-R2-002, REL-R2-001, PRD-R3-001, ARCH-R3-001, ENG-R3-001, REL-R3-001, PRD-R4-001, ARCH-R4-001, ENG-R4-001, ENG-R4-002, REL-R4-001, PRD-R5-001, ARCH-R5-001, ENG-R5-001, REL-R5-001, PRD-R6-001, ARCH-R6-001, ENG-R6-001, REL-R6-001, PRD-R7-001, ARCH-R7-001, ENG-R7-001, REL-R7-001, PRD-R8-001, ARCH-R8-001, QA-R8-001, REL-R8-001, PRD-R9-001, QA-R9-001, REL-R9-001, PID-R10-001, ARCH-R10-001, REL-R10-001 | Planned and regression-gated. | Mapped to one or more release-planning, implementation, or acceptance tasks. | 45
LID-OPS-012 | R0 | SPK-R0-001, PRD-R0-001, UX-R0-001, ARCH-R0-001, ENG-R0-001, REL-R0-001, QA-R8-001, REL-R8-001, PRD-R9-001, QA-R9-001, REL-R9-001 | Planned and regression-gated. | Mapped to one or more release-planning, implementation, or acceptance tasks. | 11
LID-OPS-013 | R4 | PRD-R4-001, UX-R4-001, ARCH-R4-001, ENG-R4-002, REL-R4-001, QA-R8-001, REL-R8-001, PRD-R9-001, QA-R9-001, REL-R9-001 | Planned and regression-gated. | Mapped to one or more release-planning, implementation, or acceptance tasks. | 10
LID-OPS-014 | R0 | SPK-R0-001, PRD-R0-001, UX-R0-001, ARCH-R0-001, ENG-R0-001, REL-R0-001, PRD-R8-001, ARCH-R8-001, QA-R8-001, REL-R8-001, PRD-R9-001, QA-R9-001, REL-R9-001, PID-R10-001, ARCH-R10-001, REL-R10-001 | Planned and regression-gated. | Mapped to one or more release-planning, implementation, or acceptance tasks. | 16
LID-OPS-015 | R2 | PRD-R2-001, UX-R2-001, ARCH-R2-001, ENG-R2-001, REL-R2-001, PRD-R5-001, UX-R5-001, ARCH-R5-001, ENG-R5-001, REL-R5-001, QA-R8-001, REL-R8-001, PRD-R9-001, QA-R9-001, REL-R9-001 | Planned and regression-gated. | Mapped to one or more release-planning, implementation, or acceptance tasks. | 15
LID-OPS-016 | R0 | SPK-R0-001, PRD-R0-001, ARCH-R0-001, ENG-R0-001, REL-R0-001, QA-R8-001, REL-R8-001, PRD-R9-001, QA-R9-001, REL-R9-001 | Planned and regression-gated. | Mapped to one or more release-planning, implementation, or acceptance tasks. | 10
LID-OPS-017 | R6 | EVAL-R6-001, PRD-R6-001, UX-R6-001, ARCH-R6-001, ENG-R6-001, REL-R6-001, EVAL-R7-001, PRD-R7-001, UX-R7-001, ARCH-R7-001, ENG-R7-001, REL-R7-001, QA-R8-001, REL-R8-001, PRD-R9-001, QA-R9-001, REL-R9-001 | Planned and regression-gated. | Mapped to one or more release-planning, implementation, or acceptance tasks. | 17
LID-OPS-018 | R0 | SPK-R0-001, PRD-R0-001, UX-R0-001, ARCH-R0-001, ENG-R0-001, REL-R0-001, PRD-R1-001, ARCH-R1-001, ENG-R1-001, REL-R1-001, PRD-R2-001, ARCH-R2-001, ENG-R2-001, ENG-R2-002, REL-R2-001, PRD-R3-001, ARCH-R3-001, ENG-R3-001, REL-R3-001, PRD-R4-001, ARCH-R4-001, ENG-R4-001, ENG-R4-002, REL-R4-001, PRD-R5-001, ARCH-R5-001, ENG-R5-001, REL-R5-001, PRD-R6-001, ARCH-R6-001, ENG-R6-001, REL-R6-001, PRD-R7-001, ARCH-R7-001, ENG-R7-001, REL-R7-001, PRD-R8-001, ARCH-R8-001, QA-R8-001, REL-R8-001, PRD-R9-001, QA-R9-001, REL-R9-001, PID-R10-001, ARCH-R10-001, REL-R10-001 | Planned and regression-gated. | Mapped to one or more release-planning, implementation, or acceptance tasks. | 46
LID-DEF-001 | Deferred | None — explicitly deferred | Explicitly deferred; no R0–R10 implementation task. | Historical VoiceNotes import is deferred. | 0
LID-DEF-002 | Deferred | None — explicitly deferred | Explicitly deferred; no R0–R10 implementation task. | Coaching, themes, streaks, reminders, and resurfacing are deferred. | 0
LID-DEF-003 | Deferred | None — explicitly deferred | Explicitly deferred; no R0–R10 implementation task. | Semantic, conversational, and question-answering retrieval is deferred. | 0
LID-DEF-004 | Deferred | None — explicitly deferred | Explicitly deferred; no R0–R10 implementation task. | Year mosaic, media wall, maps, and native/offline applications are deferred. | 0
LID-DEF-005 | Deferred | None — explicitly deferred | Explicitly deferred; no R0–R10 implementation task. | PDF/Word/OCR ingestion, books/printing, and immutable export are deferred. | 0
LID-DEF-006 | Deferred | None — explicitly deferred | Explicitly deferred; no R0–R10 implementation task. | Additional or fuzzy VoiceNotes tag eligibility is deferred. | 0

## Risks & Gates
Delivery Risks, Assumptions, Dependencies, and Release Gates | Delivery Risks, Assumptions, Dependencies, and Release Gates | Delivery Risks, Assumptions, Dependencies, and Release Gates | Delivery Risks, Assumptions, Dependencies, and Release Gates | Delivery Risks, Assumptions, Dependencies, and Release Gates | Delivery Risks, Assumptions, Dependencies, and Release Gates | Delivery Risks, Assumptions, Dependencies, and Release Gates | Delivery Risks, Assumptions, Dependencies, and Release Gates
Delivery Risks, Assumptions, Dependencies, and Release Gates | Delivery Risks, Assumptions, Dependencies, and Release Gates | Delivery Risks, Assumptions, Dependencies, and Release Gates | Delivery Risks, Assumptions, Dependencies, and Release Gates | Delivery Risks, Assumptions, Dependencies, and Release Gates | Delivery Risks, Assumptions, Dependencies, and Release Gates | Delivery Risks, Assumptions, Dependencies, and Release Gates | Delivery Risks, Assumptions, Dependencies, and Release Gates
Risk responses preserve privacy, recovery, accessibility, and co-resident safety before schedule. Unknown live/provider facts remain evidence-gated. | Risk responses preserve privacy, recovery, accessibility, and co-resident safety before schedule. Unknown live/provider facts remain evidence-gated. | Risk responses preserve privacy, recovery, accessibility, and co-resident safety before schedule. Unknown live/provider facts remain evidence-gated. | Risk responses preserve privacy, recovery, accessibility, and co-resident safety before schedule. Unknown live/provider facts remain evidence-gated. | Risk responses preserve privacy, recovery, accessibility, and co-resident safety before schedule. Unknown live/provider facts remain evidence-gated. | Risk responses preserve privacy, recovery, accessibility, and co-resident safety before schedule. Unknown live/provider facts remain evidence-gated. | Risk responses preserve privacy, recovery, accessibility, and co-resident safety before schedule. Unknown live/provider facts remain evidence-gated. | Risk responses preserve privacy, recovery, accessibility, and co-resident safety before schedule. Unknown live/provider facts remain evidence-gated.
ID | Type | Milestone | Risk / assumption / dependency | Owner | Trigger | Response | Status
RAID-001 | Risk | R0 | Shared-host contention or namespace/routing collision harms an existing service. | Technical Architect | R0 entry/exit | Synthetic-only live preflight, limits, non-regression, and rollback; block R1 on failure. | Open
RAID-002 | Assumption | R0 | SQLCipher/SQLite works with FTS5, WAL concurrency, backup, migration, and crash recovery in the target runtime. | Technical Architect | R0 | Execute target proof; select PostgreSQL only if documented gates fail. | Open
RAID-003 | Dependency | R0 | Human and callback routing require approved Cloudflare configuration. | Technical Architect / Owner | R0 deploy | Prepare sanitized plan; make provider mutations only in the scoped execution step. | Open
RAID-004 | Risk | All | A successful backup upload is mistaken for recovery evidence. | Project Manager | Every release | Require executed restore for each new shape and full Recovery Ceremony at R9. | Open
RAID-005 | Dependency | R5 | VoiceNotes identity, authentication, and reconciliation behavior is partly unknown. | Product + Architecture | R5 entry | Synthetic contract spike; block R5 and reopen decisions on material failure. | Open
RAID-006 | Risk | R2/R6/R7 | Real photos or derived photo data reach AI. | Architecture + QA | R2, R6, R7 | Typed allowlists, structural no-photo tests, sanitized evidence, release block on leakage. | Open
RAID-007 | Risk | All | Proposed dates become commitments and weaken gates. | Project Manager | Weekly | Move dates before weakening privacy, recovery, accessibility, or evidence gates. | Open
RAID-008 | Risk | R2/R8 | Small-host image work exhausts memory or disk. | Technical Architect | R2 and R8 | Bounded staging/decoder, one heavy job, watermarks, backpressure, and fault tests. | Open
RAID-009 | Risk | R6/R7 | AI output is mistaken for authentic source truth. | Product + Design + QA | R6 and R7 | Separate records, persistent labels, provenance, protected fields, and owner acceptance. | Open
RAID-010 | Risk | R10 | Object-store transition starts without a measured need or recovery proof. | Project Manager | R10 | Keep dates blank; require trigger, inventory, dual-write, restore, observation, and rollback. | Open
RAID-011 | Risk | All | A task starts from shared plans or roadmap status without task-specific Product Council readiness. | Project Manager | Every task entry | Require six P0-prefixed task artifacts, exact hashes/revision, five-seat verdict, and executionAllowed=true. | Open — all 58 dossiers Incomplete
RAID-012 | Risk | P0 | Broad Project views or unreadable workflows admit non-delivery items or change status unexpectedly. | Project Manager | GitHub synchronization | Narrow views one at a time to phase1; do not mutate unreadable workflows; verify exact issue/field parity after publication. | Open — live hardening pending
Milestone entry and exit gates | Milestone entry and exit gates | Milestone entry and exit gates | Milestone entry and exit gates | Milestone entry and exit gates | Milestone entry and exit gates | Milestone entry and exit gates | Milestone entry and exit gates
Milestone | Release | Start | Target | Entry dependency | Exit evidence | Rollback/restore rule | Decision state
P0 | Council Planning Baseline | 2026-08-14 | 2026-08-16 | None | Council reviews, source hashes, requirement coverage, workbook, and GitHub roadmap agree. | Planning evidence only; no production mutation. | Hold — control candidate under review
R0 | Shared-Host Private Foundation | 2026-08-17 | 2026-08-28 | P0 accepted | Owner access/denial, sanitized capacity and non-regression evidence, encrypted synthetic restore, and rollback proof. | Restore every new persistent shape and prove reversible rollback before acceptance. | Hold — task dossiers Incomplete
R1 | Manual Journal Archive | 2026-08-31 | 2026-09-18 | R0 accepted | An owner-approved text fixture survives ingestion, restart, backup, restore, and export/checksum validation. | Restore every new persistent shape and prove reversible rollback before acceptance. | Hold — task dossiers Incomplete
R2 | Telegram Photo Capture | 2026-09-21 | 2026-10-09 | R1 accepted | Authorization, invalid media/date, album, duplicate, cover, Original, privacy, backup, and restore fixtures pass. | Restore every new persistent shape and prove reversible rollback before acceptance. | Hold — task dossiers Incomplete
R3 | Retrieval and Date Integrity | 2026-10-12 | 2026-10-30 | R2 accepted | Known queries work without leakage and a redated item updates both days and restored indexes atomically. | Restore every new persistent shape and prove reversible rollback before acceptance. | Hold — task dossiers Incomplete
R4 | Source History and Lifecycle Safety | 2026-11-02 | 2026-11-20 | R3 accepted | Three conflict outcomes and delete/restore/export/import invariants pass across every existing data shape. | Restore every new persistent shape and prove reversible rollback before acceptance. | Hold — task dossiers Incomplete
R5 | Prospective VoiceNotes Sync | 2026-11-23 | 2026-12-11 | R4 accepted and VoiceNotes synthetic contract spike passes | Synthetic contract, activation, eligibility, dating, replay, suppression, upstream revision, and restore gates pass. | Restore every new persistent shape and prove reversible rollback before acceptance. | Hold — task dossiers Incomplete
R6 | Generated Text Reflection | 2026-12-14 | 2027-01-08 | R5 accepted and text-model evaluation passes | Evaluation, typed privacy allowlist, field protection, source-race, failure, spend, and restore gates pass. | Restore every new persistent shape and prove reversible rollback before acceptance. | Hold — task dossiers Incomplete
R7 | Generated Artwork | 2027-01-11 | 2027-01-29 | R6 accepted and artwork-model evaluation passes | Evaluation, safety, cost, lifecycle, labeling, privacy, cover, and restore gates pass. | Restore every new persistent shape and prove reversible rollback before acceptance. | Hold — task dossiers Incomplete
R8 | Operational Scale and Resilience | 2027-02-01 | 2027-02-19 | R0 through R7 accepted | Watermark, restart, alert, fault, backup/restore, security, browser, and accessibility evidence passes. | Restore every new persistent shape and prove reversible rollback before acceptance. | Hold — task dossiers Incomplete
R9 | Private Launch Acceptance and Stabilization | 2027-02-22 | 2027-03-12 | R8 accepted and explicit launch authority | Owner UAT, Recovery Ceremony, observation window, severity gate, and go/no-go or rollback record pass. | Restore every new persistent shape and prove reversible rollback before acceptance. | Hold — task dossiers Incomplete
R10 | Conditional Object-store Transition |  |  | Measured storage trigger; no calendar commitment | Trigger, inventory, dual-write, reconciliation, restore, observed reads, cutover, and rollback gates pass. | Restore every new persistent shape and prove reversible rollback before acceptance. | Trigger not approved; dates blank

## Review Guide
Workbook Review Guide and Evidence Boundary | Workbook Review Guide and Evidence Boundary | Workbook Review Guide and Evidence Boundary
Workbook Review Guide and Evidence Boundary | Workbook Review Guide and Evidence Boundary | Workbook Review Guide and Evidence Boundary
Use this workbook to review the plan; use the JSON manifest as the edit source. Reconcile any approved change to Markdown, GitHub issues, and the live Project. | Use this workbook to review the plan; use the JSON manifest as the edit source. Reconcile any approved change to Markdown, GitHub issues, and the live Project. | Use this workbook to review the plan; use the JSON manifest as the edit source. Reconcile any approved change to Markdown, GitHub issues, and the live Project.
Topic | Decision / instruction | Reviewer note
Purpose | Detailed reviewable Phase 1 release plan for a single-user private archive. | Owner: Project Manager
Source manifest SHA-256 | sha256:e312399a16a72a8030e5735413270af989c0295c50b73ce0a9ecf4e02406c166 | docs/project/PHASE1-ROADMAP-MANIFEST.json — do not use a workbook-only edit as a planning decision.
Governing product | docs/product/PRODUCT-REQUIREMENTS.md | 78 stable requirement IDs.
Governing design | docs/design/UX-SPECIFICATION.md | Prototype v5 is interaction intent only.
Implementation plan | docs/architecture/PHASE1-IMPLEMENTATION-PLAN.md | Detailed technical sequence, architecture, security, recovery, and task contracts.
Task Definition of Ready | docs/council/execution/P0-PHASE1-TASK-DEFINITION-OF-READY.md | Every substantive task requires Product, Architecture, Design, QA, Delivery, and Council approval.
Task artifact register | docs/project/P0-PHASE1-TASK-ARTIFACT-REGISTER.json | Paths, states, SHA-256, scenario IDs, owner actions, execution scope, and council decision.
Current task readiness | 58 Incomplete; 45 Hold + 13 Historical non-authorizing; 0 Ready; 0 execution-allowed | Artifact generation is not specialist approval; roadmap status is not a start override.
GitHub projection | 58 existing issues; 17 managed Project fields; six dossier links per task | Publish only from merged remote main, then verify read-only by stable task ID.
Deployment spike | docs/research/HETZNER-SHARED-HOST-DEPLOYMENT-SPIKE.md | Live host capacity/readiness remains unverified until sanitized evidence exists.
Roadmap | https://github.com/users/arunpr614/projects/1 | Four lanes: Backlog, Next, In progress, Done.
Date semantics | Start/Target are proposed estimates in Asia/Kolkata. | Evidence gates move dates; dates never weaken gates.
R0 | Synthetic fixtures only. | No authentic memory may enter before R0 restore/rollback/privacy proof.
R1 | First authentic-memory release. | Use only an owner-approved fixture after R0 acceptance.
R10 | Start/Target intentionally blank. | Populate only after measured watermark trigger approval.
Done — planning | Named planning artifact exists and validates. | Does not imply implementation, testing, deployment, production, or release acceptance.
Done — delivery | Behavior works in the named environment with linked tests, migration, restore, rollback, and approvals. | Code, CI, deploy, or backup upload alone is insufficient.
Privacy | No personal content, prompts, tokens, credentials, private account IDs, or unsanitized infrastructure evidence in public artifacts. | Real-photo data is structurally excluded from all AI requests.
Recovery | Every release restores each new persistent data shape. | Backup success is not restore evidence.
Workbook sheets | Executive Summary; Release Plan; Roadmap Tasks; Roadmap Timeline; Requirement Map; Risks & Gates; Review Guide. | Filters, validations, formulas, conditional formatting, and charts support review.